## Future gate
| NSI - Training Management System |  | 2019-06-04
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 10 | 10
| Business Analysis | 32 | 4 | Sr Developer | 1 | 45 | 45 | 154.25 | 120.125 | 154.25 | 105
| Project Management | 121 | 15.125 | Jr Developer | 1 | 60 | 60
| Design and Prototype | 80 | 10 | PM | 1 | 15.125 | 15.125
| Documentation (SRS, FS, Weekly Reports,User Manual) | 64 | 8 | BA | 1 | 4 | 4
| Development |  |  | TechWriter | 1 | 8 | 8
| Application Basic Setup | 8 | 1 | QA | 1 | 71.5 | 71.5
| Active Directory Integration | 16 | 2
| Company Module |  |  | Total |  |  | 213.625
| Company Registration | 12 | 1.5
| Company Login | 6 | 0.75 | Total Delivery days | 141.5
| Company Dashboard | 20 | 2.5 | Total Effort | 213.625
| Manage Applicants | 16 | 2
| Company Application Request | 16 | 2
| Company Application View | 16 | 2
| Company Schedule View | 16 | 2
| Company Evaluation View | 16 | 2
| Company Notices View | 16 | 2
| Order (Payment) History | 16 | 2
| Attempt Survey | 16 | 2
| Chat Module (Integration only) | 8 | 1
Guards Module
| Login/Logout | 4 | 0.5
| Dashboard | 8 | 1
| View Training Schedule | 6 | 0.75
| Online Exam | 24 | 3
| Survey | 4 | 0.5
| View Certificates | 4 | 0.5
| Course material - Download | 8 | 1
NSI Admin Module
| Login/Logout | 4 | 0.5
| Dashboard | 24 | 3
| Company Management | 32 | 4
| Company Notice Management | 20 | 2.5
| Course Management | 40 | 5
| Notebook Management | 32 | 4
| Email/SMS Template Management | 24 | 3
| Process Application Requests/Course scheduling | 56 | 7
| Schedule Status Update | 56 | 7
| Evaluation/Survey Results | 48 | 6
| Update Guard License | 40 | 5
| Issue Notebooks | 32 | 4
| Violation in Notebooks | 32 | 4
| Manage Dump Data | 24 | 3
| Manage Restored guards | 16 | 2
| Reports (8) | 96 | 12
| Online Examination Module | 32 | 4
Master Management
| User Management | 20 | 2.5
| Business Unit | 8 | 1
| Answer legend | 8 | 1
| Classroom Management | 8 | 1
| Schedule Management | 8 | 1
| Course Category Management | 8 | 1
| Survey Module | 32 | 4
| Chat Module | 2 | 0.25
NSI Account Users Module
| Login/Logout | 4 | 0.5
| Dasboard | 8 | 1
| Coupon Management | 32 | 4
| Issue Coupons to Companies | 24 | 3
| Reports (3) | 36 | 4.5
NSI Instructors Module
| Login/Logout | 4 | 0.5
| Dasboard | 8 | 1
| Attendance Management * | 32 | 4
| Evaluation Management | 40 | 5
| Notebook Acknowledgement | 24 | 3
Police Module
| Login/Logout | 4 | 0.5
| Dasboard | 8 | 1
| Conduct Interview | 24 | 3
Others - Done by super admin?
| Login/Logout | 4 | 0.5
| Dasboard | 8 | 1
| Notification management | 16 | 2
Quality Assurance
31 | QA & Bug Fixing | 516 | 64.5
32 | UAT | 40 | 5
33 | Deployment per instance | 16 | 2
| Total Effort | 2103 | 262.875
Estimated hours may change with detailed system study
Assumptions
Passport place of issue - values will be provided by Client
Payment Gateway integration details will be provided
Chat Module will be a 3rd party tool
SMS gateway should be provided
Attachments(Course Material), if in case its large size file, the course mterial will be uploaded directly to FTP and the path of the file shall be linked with respective course
Reports will have only tabular data
Active directory details environment will be shared by Client
Integration with Biometric system for attendance - details should be provided