## TRC
| Tax Residency Certificate System |  | 16/04/2019
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 15 | 15
| Business analysis | 80 | 10 | Senior Developer | 1 | 25 | 25 | 38.75 | 64.75 | 59.75 | 59.75
| Project Management | 40 | 5 | junior Developer | 1 | 34.75 | 34.75
| Design and Prototype | 120 | 15 | PM | 1 | 5 | 5
| Documentation(FS, SRS, User Manual) | 32 | 4 | BA | 1 | 10 | 10
| Development |  |  | Tech writer | 1 | 4 | 4
| Application basic setup | 40 | 5 | QA | 1 | 18.5 | 18.5
| Front End - Issue Certificate |  |  | Total |  |  | 112.25
| Registration | 48 | 6
| Basic Information |  |  | Delivery days | 93.25
| Initial Payment |  |  | total effort | 112.25 | additional 2 days for deployment
| Login | 8 | 1
| Certificate Issual | 48 | 6 | Task | Days
| Select Certificate type |  |  | PSD Design | 3
| Upload necessary documents |  |  | HTML (En,Ar) | 12
Payment of Certificate Fees
On approval, send certificate in mail
Admin End - Super Admin
| Login | 4 | 0.5
| Manage document types master (passport,ID, Salary etc) | 6 | 0.75
| Manage users (Admins/Managers) | 8 | 1
| View Users | 48 | 6
Registered Users in application
Payment details
View paid users and payment details
In case of Reject - return certificate fees
| Dashboard/Reports | 24 | 3
Admin End - Admins/Manager
| Login | 4 | 0.5
| Users | 40 | 5
View Users, verify documents according to the certificate
Change user status - Approve/Reject/Return
| View and Delete non-paid users | 8 | 1
| Dashboard/Reports | 24 | 3
Other
| UIPath RPA automation | 168 | 21
OCR Abbyy Flexicapture OCR distributed engine
Quality Assurance
120 | QA & Bug Fixing | 108 | 13.5
121 | UAT | 40 | 5
122 | Deployment per instance | 16 | 2
| Total Effort | 914 | 114.25
Actual hours may change according to the detailed requirement analysis
Assumptions
1 | RFP - The system should be fully automated to minimize human intervention
2 | If there is any doument validating software, the admin/manager part can be omitted
3 | Application will be reponsive for Mobile view
4 | The data should be stored in MOF Data Lake platform – Cloudera and all the reporting should be done through MOF Tableau application - Necessary help will be available from client
5 | The payment is initially done before the processing of certificate.
6 | The system needs to be integrated with MOF e-dirham payment gateway (the same as the current system) - return policy is available for payment return in case of rejected application

## TRC-mobile
| Tax Residency Certificate System |  | 16/04/2019
|  | iOS |  | Android |  |  | No | Man Days | Total Effort
| Module | Hours | Man Days | Hours | Man Days | Designer | 1 | 1.5 | 1.5
| Design and prototype | 12 | 1.5 | 12 | 1.5 | Senior Developer | 1 | 4.5 | 4.5
| Development |  |  |  |  | junior Developer | 1 | 6 | 6
| Application basic setup | 8 | 1 | 8 | 1 | PM |  |  | 0
| Front End - Issue Certificate |  |  |  |  | BA |  |  | 0
| Registration |  |  |  |  | Tech writer |  |  | 0
| Basic Information | 8 | 1 | 8 | 1 | QA | 1 | 2.375 | 2.375
| Initial Payment | 8 | 1 | 8 | 1 | Total |  |  | 14.375
| Login | 4 | 0.5 | 4 | 0.5
| Select Certificate type | 8 | 1 | 8 | 1 | Delivery days | 12.875
| Upload necessary documents | 8 | 1 | 8 | 1 | total effort | 14.375 | 1 day for deployment
| Payment of Certificate Fees | 4 | 0.5 | 4 | 0.5
| Push Notification | 12 | 1.5 | 12 | 1.5 | Task | Days
| Payment gateway integration | 24 | 3 | 24 | 3 | Design(Android+iOS) | 3
Quality Assurance
120 | QA & Bug Fixing | 3 | 0.375 | 3 | 0.375
121 | UAT | 16 | 2 | 16 | 2
122 | Deployment per instance | 8 | 1 | 8 | 1
| Total Effort | 123 | 15.375 | 123 | 15.375
This estimation is only for native application
This estimation is to develop an application from the beginning
This estimation is to be considered for operation of mobile phones only in protrait mode
On changes in requirement the estimation might change