## TekZone
| Lube System |  | 2019-08-04
Monday
| Module | Hours | Man Days |  | No of resources | Man Days | Adjusted Del Days | Total Effort
| Initiation |  |  | Designer | 1 | 4 | 4 | 4
1 | Business analysis | 32 | 4 | Developer | 1.5 | 35 | 23.3333 | 35 | #REF! | 38.45 | 34.5
2 | SRS | 16 | 2 | PM | 1 | 3.45 | 3.45 | 3.45
| UI/UX | 32 | 4 | BA | 1 | 6 | 6 | 6
3 | Project Management | 27.6 | 3.45 | QA | 1.5 | 12.075 | 8.05 | 12.075
| Design and Development |  |  |  | Sum |  |  | 60.525
Maintain Lube Change Intervals
1 | Capture Vehicle make, model, Year, Cylinder, Oil Capacity, Last Svc date, KM, Next Svc date, KM, Interval and defects observed | 8 | 1 | [8 empty] | Initiation | 39
| Manage Customer Information |  |  | Delivery Days | 35.3833 | [6 empty] | F&V | 70
2 | Customer information ( Name, gender, Mobile no, Vehicle reg. #, Make, Model, Year, Cust. Age & Nationality | 8 | 1 | Total Effort | 60.525 | [6 empty] | Bakery | 44
3 | Map customer & vehicle. Generate reports | 12 | 1.5 | [8 empty] | Butchery | 19
| Sales Transaction | [10 empty] | qa & Bug Fixing | 45
4 | Cash | 6 | 0.75 | Task Breakdown | Days | [7 empty] | 217
5 | ADNOC Wallet | 20 | 2.5 | Initiation | 13.45
6 | RAHAL | 20 | 2.5 | F&V | 25.5
7 | Credit / Debit Cards (@2.5 days / agency) | 20 | 2.5 | Bakery | #REF!
8 | POS <-> Lube system integration via API | 20 | 2.5 | Butchery | 9
| Site back Office integration |  |  | Common & System features | #REF!
9 | Price Book Requirments: Site Back Office <-> Lube System integration via API | 12 | 1.5 | QA & Bug fixing | 12.075
10 | End of Shift Requirments: Site Back Office <-> Lube System integration via API : Nozzle meters, product stock, Lube system configuration | 12 | 1.5 | Total Effort | #REF!
Product Safety
11 | Alarm generation | 4 | 0.5
12 | Stock recording | 6 | 0.75
13 | Suspicious transactions | 8 | 1
Admin Features
14 | Users / Roles | 12 | 1.5
15 | Manage Reward vouchers | 16 | 2
16 | Setup system to accept promotions | 20 | 2.5
Integration with Octane POS
17 | Shift control and accounting | 12 | 1.5
18 | Attendant Cash accounting | 12 | 1.5
19 | Acceptance of reward vouchers | 12 | 1.5
20 | Redeem promotions | 12 | 1.5
System Features
21 | Auditing and logging | 8 | 1
22 | Exception Handling | 8 | 1
23 | Authetication and Authorization | 8 | 1
48 | QA & Bug Fixing | 96.6 | 12.075
| Total Effort | 480.2 | 60.025
3.0013
[11 empty] | #REF! | 0

## Sheet2
F&V ordering System
1. Import files (order support, daily sales, promotions)
2. Normalize and fit data to target DB (Our Database)
3. Upload Quotation file
4. Edit quotation file
5. Repeat step 2 (if necessary)
6. Generate summary information for Avg. sales, promotion Sales History etc for all items (Fruits and Vegetables only) sold in store
7. Generate summary information for a time series (hourly, daily, monthly, yearly, date ranges, time ranges etc)
8. Create holiday calendar
9. Create promotions
10. Check inventory in DC
11. Block Suppliers when inventory is available is DC
12. Place orders in DC
13. View supplier Rates and Qty available when item not present in DC
14. Recommend supplier based on past history (or some other criterion
15. Reports with multiple filters exportable to word, pdf or excell
16. Order creation API calls to GIMA, GICA
17. Responsive and bilingual Mobile tablet app
18. Manage local Item inventory (Price, qty, margin, promotion, sold, unsold, daily inventory requirements, throw aways etc)
19. Consolidate daily transactions and push to source (GICA , GIMA)
Development Time Frame: 30 working man days (one 1/2 month)
Butchery Product Estimate System
1. File Imports from Carrefour (sales, mappings, promotions, Hourly sales)
2. Scrub, Normalize and fit data to target (Our database)
2. Define products (meat cuts, types-chicken, fish, lamb, cow; portion sizes)
3. Identify availability and daily requirements (estimates)
4. Generate summary information
5. predictions based on past information (daily, promotions, holidays etc)
6. Identify cheapest meat cut for minced meat (to get optimum cost)
7. Manage waste
8. Push EOD data to GICA
9. Generate multi-format reports with multiple filters and orderings
10. API integration with source and target systems
11. Update source systems (GICA, GIMA) with daily sales and inventory data
Development Time Frame: 15 working man days
Cumulative Total : 9 weeks
Bakery Product Estimate System
1. File Imports from Carrefour ( promotions, daily sales, hourly sales, recipe packing details, waste details)
2. Scrub, normalize and fit data to target
3. Generate Historical data
4. Estimate daily requirements based on historical data
5. Create recipe with ingredient quantity
6. Generate raw material quantity of items based on order
7. Manage package information (packed, unpacked)
8. Manage waste
9. Update source systems (GICA, GIMA) with daily sales and inventory data
Development Time Frame: 15 working man days (3 weeks)
Cumulative total: 12 weeks (3 months)
This estimate only reflects a delivery time line and not the actual effort