## LT
language translation |  | Sep 29 2018
Thursday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 24 | 3 | Designer | 1 | 72 | 9 | 9
Functional Specification | 16 | 2 | Web Developer | 1 | 260 | 32.5 | 32.5 | 65 | 65
Project Management | 52 | 6.5 | sr. developer | 1 | 260 | 32.5 | 32.5
Graphic Design | 40 | 5 | PM | 1 | 52 | 6.5 | 6.5
Working Prototype | 32 | 4 | BA | 1 | 40 | 5 | 5
Development |  |  | QA | 2 | 99 | 12.375 | 24.75 | 882
Administration |  |  | Total |  |  |  | 110.25
User management | 8 | 1
language configuration | 6 | 0.75 | Total Delivery days | 53.875
editor configuration | 8 | 1 | Total Man day Effort | 110.25 | 882 | 17640
chat plugin configuration | 8 | 1
Country setup | 6 | 0.75
payment gateway configuration | 0 | 0 |  |  | Monthly Active Users (MAU) | USD 0.001 per MAU
google ads configuration | 16 | 2 |  |  | Concurrent Users**
Other adv configurations (movie Ads) | 16 | 2 |  |  | Bandwidth | USD 0.9 / GB
SMS and email configuration | 8 | 1 |  |  | Storage | USD 2.5 per GB
Various reports (8 hrs per report) | 8 | 1 |  |  | Monthly Commitment | USD 49
General |  |  |  |  | Google Transcribing Services | ($0.006 USD / 15 seconds*)
Register App ( enter mobile no., receive confirmation code via SMS, select language and country) | 16 | 2 |  |  | Google Translation Services | ($20 per 1,000,000 characters*)
Permission to access GPS, contacts, microphone, push notifications etc | 6 | 0.75
Send invites via contacts | 8 | 1
contact status (existing users + users who downlaoded the app + currently online users) | 8 | 1
serve google ads | 16 | 2
serve movie ads | 16 | 2
add credit for watching movies | 12 | 1.5
Static pages (contact us etc) | 12 | 1.5
mesebo intialization and configuration | 12 | 1.5
google service initialization | 12 | 1.5
push to chat for audio translation (google cloud service) | 20 | 2.5
Save audio and convert to text, encrypt and save text (google cloud service) | 20 | 2.5
convert text to another language (google cloud service) | 20 | 2.5
save text and convert to audio (google cloud service) | 20 | 2.5
direct messaging using Mesebo | 24 | 3
direct audio chat using Mesebo | 24 | 3
Send attachments (audio, video, images) | 24 | 3
message delivery status | 16 | 2
Manage preferences | 12 | 1.5
Manage profile | 12 | 1.5
buy credits (payment processing) : 16 - 24 hrs per processor | 20 | 2.5
calculate audio chat time and charges (non translated) | 10 | 1.25
calculate text chat chatracter count and charges ( non translated) | 10 | 1.25
calculate audio chat time and charges (translated) | 10 | 1.25
calculate text chat chatracter count and charges (translated) | 10 | 1.25
Call log information | 10 | 1.25
System features
Authentication & authorization | 8 | 1
Auditing & logging | 16 | 2
Exception handling | 8 | 1
Manage files and directories | 24 | 3 | Only authentication
Testing & Deployment
Testing | 182 | 22.75
UAT | 16 | 0.5
Deployment | 8 | 1
Total Effort | 878 | 109.75
Assumptions
The application will be a responsive web application
SCORM +IMS LT1 + Open Source integrations not in scope
not in scope
not in scope
not in scope
not in scope