## AIRPORT WEBSITE
AIRPORT WEBSITE |  | 2019-05-27
Monday
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Developer | 1 | 17.75 | 17.75
System Study | 32 | 4 | PM | 1 | 0 | 0 | 4 | 17.75 | 4 | 17.75
Application Development and Testing |  |  | QA | 1 | 3.35 | 3.35
Creating Developemt Environment PHP - Drupal | 8 | 1 | SRS / System study | 1 | 4 | 4
Configure Theme | 30 | 3.75 | Total |  |  | 25.1
Configure Flight Search API | 32 | 4
Create Pages | 40 | 5 | Deliver Days | 21.1
Chat Bot | 32 | 4 | Total Effort | 25.1
Quality Assurance
QA & Bug Fixing | 26.8 | 3.35
PM | 0 | 0
Total Effort | 200.8 | 25.1
Assumption
All pages except Flight search are content management pages
Client need to purchase the Theme and Flight search API account