## Intelli Planner
| Intelli Planner |  | 2019-04-04
Thursday
| Module | Hours | Man Days |  | No of resources | Man Days | Adjusted Del Days | Total Effort
| Initiation |  |  | Designer | 1 | 10 | 10 | 10
1 | Business analysis | 96 | 12 | Developer | 2 | 113 | 56.5 | 113 | 0 | 122.025 | 113.5
2 | SRS | 40 | 5 | PM | 1 | 9.025 | 9.025 | 9.025
| UI/UX | 80 | 10 | BA | 1 | 17 | 17 | 17
3 | Project Management | 72.2 | 9.025 | QA | 1.5 | 40.6125 | 27.075 | 40.6125
| Design and Development |  |  |  | Sum |  |  | 189.6375
F &V Order Support
1 | Import files (order support, daily sales, promotions) | 16 | 2 | [8 empty] | Initiation | 39
2 | Normalize and fit data to target DB (Our Database) | 14 | 1.75 | Delivery Days | 93.575 | [6 empty] | F&V | 70
3 | Upload Quotation file | 4 | 0.5 | Total Effort | 189.6375 | [6 empty] | Bakery | 44
4 | Edit quotation file | 12 | 1.5 | [8 empty] | Butchery | 19
5 | Repeat step 2 (if necessary) | 8 | 1 | [8 empty] | qa & Bug Fixing | 45
6 | Generate summary information for Avg. sales, promotion Sales History etc for all items (Fruits and Vegetables only) sold in store | 16 | 2 | Task Breakdown | Days | [7 empty] | 217
7 | Generate summary information for a time series (hourly, daily, monthly, yearly, date ranges, time ranges etc) | 16 | 2 | Initiation | 36.025
8 | Create holiday calendar | 16 | 2 | F&V | 39.75
9 | Create promotions | 16 | 2 | Bakery | 30
10 | Check inventory in DC | 16 | 2 | Butchery | 20.5
11 | Block Suppliers when inventory is available is DC (Active / Blocked) | 16 | 2 | Common & System features | 23.25
12 | Place orders in DC | 16 | 2 | QA & Bug fixing | 40.6125
13 | View supplier Rates and Qty available when item not present in DC | 16 | 2 | Total Effort | 190.1375
14 | Recommend supplier based on past history (or some other criterion | 24 | 3
15 | Reports exportable to word, pdf or excell | 16 | 2
16 | Order creation API calls to GIMA, GICA | 32 | 4
17 | Responsive and bilingual Mobile tablet app | 16 | 2
18 | Manage local Item inventory (Price, qty, margin, promotion, sold, unsold, daily inventory requirements, throw aways etc) | 24 | 3
19 | Consolidate daily transactions and push to source (GICA , GIMA) | 24 | 3
Butchery Product Estimate
20 | File Imports from Carrefour (sales, mappings, promotions, Hourly sales) | 12 | 1.5
21 | Scrub, Normalize and fit data to target (Our database) | 12 | 1.5
22 | Define products (meat cuts, types-chicken, fish, lamb, cow; portion sizes) | 12 | 1.5
23 | Identify availability and daily requirements (estimates) | 12 | 1.5
24 | Generate summary information | 8 | 1
25 | Predictions based on past information (daily, promotions, holidays etc) | 12 | 1.5
26 | Identify cheapest meat cut for minced meat (to get optimum cost) | 12 | 1.5
27 | Manage waste | 12 | 1.5
28 | Push EOD data to GICA | 12 | 1.5
29 | Generate multi-format reports with multiple filters and orderings | 24 | 3
30 | API integration with source and target systems | 20 | 2.5
31 | Update source systems (GICA, GIMA) with daily sales and inventory data | 16 | 2
Bakery Product Estimate
32 | File Imports from Carrefour ( promotions, daily sales, hourly sales, recipe packing details, waste details) | 16 | 2
33 | Scrub, normalize and fit data to target | 16 | 2
34 | Generate Historical data (Time series) | 32 | 4
35 | Estimate daily requirements based on historical data | 24 | 3
36 | Create recipe with ingredient quantity | 32 | 4
37 | Baking batches | 16 | 2
38 | Generate raw material quantity of items based on order | 24 | 3
39 | Manage package information (packed, unpacked) | 24 | 3
40 | Manage waste | 24 | 3
41 | Update source systems (GICA, GIMA) with daily sales and inventory data | 32 | 4 | 9.5069
Admin Features
| Setup stores | 16 | 2
| Setup users and roles | 12 | 1.5 | [7 empty] | 0 | 0
| Setup departments | 12 | 1.5
| Manage storewise Promotion framework | 24 | 3
| Manage storewise Recipe framework | 24 | 3
| Store wise reporting framework | 24 | 3
Common Features
42 | Purge process to delete old promotions | 12 | 1.5
43 | Reports with dynamic filters | 12 | 1.5
44 | Top Selling and top wastage | 14 | 1.75
System Features
45 | Auditing and logging | 12 | 1.5
46 | Authentication & Authorization | 12 | 1.5
47 | Exception Handling | 12 | 1.5
48 | QA & Bug Fixing | 324.9 | 40.6125
| Total Effort | 1521.1 | 190.1375

## Sheet2
F&V ordering System
1. Import files (order support, daily sales, promotions)
2. Normalize and fit data to target DB (Our Database)
3. Upload Quotation file
4. Edit quotation file
5. Repeat step 2 (if necessary)
6. Generate summary information for Avg. sales, promotion Sales History etc for all items (Fruits and Vegetables only) sold in store
7. Generate summary information for a time series (hourly, daily, monthly, yearly, date ranges, time ranges etc)
8. Create holiday calendar
9. Create promotions
10. Check inventory in DC
11. Block Suppliers when inventory is available is DC
12. Place orders in DC
13. View supplier Rates and Qty available when item not present in DC
14. Recommend supplier based on past history (or some other criterion
15. Reports with multiple filters exportable to word, pdf or excell
16. Order creation API calls to GIMA, GICA
17. Responsive and bilingual Mobile tablet app
18. Manage local Item inventory (Price, qty, margin, promotion, sold, unsold, daily inventory requirements, throw aways etc)
19. Consolidate daily transactions and push to source (GICA , GIMA)
Development Time Frame: 30 working man days (one 1/2 month)
Butchery Product Estimate System
1. File Imports from Carrefour (sales, mappings, promotions, Hourly sales)
2. Scrub, Normalize and fit data to target (Our database)
2. Define products (meat cuts, types-chicken, fish, lamb, cow; portion sizes)
3. Identify availability and daily requirements (estimates)
4. Generate summary information
5. predictions based on past information (daily, promotions, holidays etc)
6. Identify cheapest meat cut for minced meat (to get optimum cost)
7. Manage waste
8. Push EOD data to GICA
9. Generate multi-format reports with multiple filters and orderings
10. API integration with source and target systems
11. Update source systems (GICA, GIMA) with daily sales and inventory data
Development Time Frame: 15 working man days
Cumulative Total : 9 weeks
Bakery Product Estimate System
1. File Imports from Carrefour ( promotions, daily sales, hourly sales, recipe packing details, waste details)
2. Scrub, normalize and fit data to target
3. Generate Historical data
4. Estimate daily requirements based on historical data
5. Create recipe with ingredient quantity
6. Generate raw material quantity of items based on order
7. Manage package information (packed, unpacked)
8. Manage waste
9. Update source systems (GICA, GIMA) with daily sales and inventory data
Development Time Frame: 15 working man days (3 weeks)
Cumulative total: 12 weeks (3 months)
This estimate only reflects a delivery time line and not the actual effort