## Sheet1
#	Activity	Hours	Days		Assumptions
	Project initiation				Special features not considered
	Business Analysis	40	5
	Documentation (Business requirements, Functional requirment specification, User guides)	40	5
	PM	40	5		Resource	#	Hours	Days
	Design (UI & UX prototypes with 3 design alternatives) : Responsive design	40	5		BA	1	40	5	5
	Development				PM	1	40	5	5
	Bilingual site	40	5		Documentation	1	40	5	5
	Integrations (Email, Payment G/W, Courier, Google Map)	40	5		Design	1	40	5	5	50	50
	Buyer		0		Jr Developer	1	200	25	25
	Login / Forgot password / Remember password	24	3		Sr Developer	1	200	25	25
	Registration, Email verification	6	0.75		QA	1.5	140	11.6666666666667	17.5
	Create update profile	12	1.5		sum		700	81.6666666666667	87.5
	Manage delivery address	8	1		Delivery Days	52.5
	Search Products, Sellers, Deals	12	1.5		Actual	87.5
	Advanced search	16	2
	view product details (description, Image, Video)	24	3		Note:
	Add items to cart (Manage Cart)	12	1.5		This estimate is meant for a responsive Web App
	Select Delivery options (Express or Normal)	6	0.75
	Payment options	6	0.75		For an equivalent PWA, consider approximately half times more effort
	Pfroduct ratings and comments	16	2		For a Hybrid App in Flutter. The effort will be approximately the same (80 additional days in effort. The work will happen parallel to the web app development)
	track order	6	0.75
	recent orders	6	0.75
	View notifications	6	0.75
	receive invoice	6	0.75
	Report abuse or complaint	6	0.75
	Receive push notifications	6	0.75
	Add items to watchlist	8	1
	Seller		0
	Registration with monthly or annual billing	16	2
	Login / Forgot password / Remember password	8	1
	Manage profile	24	3
	mark item unavailable	4	0.5
	view orders received	4	0.5
	view sales	6	0.75
	view buyer profile	6	0.75
	autoreject orders after 48 hours	6	0.75
	change order status	4	0.5
	view order status notificationbs	4	0.5
	Dasboards and reports	12	1.5
	Admin		0
	Advanced search	8	1
	view seller registration requests	8	1
	Approve / block seller	6	0.75
	block buyers	6	0.75
	update buyer info	6	0.75
	update product info	6	0.75
	QA	140	17.5
	Total	700	87.5