## Sheet1
# | Activity | Hours | Days | Assumptions
| Project initiation |  |  | Special features not considered
| Business Analysis | 40 | 5
| Documentation (Business requirements, Functional requirment specification, User guides) | 40 | 5
| PM | 40 | 5 | Resource | # | Hours | Days
| Design (UI & UX prototypes with 3 design alternatives) : Responsive design | 40 | 5 | BA | 1 | 40 | 5 | 5
| Development |  |  | PM | 1 | 40 | 5 | 5
| Bilingual site | 40 | 5 | Documentation | 1 | 40 | 5 | 5
| Integrations (Email, Payment G/W, Courier, Google Map) | 40 | 5 | Design | 1 | 40 | 5 | 5 | 50 | 50
| Buyer |  | 0 | Jr Developer | 1 | 200 | 25 | 25
| Login / Forgot password / Remember password | 24 | 3 | Sr Developer | 1 | 200 | 25 | 25
| Registration, Email verification | 6 | 0.75 | QA | 1.5 | 140 | 11.6667 | 17.5
| Create update profile | 12 | 1.5 | sum |  | 700 | 81.6667 | 87.5
| Manage delivery address | 8 | 1 | Delivery Days | 52.5
| Search Products, Sellers, Deals | 12 | 1.5 | Actual | 87.5
| Advanced search | 16 | 2
| view product details (description, Image, Video) | 24 | 3 | Note:
| Add items to cart (Manage Cart) | 12 | 1.5 | This estimate is meant for a responsive Web App
| Select Delivery options (Express or Normal) | 6 | 0.75
| Payment options | 6 | 0.75 | For an equivalent PWA, consider approximately half times more effort
| Pfroduct ratings and comments | 16 | 2 | For a Hybrid App in Flutter. The effort will be approximately the same (80 additional days in effort. The work will happen parallel to the web app development)
| track order | 6 | 0.75
| recent orders | 6 | 0.75
| View notifications | 6 | 0.75
| receive invoice | 6 | 0.75
| Report abuse or complaint | 6 | 0.75
| Receive push notifications | 6 | 0.75
| Add items to watchlist | 8 | 1
| Seller |  | 0
| Registration with monthly or annual billing | 16 | 2
| Login / Forgot password / Remember password | 8 | 1
| Manage profile | 24 | 3
| mark item unavailable | 4 | 0.5
| view orders received | 4 | 0.5
| view sales | 6 | 0.75
| view buyer profile | 6 | 0.75
| autoreject orders after 48 hours | 6 | 0.75
| change order status | 4 | 0.5
| view order status notificationbs | 4 | 0.5
| Dasboards and reports | 12 | 1.5
| Admin |  | 0
| Advanced search | 8 | 1
| view seller registration requests | 8 | 1
| Approve / block seller | 6 | 0.75
| block buyers | 6 | 0.75
| update buyer info | 6 | 0.75
| update product info | 6 | 0.75
| QA | 140 | 17.5
| Total | 700 | 87.5