## Web App
| Jumeirah - Approval Management System |  | 2019-08-02
Friday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 4.5 | 4.5
| Business analysis | 8 | 1 | Sr. Developer | 1 | 17.25 | 17.25 | 34.25 | 38.7025 | 34.25
| Project Management | 35.62 | 4.4525 | Jr. Developer | 1 | 17 | 17
| Design and Prototype | 36 | 4.5 | PM | 1 | 4.4525 | 4.4525
| Documentation(Project Plan, SRS, User Manual) | 64 | 8 | BA | 1 | 1 | 1
| Development |  |  | Tech writer | 1 | 8 | 8
1 | Application basic setup | 12 | 1.5 | QA | 2 | 5.1375 | 10.275
2 | Login/Logout (Active directory integration) | 8 | 1 | Total | 8 | 57.34 | 62.4775
Initiator(Outlet Manager/ Department head)
3 | Dashboard | 8 | 1 | Effort | 62.4775 | + 1 Day (Deployment)
4 | POS Update Request |  |  | Delivery Time | 40.34 | + 1 Day (Deployment)
5 | Raise requests | 10 | 1.25
6 | View Submitted requests | 6 | 0.75
7 | View Approved requests | 6 | 0.75
8 | View and Resubmit Rejected requests | 16 | 2
9 | Complementary Request
10 | Raise requests | 8 | 1
11 | View Submitted requests | 6 | 0.75
12 | View Approved requests | 6 | 0.75
13 | View and Resubmit Rejected requests | 14 | 1.75
14 | Reports (with search, sort & export to excel feature)
15 | POS Update Request | 8 | 1
16 | Complementary Request | 8 | 1
Approver
17 | Dashboard | 8 | 1
18 | POS Update Request
19 | View Submitted/Resubmitted requests (Approve or Reject request with reason) | 6 | 0.75
20 | View Approved requests | 4 | 0.5
21 | View Rejected requests | 4 | 0.5
22 | Complementary Request
23 | View Submitted/Resubmitted requests (Approve or Reject request with reason) | 6 | 0.75
24 | View Approved requests | 4 | 0.5
25 | View Rejected requests | 4 | 0.5
26 | Delegation of Authority (delegate and revoke the delegation) | 6 | 0.75
27 | Reports (with search, sort & export to excel feature)
28 | POS Update Request | 8 | 1
29 | Complementary Request | 8 | 1
DOA
30 | Dashboard | 8 | 1
31 | POS Update Request
32 | View Submitted/Resubmitted requests (Approve or Reject request with reason) | 6 | 0.75
33 | View Approved requests | 4 | 0.5
34 | View Rejected requests | 4 | 0.5
35 | Complementary Request
36 | View Submitted/Resubmitted requests (Approve or Reject request with reason) | 6 | 0.75
37 | View Approved requests | 4 | 0.5
38 | View Rejected requests | 4 | 0.5
Admin
39 | Dashboard | 8 | 1
40 | Brand Management (add/edit/delete) | 6 | 0.75
41 | Outlet Management (add/edit/delete) | 6 | 0.75
42 | User Management (add/edit/delete) | 6 | 0.75
43 | Master data management (add/edit/delete) [considering 3 master data] | 18 | 2.25
44 | Reports (with search, sort & export to excel feature)
45 | POS Update Request | 8 | 1
46 | Complementary Request | 8 | 1
47 | Email Integration | 4 | 0.5
Quality Assurance
49 | QA & Bug Fixing | 82.2 | 10.275
50 | UAT | 16 | 2
51 | Deployment per instance | 8 | 1
| Total Effort | 523.82 | 65.4775
Assumptions
Only English language is considered
The effort may vary based on the actual functionalities.

## Mobile App
Jumeirah Restaurant Group
| Module | Hours | Man Days | Hours | Man Days |  | No | Hours | Man Days
|  | iOS | iOS | Android | Android | Android developer | 1 | 180 | 22.5
| Initiation |  |  |  |  | iOS developer | 1 | 180 | 22.5
| Design and Prototype | 40 | 5 | 0 |  | Designing | 1 | 40 | 5
[6 empty] | QA | 1 | 108 | 13.5
| Development, Design and API |  |  |  |  | Total |  |  | 63.5
| Application basic setup | 8 | 1 | 8 | 1
| Splash screen | 8 | 1 | 8 | 1
| Common |  |  |  |  | Total Effort | 63.5 | days
1 | Login | 8 | 1 | 8 | 1
2 | LogOut | 4 | 0.5 | 4 | 0.5
3 | Settings | 12 | 1.5 | 12 | 1.5
Dashboard - Initiator
4 | POS Update Request
| Food | 6 | 0.75 | 6 | 0.75
| Beverage | 6 | 0.75 | 6 | 0.75
| Tobacco | 6 | 0.75 | 6 | 0.75
| Discounts | 6 | 0.75 | 6 | 0.75
| Package | 8 | 1 | 8 | 1
| Complimentary Request | 5 | 0.625 | 5 | 0.625
5 | Initiate a request - Attach files | 24 | 3 | 24 | 3
6 | Review status of requests | 12 | 1.5 | 12 | 1.5
7 | Resubmit the request | 5 | 0.625 | 5 | 0.625
Dashboard - Approver
8 | List of raised requests | 10 | 1.25 | 10 | 1.25
9 | Approve/Reject request with reason | 10 | 1.25 | 10 | 1.25
10 | Delegate someone to review the request | 12 | 1.5 | 12 | 1.5
11 | Revoke/update the delegation | 10 | 1.25 | 10 | 1.25
Dashboard - DOA
12 | List of raised requests | 10 | 1.25 | 10 | 1.25
13 | Approve/Reject request with reason | 10 | 1.25 | 10 | 1.25
| Total Effort | 180 | 22.5 | 180 | 22.5
Note:1.This estimation is purely based on assumptions, since mobile app screens are not provided. The effort may vary based on the actual functionalities. 2.The estimation is done for iOS and Android Portrait mode. 3. Mobile App testing can be done only with the available devices mentioned in the technical proposal

## Web & Api
| Jumeirah Restaurant Group |  | 2019-08-02
Friday
| Module | Hours | Man Days
Initiation
Development, Design and API
| Application basic setup | 8 | 1
Common
1 | Login | 4 | 0.5
2 | LogOut | 2 | 0.25
Dashboard - Initiator
3 | POS Update Request | 8 | 1
4 | Complimentary Request | 8 | 1
5 | Review status of requests | 4 | 0.5
5 | Dashboard - Approver
5.1 | List of raised requests | 3 | 0.375
5.2 | Approve/Reject request with reason | 6 | 0.75
5.3 | Delegate someone to review the request | 6 | 0.75
5.4 | Revoke/update the delegation | 4 | 0.5
6 | Dashboard - DOA
6.1 | List of raised requests | 3 | 0.375
6.2 | Approve/Reject request with reason | 6 | 0.75
| Total Effort | 62 | 7.75
Note: Effort may vary based on the actual functionalities