## Car Service- mobile
| Car Service Application |  |  |  | 24/09/2019
Tuesday
[9 empty] | Native |  |  | Hybrid
| Module | Full Project |  |  |  |  | No | Man Days | Total Effort
| Initiation | Hours | Days |  |  | Designer | 1 | 6.25 | 6.25 |  |  | 4.6875
| Business analysis | 8 | 1 |  |  | Hybrid App Design | 1 | 0 | 0 | 25.125 | 77.025 | 20
| Project Management | 40.2 | 5.025 |  |  | IOS Developer | 1 | 25.125 | 25.125 |  |  | 25.125
| Design | 50 | 6.25 |  |  | Android Developer | 1 | 25.125 | 25.125
| Documentation(FS, SRS, User manual) | 32 | 4 |  |  | Web Developer | 1 | 21.75 | 21.75 |  |  | 21.75
[6 empty] | PM | 1 | 5.025 | 5.025 |  |  | 2.5125
| Module | Android |  | iOS |  | BA | 1 | 1 | 1 |  |  | 1
| Initiation | Hours | Days | Hours | Days | Tech writer | 1 | 4 | 4 |  |  | 2
| Development and Api |  |  |  |  | QA | 1 | 17.5875 | 17.5875 |  |  | 13.1906
| Application basic setup | 8 | 1 | 8 | 1 | Total |  | 105.8625 | 105.8625 |  |  | 90.2656
| Splash Screen | 8 | 1 | 8 | 1
| Home Screen |  |  |  |  | Native Mobile App
1 | Login/Logout | 6 | 0.75 | 6 | 0.75 | Total Effort | 105.8625
2 | Fast Login | 5 | 0.625 | 5 | 0.625 | Delivery Days | 52.9625
3 | Create account | 8 | 1 | 8 | 1
4 | Service List |  |  |  |  | Hybrid Mobile App (Flutter)
5 | Service options | 6 | 0.75 | 6 | 0.75 | Total Effort | 90.2656
6 | Click desired service-Add car details | 5 | 0.625 | 5 | 0.625 | Delivery Days | 63.0031
7 | Select existing car | 5 | 0.625 | 5 | 0.625
8 | Add new car- add car details(manufacturer,VIN,model,year,mileage) | 5 | 0.625 | 5 | 0.625
9 | Describe issue in text box | 4 | 0.5 | 4 | 0.5
10 | Add photos | 6 | 0.75 | 6 | 0.75
11 | Pin location using map | 2 | 0.25 | 2 | 0.25 |  |  | 201
12 | Select pick up time | 5 | 0.625 | 5 | 0.625 |  |  | 201
13 | Option to select "delivery on completion" (Yes/No) | 4 | 0.5 | 4 | 0.5
14 | Payment (debit/credit card) | 5 | 0.625 | 5 | 0.625
15 | Emergency List
16 | Pin location using map | 5 | 0.625 | 5 | 0.625
17 | Option to select "delivery on completion" (Yes/No) | 4 | 0.5 | 4 | 0.5
18 | Payment (debit/credit card) | 4 | 0.5 | 4 | 0.5
19 | Tabs/Pages available to customer
20 | Home page | 8 | 1 | 8 | 1
21 | Manage vehicles | 8 | 1 | 8 | 1
22 | My service requests | 6 | 0.75 | 6 | 0.75
23 | View status (New/assigned to driver/picked up/delivered to workshop/assessment done & waiting for customer payment/fixed/closed) | 6 | 0.75 | 6 | 0.75
24 | My Account | 6 | 0.75 | 6 | 0.75
25 | Receive push notifications on status change | 14 | 1.75 | 14 | 1.75
26 | Edit/update details | 8 | 1 | 8 | 1
28 | Integration
29 | Payment Integration gateway | 22 | 2.75 | 22 | 2.75
30 | Maps Integration | 16 | 2 | 16 | 2
32 | VIN -api integration to fetch car details | 12 | 1.5 | 12 | 1.5
34 | Quality Assurance
35 | QA & Bug Fixing | 70.35 | 8.7937 | 70.35 | 8.7937
36 | UAT |  | 0 |  | 0
37 | Deployment per instance |  | 0 |  | 0
| Total Effort | 271.35 | 33.9188 | 271.35 | 33.9188
| Total Effort Mobile | 542.7 | 67.8375
| Mobile Dev + Initiation | 672.9 | 84.1125
| Total Effort Web | 174 | 21.75
| Net Effort | 846.9 | 105.8625
Assumptions
This estimation consider only Mobile phones in portratit mode
Consider only online mode
This estimation may vary based on additional functionalities and is currently based on description from Mail.
In android it will work with Lollipop and above and iOS 9.0+.
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118

## Admin
Car Service Application
| Module | Hours | Days
Initiation
Development and Api
Application basic setup
Home Screen
1 | Login/Logout | 4 | 0.5
2 | Service management |  | 0
| Define service name & price | 8 | 1
3 | Manage Vehicles | 8 | 1
4 | View request received | 4 | 0.5
5 | Change status (New/assigned to driver(define time)/picked up/At the workshop/assessment done/fixed(pickup, delivery)) | 6 | 0.75
6 | Mobile API Integration | 80 | 10
7 | SMS API | 8 | 1
| Payment Gateway API | 24 | 3
Quality Assurance
| QA & Bug Fixing | 32 | 4
UAT
Deployment per instance
| Total Effort | 174 | 21.75
Assumptions