## MOE
| MOE-Smart Innovation System |  | 16/10/2019
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 8 | 8
1 | Business analysis | 80 | 10 | Sr Developer | 2 | 50.55 | 101.1 | 63.1 | 115.254 | 101.1
2 | Project Management | 113.232 | 14.154 | PM | 1 | 14.154 | 14.154
3 | SRS,FS,User Manual,Weekly Reports | 80 | 10 | BA | 1 | 10 | 10
4 | Design and Prototype | 64 | 8 | Tech writer | 1 | 10 | 10
| Development |  |  | QA | 1.5 | 26.96 | 40.44
5 | Application basic setup | 8 | 1 | Total | 7.5 | 119.664 | 183.694
| Arabic Support | 130.8 | 16.35
Admin
| Extract reports in excel/PDF format | 16 | 2
| Create challenges | 12 | 1.5
| Backend management | 24 | 3
| User roles management | 12 | 1.5
| FAQ(edit/delete) | 10 | 1.25
| Upload previous manual employee suggestion | 12 | 1.5 |  | Days
| Upload documents | 8 | 1 | Effort | 183.694 | + 1 Day (Deployment)
| Convert ideas to project | 24 | 3 | Delivery Time | 95.51 | + 1 Day (Deployment)
| Login/Logout | 4 | 0.5
IT Admin
| Create dynamic dashboards & reports | 32 | 4
| Create dynamic entry forms | 20 | 2.5
| Add attachments | 8 | 1
| Create/Modify workflows | 12 | 1.5
| Login/Logout | 8 | 1
Public Users & MOE Employees
| Dashboard | 12 | 1.5
| Leader board(display top 10 ideas,users, etc.) | 8 | 1
| Manage account(reset password, 2-factor authentication, set security questions) | 20 | 2.5
| Submit Ideas | 8 | 1
| Upload files/pictures | 8 | 1
| Fill forms | 24 | 3
| Receive alerts(Mail/SMS) on new challenges | 12 | 1.5
| Registration for Public Users(Unlimited registration) | 16 | 2
| Active directory login | 8 | 1
| Login/Logout | 4 | 0.5
Judges
| Register | 12 | 1.5
| Login/Logout | 4 | 0.5
| List,View,Search and Evaluate submitted ideas | 20 | 2.5
| Send selected & best ideas to Admin | 8 | 1
| Dashboard | 16 | 2
| Receive alerts(Mail/SMS) on new ideas | 4 | 0.5
General Features
| Implementing performance & speed tracking tools | 32 | 4
| Advanced search | 24 | 3
| Contact us (contact form) | 4 | 0.5
| Integration with current workflow engine implemented by Ministry Of Economy team | 40 | 5
| AI features to identify user issues | 48 | 6
| dynamic forms | 48 | 6
| dynamic workflows | 56 | 7
| Chat [Conversation] | 32 | 4
Quality Assurance
| QA & Bug Fixing | 307.52 | 38.44
| UAT | 16 | 2
| Deployment per instance | 8 | 1
| Total Effort |  | 184.694
Assumptions
Effort may change after a detailed system study
All the third party components, services that would be identified after a detailed system study would be procured by the client
A relative accurate Effort and timeline for Integration with MOE systems can estimated after recieveing the details of MOE systems