## PABS Service
PABS Service |  | 2019-06-14
Friday
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Tech Writer | 1 | 4 | 4
System Study | 8 | 1 | UI/UX | 1 | 3 | 3 | 64.375 | 64.375
SRS, FRS, Project Plan, Weekly Status | 32 | 4 | Developer | 1 | 25.75 | 25.75
Design Custom | 0 | 0 | Jn.Developer | 1 | 38.625 | 38.625
Prototype - Diffent Layout | 24 | 3 | PM | 1 | 7.4375 | 7.4375
Application Development and Testing |  |  | QA | 1 | 16.0938 | 16.0938
Creating Developemt Environment PHP |  | 0 | Total |  |  | 94.9062
Admin
Manage Users (Service Advisor, T echnician, Spare Manager, Account ant) | 8 | 1
Manage Car Models (upload) | 8 | 1
Manage Categores | 4 | 0.5 |  | Days | Months
Manage Customers | 8 | 1 | Deliver Days | 57.7188 | 2.8859
Reports (@6 hrs / reports) 6 reports | 36 | 4.5 | Total Effort | 94.9062
Service Advisor |  |  | 30% Buffer | 123.3781
Work Management | 20 | 2.5
T ool management | 22 | 2.75
Equipment Management | 22 | 2.75 | Development Time ~ | 3 months
Oil Management | 22 | 2.75 | Blended rate | $12/hr
Manage Reports | 15 | 1.875
T echnician
Equipment Management | 25 | 3.125
Oil Management | 8 | 1
Manage Reports | 15 | 1.875
Spare Manager
Spares Management | 23 | 2.875
Service Management | 23 | 2.875
Equipment Management | 16 | 2
Oil Management | 16 | 2
T ools Management | 16 | 2
Manage Reports | 15 | 1.875
Account ant
Account s | 42 | 5.25
Equipment Management | 18 | 2.25
Oil Management | 15 | 1.875
T ools Management | 12 | 1.5
Manage Reports | 15 | 1.875
System Features |  | 0
Routing of workflows based on user actions | 35 | 4.375
Customizable email messages | 24 | 3
Detailed audit log / history | 32 | 4
Quality Assurance
QA & Bug Fixing | 128.75 | 16.0938
PM | 51.5 | 6.4375
Total Effort | 719.25 | 94.9062
Assumption
Customization of templates are not considered