## ADSC
| ADSC |  | 23/05/2018
Wednesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 5 | 5
| Business analysis | 32 | 4 | Sr Developer | 1 | 50 | 50 | 8.5 | 125 | 33 | 100
| Project Management | 26.4 | 3.3 | Jr Developer | 1 | 50 | 50
| Design and Prototype | 40 | 5 | IOS | 1 | 25 | 25
| Development |  |  | PM | 1 | 3.3 | 3.3
| Application Basic Setup | 8 | 1 | BA | 1 | 4 | 4
1 | Tutor |  |  | Tech writer | 1 | 3 | 3
2 |  |  |  | QA | 2 | 8.425 | 16.85
3 |  |  |  | Total |  |  | 157.15
4
5
6 |  |  |  | Total Delivery days | 63.425
7 |  |  |  | Total Effort | 157.15 | (+1 Day deployment)
8
9 |  |  |  | Assumption
10 |  |  |  | Simple Workflows | 5 Man Days
11 |  |  |  | Moderate Workflow | 10 Man Days
12 |  |  |  | Complex Workflow | 15 Man Days
13
14
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56 |  |  |  |  | Onsite inspection (mobile App)
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
79
80
81
82
83
84
85
System features
108 | Authentication & authorization | 8 | 1
109 | Auditing & logging | 8 | 1
110 | Exception handling | 8 | 1
111 | Manage files and folders | 12 | 1.5
112 | LDAP Integration | 12 | 1.5
113 | SMS & Email | 12 | 1.5
114 | ERP integration for PRO requests | 40 | 5
115 | Scheduling | 12 | 1.5
116 | Payment Gateway Integration |  | 0
117 | Invoice Generation | 16 | 2
| English and Arabic | 40 | 5
| Office 365 integration for email communication | 24 | 3
| Application hosting model as cloud or on-premise | 24 | 3
| Reports | 40 | 5
Quality Assurance
| QA & Bug Fixing | 118.8 | 14.85
| UAT | 16 | 2
| Deployment per instance | 8 | 1
| Total Effort | 505.2 | 63.15
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118