## ADSC
| ADSC |  | 20/06/2018
Wednesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 20 | 20
| Business analysis | 80 | 10 | Sr Developer | 1 | 221 | 221 | 437.25 | 442 | 442.25 | 442
| Project Management | 353 | 44.125 | Jr Developer | 1 | 221 | 221
| Design and Prototype | 160 | 20 | IOS | 0 | 0 | 0
| Development |  |  | PM | 1 | 44.125 | 44.125
| Application Basic Setup | 8 | 1 | BA | 1 | 10 | 10
| ADSC Workflows |  |  | Tech writer | 0 | 0 | 0
| Booking Conference Room Application |  |  | QA | 2 | 78.2188 | 156.4375
1 | Users |  |  | Total |  |  | 672.5625
2 | Coordinator of applicant division | 4 | 0.5
3 | Director of applicant division | 4 | 0.5
4 | Communication Section Coordinator | 4 | 0.5 | Total Delivery days | 319.2188
5 | Communication Section Head | 0 | 0 | Total Effort | 672.5625 | (+1 Day deployment)
6 | Process |  | 0
7 | Booking form application | 16 | 2 | Assumption
8 | Applicatin form Approval | 6 | 0.75 | Simple Workflows | 5 Man Days
9 | Submission of Approved Form | 6 | 0.75 | Moderate Workflow | 10 Man Days
10 | Application Processing | 4 | 0.5 | Complex Workflow | 15 Man Days
11 | Application form Approval by Commjunication Head | 6 | 0.75
12 | Booking of Conference Room | 12 | 1.5
13 | Media Coverage Application |  | 0
14 | Users |  | 0
15 | Coordinator of applicant division | 4 | 0.5
16 | Director of applicant division | 4 | 0.5
17 | Communication Section Head | 0 | 0
18 | Process |  | 0
19 | Media Coverage Application form | 16 | 2
20 | Receiving application form | 16 | 2
21 | Check,Review and Approval of Application form | 6 | 0.75
22 | Reply to Applicant Division | 4 | 0.5
23 | Video Production |  | 0
24 | Users |  | 0
25 | Communication Section | 4 | 0.5
26 | Head of Communication Section | 4 | 0.5
27 | Process |  | 0
28 | Receiving application form from divisions | 16 | 2
29 | Forwarding application to person in charge | 8 | 1
30 | Processing Applications | 8 | 1
31 | Receiving applications and Video show for final approval | 12 | 1.5
32 | Appearences of General Secretary on Media |  | 0
33 | Users |  | 0
34 | GS office | 4 | 0.5
35 | The General Secretary | 4 | 0.5
36 | Communication Section | 0 | 0
37 | communication Section Head | 0 | 0
38 | Process |  | 0
39 | Receiving applications | 16 | 2
40 | Fixing Appoinment dates | 12 | 1.5
41 | Informing Communication Section Head | 6 | 0.75
42 | Informing Communication Section Head and Instructing about Media appearences | 12 | 1.5
43 | Final Approval | 4 | 0.5
44 | Application To Organize/ Host Sporting championship |  | 0
45 | Users |  | 0
46 | The Club | 4 | 0.5
47 | The GS Office | 4 | 0.5
48 | Events Coordinator | 4 | 0.5
49 | Marketing and Communication Director | 0 | 0
50 | Technical Affairs Director | 0 | 0
51 | Supportive Service Director | 0 | 0
52 | Process |  | 0
53 | Application Form | 16 | 2
54 | Receiving Club application form | 16 | 2
55 | Preparation of memo for necessary actions | 12 | 1.5
| Memo submitted for approval | 8 | 1
56 | Application's memo reviewed/remarks and comments added | 8 | 1
57 | Memo checked /reviewed,comments and remarks added | 6 | 0.75
58 | Rejection reasons mentioned in writing/kept | 6 | 0.75
59 | Memo after approvals of directors of the 3 respective divisions | 8 | 1
60 | Memo received and rejection reasons mentioned in writing | 8 | 1
61 | Final Approval by the H.E the GS | 4 | 0.5
62 | Sport Activity Approval License |  | 0
63 | Users |  | 0
64 | The System | 4 | 0.5
65 | Customers | 4 | 0.5
66 | Licensing Section Employee | 0 | 0
67 | Licensing section Head | 0 | 0
68 | Inspection Section | 0 | 0
69 | Process |  | 0
70 | Properties database 1.Issurance 2.Renewal 3.Amendment 4.Cancellation | 16 | 2
71 | Enter the application on the system | 16 | 2
72 | Receive the application,Check the data and documents as per the procedures | 8 | 1
73 | Transaction approved and forwarded for field action | 6 | 0.75
74 | Field action procedures taken to finalize the licensing | 6 | 0.75
75 | Approval issued | 6 | 0.75
76 | Reasons of rejection received | 6 | 0.75
77 | The two transactions to be done simultaneously | 8 | 1
78 | Application received | 8 | 1
79 | New /Regular inspection visit |  | 0
80 | Users |  | 0
81 | Inspector | 4 | 0.5
82 | Customer care Section Head | 4 | 0.5
83 | Process |  | 0
84 | Application opened as per reference number | 12 | 1.5
85 | Application received | 12 | 1.5
86 | Reasons of rejection | 6 | 0.75
87 | The two transactions to be done simultaneously | 12 | 1.5
88 | Site /Filed visit inspection ,report submitted including supporting pictures,photos and data | 12 | 1.5
89 | Report received, recommendations made by person in charge | 12 | 1.5
90 | New Sport Project plan- Appoint a Consultant Phase |  | 0
91 | Users |  | 0
92 | Relevant Bodies | 4 | 0.5
93 | Properties Section Employees | 4 | 0.5
94 | Supportive Services | 4 | 0.5
95 | Consultant/Contractor | 0 | 0
96 | Properties Section Head | 0 | 0
97 | Properties and Licensing Director | 0 | 0
98 | The Gs | 0 | 0
99 | Process |  | 0
100 | New Project Application | 16 | 2
101 | Application of a new project received | 12 | 1.5
102 | Project studied/Report submitted | 8 | 1
103 | Report received | 6 | 0.75
104 | Consultant appointing bid submitted | 12 | 1.5
105 | Quotation received | 6 | 0.75
106 | Recommendations reported | 6 | 0.75
107 | Appointing a consultant report received | 8 | 1
108 | Set the technical plams and cost of the project | 8 | 1
109 | Receive the technical plams and cost of the project to study them over | 8 | 1
110 | Approved | 6 | 0.75
111 | Plans amended | 8 | 1
112 | Report about appointing a connsultant | 8 | 1
113 | Appointing a consultant report received | 6 | 0.75
114 | Appointing a contractor appointing bid published | 6 | 0.75
115 | Quotations received | 8 | 1
116 | Recommendations submitted | 8 | 1
117 | Appointing a contractor report received | 8 | 1
118 | Set the technical plans and cost of the project | 24 | 3
119 | Execution /Implementation plan received including timetable and necessary documents | 12 | 1.5
120 | Received by contractor,work starts | 6 | 0.75
121 | Follow up with the contractor as per the tmetable | 12 | 1.5
122 | Work progress and follow up report by the contractor | 16 | 2
123 | Report by the end of a certain time period | 8 | 1
124 | New /Regular Inspection Visit |  | 0
125 | Users |  | 0
126 | Inspector | 4 | 0.5
127 | Properties Section Head | 4 | 0.5
128 | Process |  | 0
129 | Openan inspection request as per | 12 | 1.5
130 | Submit a report about the case with the same reference number | 12 | 1.5
131 | Submit a report including all needed details,recommendations and remarks | 12 | 1.5
132 | Report received,Recommendations checked by the person in charge | 8 | 1
133 | Maintanence Request |  | 0
134 | Users |  | 0
135 | The Club | 4 | 0.5
136 | Properties Section Head | 4 | 0.5
137 | Properties Section Employees | 0 | 0
138 | The inspector | 0 | 0
139 | Process |  | 0
140 | Clubs sends online maintanence request form including all needed documents | 16 | 2
141 | Report received,property information collected,needed maintanence works detailed | 16 | 2
142 | Maintanence Request studied | 8 | 1
143 | Approved | 8 | 1
144 | Fiels /site visit as per the case | 12 | 1.5
145 | Clun informed and notified | 12 | 1.5
146 | Rejected | 8 | 1
147 | the two transactions to be done simultaneously | 12 | 1.5
148 | Prepare a report about the requested maintenance work | 12 | 1.5
149 | Report received and archieved | 8 | 1
150 | Training Allowance Procedure Plan |  | 0
151 | Users |  | 0
152 | Notify the employee of a training allowance | 4 | 0.5
153 | Direct Line Manager | 4 | 0.5
154 | Employee of the training and development section | 0 | 0
155 | Accounts Section Head | 0 | 0
156 | Process |  | 0
157 | Application submitted | 16 | 2
158 | Application approved | 6 | 0.75
159 | Approved and attach a document | 8 | 1
160 | Application processed | 6 | 0.75
161 | Receive the result | 8 | 1
162 | Sport Club Service Procedures Plan |  | 0
163 | Users |  | 0
164 | Applicant Club | 4 | 0.5
165 | HR Employee | 4 | 0.5
166 | HR Section Head | 4 | 0.5
167 | HR Director | 0 | 0
168 | Technical Affairs Director | 0 | 0
169 | GS | 0 | 0
170 | Process |  | 0
171 | Application sumitted | 16 | 2
172 | Application received and checked | 8 | 1
173 | Application checked and approved | 6 | 0.75
174 | Administrative opinion | 12 | 1.5
175 | Technical Opinion | 12 | 1.5
176 | Operations taken asper the said case | 12 | 1.5
177 | Action taken | 8 | 1
178 | For approval/rejection | 8 | 1
179 | Action taken | 8 | 1
180 | Acceptance/Rejection | 8 | 1
181 | Delegation and Job Rotation Procedure Plan |  | 0
182 | Users |  | 0
183 | HR Planning Section | 4 | 0.5
184 | Division director | 4 | 0.5
185 | Relevant Employees | 4 | 0.5
186 | Development and Training section | 0 | 0
187 | HR Director | 0 | 0
188 | GS | 0 | 0
189 | Process |  | 0
190 | Job Rotatin form submitted | 16 | 2
191 | Form received ,approved and completed | 8 | 1
192 | Approved | 4 | 0.5
193 | Approved completed form submitted | 8 | 1
194 | Approved | 4 | 0.5
195 | Approved/Rejected | 4 | 0.5
196 | For information and archiving | 8 | 1
197 | Select and implement target training courses | 12 | 1.5
198 | For Information | 6 | 0.75
199 | Result/Decision:Acceptance/Rejection | 8 | 1
200 | Shadow Employee Guidance Form Plan |  | 0
201 | Users |  | 0
202 | HR Planning Section | 4 | 0.5
203 | Training and Development Section | 4 | 0.5
204 | Direct Line Manager | 4 | 0.5
205 | Relevant Employees | 0 | 0
206 | HR Director | 0 | 0
207 | GS | 0 | 0
208 | Process |  | 0
209 | Employee evaluation form submitted | 16 | 2
210 | Shadow | 12 | 1.5
211 | Procedures taken | 8 | 1
212 | Application form received and approved | 12 | 1.5
213 | Shadow Employee Guid's evaluation form submitted | 16 | 2
214 | Approved form | 8 | 1
215 | For Approval | 8 | 1
216 | Approved | 8 | 1
217 | For information | 8 | 1
218 | For information and archiving | 8 | 1
219 | Jon Rotation Form Plan |  | 0
220 | Users |  | 0
221 | HR Planning and Development section | 4 | 0.5
222 | Division Director | 4 | 0.5
223 | Development and training section | 0 | 0
224 | HR Director | 0 | 0
225 | Process |  | 0
226 | Job rotation form | 16 | 2
227 | Completed form received | 12 | 1.5
228 | Completed form received | 0 | 0
229 | Training courses attended by relevant person | 16 | 2
230 | Continue filling the form | 8 | 1
231 | Implementation | 8 | 1
232 | Foe information and archiving | 4 | 0.5
233 | Shadow Employment Plan |  | 0
234 | Users |  | 0
235 | HR Planning Section | 4 | 0.5
236 | Division director | 4 | 0.5
237 | Relevant Employees | 4 | 0.5
238 | Development and Training section | 0 | 0
239 | Training and Development staff member in charge | 0 | 0
240 | Direct Line Manager | 0 | 0
241 | Process |  | 0
242 | Shadow employment form submitted | 16 | 2
243 | For approval | 12 | 1.5
244 | Action taken | 12 | 1.5
245 | Form received ,approved | 8 | 1
246 | Form submitted to approve the nominees | 12 | 1.5
247 | Application form received and processed | 8 | 1
248 | Form filling in and completed by relevant shadow employee | 12 | 1.5
249 | For approval | 6 | 0.75
250 | Result | 8 | 1
251 | Jonb analyses Survey plan |  | 0
252 | Users |  | 0
253 | HR Development Section | 4 | 0.5
254 | Division director | 4 | 0.5
255 | Relevant Section Head | 0 | 0
256 | Relevant Employees | 0 | 0
257 | Process |  | 0
258 | Job analysis survey form/Application submitted | 16 | 2
259 | Application form received and transferred | 12 | 1.5
260 | Fill the form and approval | 12 | 1.5
261 | Necessary actions taken | 12 | 1.5
262 | Employees Transactions Finalizing Procedures Plan |  | 0
263 | Users |  | 0
264 | Applicant Club | 4 | 0.5
265 | Employee | 4 | 0.5
266 | Head | 0 | 0
267 | Process |  | 0
268 | Application submitted | 16 | 2
269 | Application received and checked | 8 | 1
270 | Application approved | 8 | 1
271 | Application processed | 8 | 1
272 | Result | 8 | 1
273 | Official Mission Procedures Plan |  | 0
274 | Users |  | 0
275 | Applicant | 4 | 0.5
276 | Respective Director | 4 | 0.5
277 | Director | 4 | 0.5
278 | HR Section | 0 | 0
279 | Applicant Direct Line Manager | 0 | 0
280 | Accounts Section Head | 0 | 0
281 | Process |  | 0
282 | Application submitted | 16 | 2
283 | Application approved (step3) | 12 | 1.5
284 | Application processes,Letter prepared | 12 | 1.5
285 | Complete the form | 12 | 1.5
286 | Application(step 7) | 12 | 1.5
287 | Application received and checked | 16 | 2
288 | Application processed | 8 | 1
289 | Result | 8 | 1
290 | Study leave Procedure Plan |  | 0
291 | Users |  | 0
292 | Training section employee | 4 | 0.5
293 | ADSc employee | 4 | 0.5
294 | Direct Line manager of applicant | 4 | 0.5
295 | Application receiver | 0 | 0
296 | GS | 0 | 0
297 | Training and Development Section | 0 | 0
298 | Process |  | 0
299 | Study leave notice sent | 16 | 2
300 | Form filled with all needed documents attached | 12 | 1.5
301 | Application approved(step3) | 8 | 1
302 | Received and checked | 12 | 1.5
303 | Application approved(step5) | 8 | 1
304 | Application approved(step6) | 8 | 1
305 | List by nominees submitted | 8 | 1
306 | Application processed | 8 | 1
307 | Result | 8 | 1
308 | Official Mission Procedures Plan |  | 0
309 | Users |  | 0
310 | Applicant | 4 | 0.5
311 | Relevant Director | 4 | 0.5
312 | GS | 4 | 0.5
313 | HR Section | 0 | 0
314 | Direct Line Manager | 0 | 0
315 | Account Section Head | 0 | 0
316 | Process |  | 0
317 | Application | 16 | 2
318 | Approved(Step2) | 12 | 1.5
319 | Approved(Step3) | 8 | 1
320 | Decision made | 8 | 1
321 | Fill the form | 16 | 2
322 | Approved | 8 | 1
323 | Approved and checked | 6 | 0.75
324 | Application processed | 8 | 1
325 | Result | 8 | 1
326 | Internal Memo Plan |  | 0
327 | Users |  | 0
328 | Employee in charge | 4 | 0.5
329 | Direct line Manager | 4 | 0.5
330 | HR Director | 0 | 0
331 | Decision Taker | 0 | 0
332 | Process |  | 0
333 | Application form submitted | 16 | 2
334 | Form received and checked | 16 | 2
335 | Application reviewed and approved | 12 | 1.5
336 | Application approved | 8 | 1
337 | Application processed | 8 | 1
338 | Application approval/Rejection | 6 | 0.75
339 | Training at Colleges and University Procedurtes Plan |  | 0
340 | Users |  | 0
341 | Training section employee | 4 | 0.5
342 | Division director | 4 | 0.5
343 | Application received by employee trainee and development section | 4 | 0.5
344 | Direct Line Manager | 0 | 0
345 | Guide employee | 0 | 0
346 | Application received by HR section | 0 | 0
347 | IT section | 0 | 0
348 | Process |  | 0
349 | Sent a notification to fill in the form | 16 | 2
350 | Form filled by relevant divisions | 16 | 2
351 | Application received and checked | 12 | 1.5
352 | Application approved(step4) | 8 | 1
353 | Application approved(step6) | 8 | 1
354 | Application approved(step7) | 8 | 1
355 | Logistics support provided | 16 | 2
356 | Application processed | 8 | 1
357 | Application accepted/rejected | 8 | 1
358 | Sport Event Licensing |  | 0
359 | Users |  | 0
360 | Applicant | 4 | 0.5
361 | Marketing Section Head | 4 | 0.5
362 | Marketing Coordinator | 4 | 0.5
363 | Tourism and culture department coordinator | 0 | 0
364 | Marketing and Communication Director | 0 | 0
365 | Process |  | 0
366 | Filling in the license form | 16 | 2
367 | Application form processed and checked | 16 | 2
368 | All needed documents and details enclosed | 8 | 1
369 | Intial approval | 8 | 1
370 | Application rejected for non-compliance with licensing requirements | 12 | 1.5
371 | File kept | 8 | 1
372 | Final approval | 8 | 1
373 | Provide all needed documents | 8 | 1
374 | Inform the applicant about the approval | 8 | 1
375 | Training courses Logistics support procedure Plan |  | 0
376 | Users |  | 0
377 | Division | 4 | 0.5
378 | Person in charge | 4 | 0.5
379 | Section Head | 4 | 0.5
380 | Receives the application at the media section | 0 | 0
381 | Process |  | 0
382 | Training rroom booking process | 16 | 2
383 | Training room booking completed+Request for media coverage | 16 | 2
384 | Application checked and approved | 12 | 1.5
385 | Application received | 8 | 1
386 | Application Confirmed | 8 | 1
387 | Response and reply to the applicant | 8 | 1
388 | Application processed and implemented | 8 | 1
389 | Training courses Logistics support procedure Plan |  | 0
390 | Users |  | 0
391 | AFF.Division | 4 | 0.5
392 | Letters prepared by | 4 | 0.5
393 | Section Head | 4 | 0.5
394 | Division director | 0 | 0
395 | GS | 0 | 0
396 | Application of club received by | 0 | 0
397 | Process |  | 0
398 | Invitations and form sent out | 16 | 2
399 | Nomination letters and invitations sent | 16 | 2
400 | Draft letters checked | 12 | 1.5
401 | Final drafts checked | 8 | 1
402 | Invitations approved and ratified | 6 | 0.75
403 | Invitation forward for action | 12 | 1.5
404 | Nomination letters and forms sent | 12 | 1.5
405 | Nomination form completed by nominee | 16 | 2
406 | Completed form sent to person in charge | 12 | 1.5
407 | Forms sorted out and names of nominees listed to check who is attending | 8 | 1
408 | Training courses Logistics support procedure Plan |  | 0
409 | Users |  | 0
410 | AFF.Division | 4 | 0.5
411 | Applicant | 4 | 0.5
412 | Section Head | 4 | 0.5
413 | Receivec by statistics section | 0 | 0
414 | Process |  | 0
415 | Analysis survey application+ survey analysis | 16 | 2
416 | Survey analysis application submitted +all needed documents | 8 | 1
417 | Application checked and approved | 8 | 1
418 | Application received | 8 | 1
419 | Application confirmed | 6 | 0.75
420 | Response sent to applicant | 8 | 1
421 | Survey analyzed+ Final statistical report prepared | 12 | 1.5
422 | Final statistical report sent to relevant employee | 8 | 1
423 | Training Budget Procedure Plan |  | 0
424 | Users |  | 0
425 | T.AFF Division | 4 | 0.5
426 | Applicant | 4 | 0.5
427 | Section Head | 4 | 0.5
428 | Division Director | 0 | 0
429 | HE the GS | 0 | 0
430 | Process |  | 0
431 | The process to allocate and approve the traiming budget | 20 | 2.5
432 | Prepare the training plan as per the allocated budget | 32 | 4
433 | Plan submitted | 8 | 1
434 | First check of the plan | 8 | 1
435 | Final check and approval | 8 | 1
436 | Final approval | 6 | 0.75
437 | Submit the plan to the director of the division for acceptance /rejection | 6 | 0.75
438 | Submit the paln to the setion head for action | 6 | 0.75
439 | Send the plan to the employee head in charge | 6 | 0.75
440 | Technical opinion to hire and appoint athletes with the SCP procedure plan
441 | Users
442 | T.AFF Division | 4 | 0.5
443 | Applicant club | 4 | 0.5
444 | Employee in Charge | 4 | 0.5
445 | Chief Coordinator | 0 | 0
446 | Section Head | 0 | 0
447 | Director of technical affairs | 0 | 0
448 | HR Division | 0 | 0
449 | Process
450 | Application submitted with all needed with all needed documents | 4 | 0.5
451 | Application forwarded | 12 | 1.5
452 | What to be taken and done | 16 | 2
453 | For action | 12 | 1.5
454 | Form to be evaluated | 8 | 1
455 | Form to be completed by the coach | 16 | 2
456 | Form submitted for evaluation | 8 | 1
457 | Evaluatuion checked and final result announced | 12 | 1.5
458 | Technical opinion form completed | 16 | 2
459 | Final checkup | 8 | 1
460 | Final checkup and approval | 6 | 0.75
461 | Form to be completed for technical opinion | 12 | 1.5
462 | Final acceptance /rejection | 8 | 1
463 | Application received and result shown | 8 | 1
464 | Job Support Regulations update Procedure plan |  | 0
465 | Users |  | 0
466 | T.AFF Division | 4 | 0.5
467 | Person in charge | 4 | 0.5
468 | HR Division | 4 | 0.5
469 | Section Head | 0 | 0
470 | Division Director | 0 | 0
471 | Planning office | 0 | 0
472 | The GS | 0 | 0
473 | Process |  | 0
474 | Support regulation process | 12 | 1.5
475 | Update database of SCP Affliates | 16 | 2
476 | Database submitted | 12 | 1.5
477 | Analyzed,status quo report prepared | 12 | 1.5
478 | First draft prepared | 16 | 2
479 | Draft reviewed,Checked and technical suggestions and recommendations made | 16 | 2
480 | Final technical checkup | 12 | 1.5
481 | Draft checked and recommendations made | 16 | 2
482 | Final checkup | 16 | 2
483 | Final checkup | 0 | 0
484 | For action and to keep the file | 8 | 1
485 | File to be kept | 8 | 1
486 | File kept | 8 | 1
487 | General Regulations Update Procedure Plan |  | 0
488 | Users |  | 0
489 | T.AFF.Division | 4 | 0.5
490 | Charge | 4 | 0.5
491 | Head | 4 | 0.5
492 | Director | 0 | 0
493 | Strategic Planning ofiice | 0 | 0
494 | The GS | 0 | 0
495 | Process |  | 0
496 | Regulations and evidence update | 16 | 2
497 | First draft prepared | 12 | 1.5
498 | First draft checked | 8 | 1
499 | Final checkup | 6 | 0.75
500 | Final approval | 6 | 0.75
501 | For action and file keeping | 16 | 2
502 | File to be kept | 12 | 1.5
503 | File kept | 6 | 0.75
504 | Host Sport Event Procedure Plans |  | 0
505 | Users |  | 0
506 | T.AFF.Division | 4 | 0.5
507 | Personal Charge | 4 | 0.5
508 | Section Head | 4 | 0.5
509 | HR Division | 0 | 0
510 | Process |  | 0
511 | Application to host sport event | 16 | 2
512 | Application form sent to host for completion | 12 | 1.5
513 | Application confirmed and approved | 12 | 1.5
514 | Coordinate with applicant | 12 | 1.5
515 | Sent SMS to relevant persons+including details | 12 | 1.5
516 | Sent the list of participants to check who has not attended | 16 | 2
517 | Take necessary actions as per rules and regulations | 12 | 1.5
518 | Clubs Financial Support Procedures Plan |  | 0
519 | Users |  | 0
520 | T.AFF.Division | 4 | 0.5
521 | Applicant Club | 4 | 0.5
522 | Employee In Charge | 4 | 0.5
523 | Section Head | 0 | 0
524 | Director | 0 | 0
525 | Process |  | 0
526 | Support prtocess procedures | 16 | 2
527 | Application submitted with all needed documents | 16 | 2
528 | Application received | 8 | 1
529 | Application forwarded | 6 | 0.75
530 | For action | 6 | 0.75
531 | Coordinate with applicant club | 16 | 2
532 | Support form completed | 16 | 2
533 | Approved application submitted | 8 | 1
534 | Application first check | 6 | 0.75
535 | Final check of the application | 12 | 1.5
536 | Final check and approval | 8 | 1
537 | Application accepted/rejected | 6 | 0.75
538 | Application forwarded for action | 6 | 0.75
539 | File kept | 6 | 0.75
540 | File kept and club notified of acceptance/rejection | 6 | 0.75
541 | For knowledge | 6 | 0.75
542 | Club's Financial Support/Award Procedure Plan |  | 0
543 | Users |  | 0
544 | Technical Affairs Division | 4 | 0.5
545 | Applicant | 4 | 0.5
546 | Employee In Charge | 4 | 0.5
547 | Section Head | 0 | 0
548 | Technical Affarirs Director | 0 | 0
549 | Supportive Services division | 0 | 0
550 | Process |  | 0
551 | Financial award process | 20 | 2.5
552 | Application submitted with all needed documents included | 8 | 1
553 | Application received | 6 | 0.75
554 | Application processed and forwarded | 8 | 1
555 | Action | 6 | 0.75
556 | For action as per the regulations of winning international accoades | 20 | 2.5
557 | Coordinate with the club | 16 | 2
558 | Application completed and processed | 12 | 1.5
559 | Approved application submitted | 12 | 1.5
560 | First checkup | 12 | 1.5
561 | First checkup | 0 | 0
562 | Checkup and approval | 8 | 1
563 | Final acceptance /rejection decision | 12 | 1.5
564 | Application forwarded for action | 8 | 1
565 | File kept | 6 | 0.75
566 | Club informed and notified aboutacceptance/rejection of their application and file kept | 12 | 1.5
567 | FI and knowledge | 8 | 1
568 | System features |  | 0
569 | Authentication & authorization | 8 | 1
570 | Auditing & logging | 8 | 1
571 | Exception handling | 8 | 1
572 | Manage files and folders | 12 | 1.5
573 | SMS & Email | 12 | 1.5
574 | Reports | 40 | 5
575 | Quality Assurance
576 | QA & Bug Fixing | 1235.5 | 154.4375
577 | UAT | 16 | 2
578 | Deployment per instance | 8 | 1
579 | Total Effort | 5390.5 | 673.8125