## Web
Agriculture & Food Safety Authority 03 July 2020
Module | Hours | Man Days | Resources | # | Days | Total
Project Initiation |  |  | UI / UX | 1 | 10 | 10
Business analysis | 80 | 10 | BA | 1 | 10 | 10
Project Management | 73.8 | 9.225 | Tech Writer | 1 | 5 | 5
SRS,FS,User Manual | 40 | 5 | PM | 1 | 9.225 | 9.225
Design and Prototype (mobile & Web) | 80 | 10 | Jr Developer | 2 | 36 | 72 | 142 | 142.25
Development |  |  | Sr Developer | 2 | 35 | 70
Application Basic setup | 8 | 1 | Mobile API | 1 | 32.2875 | 32.2875
Part A - Technical Data & Information |  |  | QA | 2 | 27.9075 | 55.815
Admin (Web Application) |  |  | Total |  |  | 264.3275
Create Components | 12 | 1.5
Create Sub Components or critical areas | 12 | 1.5 |  | Days | Months
Create activities and tasks for each critical areas | 12 | 1.5 | Total Effort | 264.3275 | 13.2164
Attach reference documents | 12 | 1.5 | Delivery Timeline | 83.9075 | 4.1954
Create control points for activities so that they can be evaluted | 12 | 1.5 | Expected Delivery time | 70 | 3.5
Extension Officer Activities (Mobile & Web Application)
Create notes against control points | 8 | 1 | Mobile Development / Track | 75.5221 | 3.7761
Review the report before final submit | 8 | 1
Assess farm based on control points | 8 | 1
Send report to extension center manager for approval | 8 | 1
Extension manager approves and sends to farm owner | 8 | 1
Send documents to farmer to mitigate GAPS found | 8 | 1
Retrieve advice from database | 8 | 1
Provide advice based on GAPS found | 8 | 1
Part B - Farm Information & Agriculture Sustainability Index
Admin (Web Application)
Create quantitave data Indicators | 12 | 1.5
Create Qualitative data indicators | 12 | 1.5
Create schedules for quantitative and qualitate data assessment | 12 | 1.5
Extension Officer Activities (Mobile Application)
Capture quantitative data | 12 | 1.5
Capture qualitative dats | 12 | 1.5
Update ADAFSA database | 12 | 1.5
Provide advice based on GAPS | 12 | 1.5
SES Utilization
Transfer responsibility of farm from one extension officer to another | 16 | 2
Send transfer request to area manager | 16 | 2
Area manager approval | 16 | 2
Data Capture Business Practice (Mobile App)
Extension engineer login via AD | 4 | 4
Capture Geo Cordinates and verify farm location | 4 | 4
Display Farm characteristics using data from ADAFSA | 8 | 8
Open SES solution check list | 8 | 8
Conduct farm assessment | 8 | 8
Consiult reference documents | 8 | 8
Append messages to farm owner for issues found | 8 | 8
Add evidence (Photos, videos) | 8 | 8
Stakeholders Access & Reporting Hierarchy (Mobile & Web)
Field Level - AEE
AEE should have access to reports created (month by month & Accumulative reports) | 8 | 1
Access to outstanding issues per farm (read only) | 8 | 1
Repport should include components, sub components & control points | 8 | 1
Farm Owners |  | 0
Farm Visit notifications | 8 | 1
AEE reports | 8 | 1
Suggested actions to improve farming practices & increase crop production | 8 | 1
Access to brief reports on farm | 8 | 1
Access to detailed report | 8 | 1
Local Farm Unit (Farm Relations Manager) |  | 0
Edit field report by extension center manager | 8 | 1
send report to farmer | 8 | 1
Farm relations manager has view only access to all reports submitted by AEE. | 8 | 1
Includes real time view of reports when AEE is visiting farm | 8 | 1
Multi monthly reports prepared by AEE / farm | 8 | 1
reports of all AEE working under him | 8 | 1
AEE has readonly access to reports submitted by them | 8 | 1
Regional Level |  | 0
Area & section managers |  | 0
Reports on specific agricultural practices | 8 | 1
Performance of AEE in a given center | 8 | 1
Change in statistical data for various farming systems | 8 | 1
Assigning regional subject matter specialist on critical issues | 8 | 1
Monitoring and evaluation of regional programs and technical staff; | 8 | 1
Mobilizing regional human and material resources to enhance field actrivities | 8 | 1
Activities and/or programs. |  | 0
Access to AEE reports | 8 | 1
Identify training needs of AEE | 8 | 1
Identify and provide reccomenfdations on specific issues in particulkar centers | 8 | 1
TSD Central Level |  | 0
Make realistic management decisions related to field program development as well as reinforcement of human and financial resources; | 8 | 1
Provide ADAFSA Executive Management & Decision Makers with sound suggestions of relevance to policies and strategies for sustainable agricultural and rural development. | 8 | 1
Training |  | 0
End user training | 8 | 1
Train the trainer | 8 | 1
Administrator training | 8 | 1
Integrations |  | 0
Siebel | 12 | 1.5
SMS gateway | 12 | 1.5
Active directory | 8 | 1
online - offline capability | 8 | 1
Bi lingual application | 40 | 5
Security
Protection against injection attacks (SQL, CRLF) | 6 | 0.75
URL encoding, Input validation | 6 | 0.75
Cookie Encryption, Cookie replay attacks | 6 | 0.75
Session hijacking prevention | 6 | 0.75
Cross site scripting and session management | 6 | 0.75
System Features |  |  | Note: 6 hrs / KPI
Authentication, Authorization, Roles | 12 | 1.5
Exception Handling and Error logging | 12 | 1.5
Auditing & Logging | 12 | 1.5
Search Engine | 12 | 1.5
Notification management | 12 | 1.5
Reporting Engine | 12 | 1.5
Workflow management | 12 | 1.5
Mobile API
Mobile API | 258.3 | 32.2875
SQA |  |  |  | data encryption
QA & Bug fixing | 398.52 | 49.815
UAT | 40 | 5 | 40
Deployment | 8 | 1 | 32
Total | 1724.62 | 264.5775
215.5775

## Mobile
Agriculture & Food Safety Authority 03 July 2020
| Hrs | Days | Hrs | Days
| Android |  | IOS
Customer Mobile App
Agriculture Directory Services
eServices &
Control Management Systems
Assumption 1.The estimation is for portrait mode. 2.The estimation may vary with the difference in functionality and the design. 3.The estimation is done for native android and iOS app.