## mobile
Restaurant Management Application |  |  |  | 2020-04-13
Monday
Module | Android |  | iOS |  |  | No | Man Days | Total Effort
| Hours | Man Days | Hours | Man Days | Designer | 1 | 0
Development |  |  |  |  | Android Developer | 1 | 0 |  | 15 | 0 | 0
[5 empty] | iOS Developer | 1 | 0
Trader registration |  |  |  |  | QA | 1 | 0
Splash Screen | 6 | 0.75 | 6 | 0.75 | Total | 4 | 0
Register new user | 8 | 1 | 8 | 1
Login Page | 6 | 0.75 | 6 | 0.75
Dashboard
View Menu | 0 | 0 | 0 | 0
Add dish to cart | 0 | 0 | 0 | 0
Payment gateway | 24 | 3 | 24 | 3
View order history | 6 | 0.75 | 6 | 0.75
View discounts | 8 | 1 | 8 | 1
Table reservation | 14 | 1.75 | 14 | 1.75
Integration with Torqus POS using APIs only | 24 | 3 | 24 | 3
Checkout process | 10 | 1.25 | 10 | 1.25
Price in UAE and Thailand currency (depending where the restaurant is) | 6 | 0.75 | 6 | 0.75
View outlets in different countries or cities with multi currency | 8 | 1 | 8 | 1
Quality Assurance
QA & Bug Fixing | 48 | 6 | 48 | 6
Total Effort | 168 | 21 | 168 | 21
Assumptions 1.The estimation may be vary with variation in new features or design. 2.The estimation is done only for protrait mode.