## Total
Web Development
Resource | No | Man Days | Total Effort
Designer | 1 | 12 | 12
Sr Developer | 1 | 30 | 30
Jr Developer | 1 | 30 | 30
PM | 1 | 5.825 | 5.825
BA | 1 | 2 | 2
Tech writer | 1 | 2 | 2
QA | 2 | 11.6312 | 23.2625
Total |  | 93.4562 | 105.0875
0 | 0 | 0 | 0
Effort | 105.0875 | + 1 Day (Deployment)
Delivery Time | 55.6313 | + 1 Day (Deployment)
Mobile Development
Resource | No | Man Days | Total Effort
Designer | 1 | 3 | 3
Android Developer | 1 | 21 | 21
iOS Developer | 1 | 21 | 21
QA | 2 | 6 | 12
API Development | 1 | 6.4 | 6.4
Total |  | 57.4 | 63.4
Effort Estimate | 63.4
Delivery Time | 36.4
Total Effort | 168.4875

## Web
| Amritsr |  | 13/4/2020
Monday
| Module | Hours | Man Days | Resource | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 12 | 12
1 | Business analysis | 16 | 2 | Sr Developer | 1 | 30 | 30 | 60.75 | 65.825 | 60.75 | 60
2 | Project Management | 46.6 | 5.825 | Jr Developer | 1 | 30 | 30
3 | SRS,FS,User Manual | 16 | 2 | PM | 1 | 5.825 | 5.825
4 | Design and Prototype | 120 | 12 | BA | 1 | 2 | 2
| Development |  |  | Tech writer | 1 | 2 | 2
5 | Application basic setup | 8 | 1 | QA | 2 | 11.6312 | 23.2625
| Database design | 12 | 1.5 | Total | 8 | 93.4562 | 105.0875
Back End
| Dashboard |  |  | Effort | 105.0875 | + 1 Day (Deployment)
| Dashboard summary | 6 | 0.75 | Delivery Time | 55.6313 | + 1 Day (Deployment)
| Recent Orders : Accept, Reject, Dispatched , Delivered , Cancelled, Order Details (read only) | 6 | 0.75
| Recent reservations: Cancelled, Confirmed | 6 | 0.75
| Reports Charts | 6 | 0.75
Restaurant
| Location List: Select and delete, paging | 12 | 1.5
| New Locations |  | 0
| Location | 6 | 0.75
| Settings | 6 | 0.75
| Apply for UTC | 6 | 0.75
| Opening Hours | 6 | 0.75
| cash on delivery | 6 | 0.75 | Effort estimate received from Sharath for UI/UX
| Delivery : Add new area | 6 | 0.75
| Edit map area | 6 | 0.75
| List tables: select & delete with paging | 6 | 0.75
| New table | 6 | 0.75
| Kitchen |  | 0
| List Menu: Select and delete, paging | 7 | 0.875
| New Menu tabs: menu, specials | 6 | 0.75
| list Menu categories :select and delete, paging | 4 | 0.5
| New menu category | 6 | 0.75
| List meal times: select & delete, paging | 4 | 0.5
| Edit meal time | 4 | 0.5
| New meal time | 4 | 0.5
| Sales |  | 0
| Order list: Select and delete with paging | 4 | 0.5
| Edit Order : Change status, Assign Order, View Invoice, Tabs: Order, menu Items, Status History (read only), save order | 12 | 1.5
| New Order | 12 | 1.5
| Reservation list: Select and delete with paging | 4 | 0.5
| Edit reseravtion: Change status and assignee, Tabs: reservation, status history | 4 | 0.5
| New reservation | 6 | 0.75
| Review list : Select & delete with paging | 4 | 0.5
| New Review | 6 | 0.75
| Edit review | 4 | 0.5
| Status list: delete, page | 4 | 0.5
| Edit Status | 4 | 0.5
| New status | 3 | 0.375
| List Payments | 4 | 0.5
| New payment (with payment integration ) / gateway | 16 | 2
| Marketing |  | 0
| list Coupons : select & delete, paging |  | 0
| New Coupons with history tab | 8 | 1
| Edit Coupon | 4 | 0.5
| List Reservation discount: select & delete, paging | 4 | 0.5
| New reservation discount | 6 | 0.75
| Edit reservation | 4 | 0.5
| Users |  | 0
| List Users: Select & delete, paging | 4 | 0.5
| Edit users | 4 | 0.5
| New Users with tabs: Customer, address ( add new address- new address added as a sub tab), Orders Reservations | 18 | 2.25
| Staff List: select delete, page | 4 | 0.5
| Edit staff | 6 | 0.75
| New Staff | 6 | 0.75
Front END
| Web site (Covered by UI/UX design) |  | 0
| Home page |  | 0
| About Us |  | 0
| menu |  | 0
| Book a table |  | 0
| login |  | 0
| register |  | 0
| Careers |  | 0
| Quality policy |  | 0
| privacy policy |  | 0
| Terms and conditions |  | 0
| Locate Us |  | 0
| Social media |  | 0
| Online Ordering |  | 0
| left menu Selection | 16 | 2 |  | 15
| Build item display based on menu selection | 12 | 1.5
| menu Selection frame | 12 | 1.5
| Order details page (image, description, price etc) | 12 | 1.5
| Checkout frame | 12 | 1.5
| Calculate order total | 12 | 1.5
| Apply coupons | 12 | 1.5
| Login | 12 | 1.5
| Registration | 12 | 1.5
| About Us | 4 | 0.5
| Change locations | 4 | 0.5
| Payment | 8 | 1
| Seed Data |  | 0
| Customer Group, coupon Validity, Coupon Type | 6 | 0.75
| Order Restriction, Authors | 6 | 0.75
| Locations | 6 | 0.75
| Sales status, Order Status | 4 | 0.5
| Notify customer option | 4 | 0.5
| Kitchen staff | 4 | 0.5
| Parent menu categories | 4 | 0.5
| Country | 4 | 0.5
| Days of week | 4 | 0.5
| Delivery hours, pick up hours | 4 | 0.5
| Department | 4 | 0.5
| Language | 4 | 0.5
| Tax rates (type, inclusion criteria, rate) | 4 | 0.5
Quality Assurance
| QA & Bug Fixing | 170.1 | 21.2625
| UAT | 16 | 2
| Deployment per instance | 8 | 1
| Total Effort |  | 106.8375
Assumptions
The effort may change after a detailed system study

## Mobile
Restaurant Management Application |  |  |  | 2020-04-13
Monday
Module | Android |  | iOS |  | Resource | No | Man Days | Total Effort
| Hours | Man Days | Hours | Man Days | Designer | 1 | 3 | 3
Development |  |  |  |  | Android Developer | 1 | 21 | 21
[5 empty] | iOS Developer | 1 | 21 | 21
Trader registration |  |  |  |  | QA | 2 | 6 | 12
Splash Screen | 6 | 0.75 | 6 | 0.75 | API Development | 1 | 6.4 | 6.4
Register new user | 8 | 1 | 8 | 1 | Total | 6 | 57.4 | 63.4
Login Page | 6 | 0.75 | 6 | 0.75
Dashboard |  |  |  |  | Effort Estimate | 63.4
View Menu | 0 | 0 | 0 | 0 | Delivery Time | 36.4
Add dish to cart | 0 | 0 | 0 | 0
Payment gateway | 24 | 3 | 24 | 3
View order history | 6 | 0.75 | 6 | 0.75
View discounts | 8 | 1 | 8 | 1
Table reservation | 14 | 1.75 | 14 | 1.75
Integration with Torqus POS using APIs only | 24 | 3 | 24 | 3
Checkout process | 10 | 1.25 | 10 | 1.25
Price in UAE and Thailand currency (depending where the restaurant is) | 6 | 0.75 | 6 | 0.75
View outlets in different countries or cities with multi currency | 8 | 1 | 8 | 1
Quality Assurance
QA & Bug Fixing | 48 | 6 | 48 | 6
Total Effort | 168 | 21 | 168 | 21
API Development | 51.2 | 6.4
Assumptions 1.The estimation may be vary with variation in new features or design. 2.The estimation is done only for protrait mode.

## UIUX
Task | Days
Front End Website Design | 5
Mobile App Design | 3
Front End Website Prototype | 5
Backend Website Prototype (template) | 5
Total | 15 | 120