## Web
CSI Hub 21 September2020
Module | Hours | Man Days | Resources | # | Days | Total
Project Initiation |  |  | UI / UX | 1 | 8 | 8
Business analysis | 40 | 5 | BA | 1 | 5 | 5
Project Management | 64 | 8 | Tech Writer | 1 | 5 | 5
SRS,FS,User Manual | 40 | 5 | PM | 1 | 8 | 8
Design and Prototype (mobile & Web) | 64 | 8 | Jr Developer | 1 | 40 | 40 | 80 | 80
Development |  |  | Sr Developer | 1 | 40 | 40
Application Basic setup | 8 | 1 | Mobile API | 1 | 0 | 0
Information & Resources |  |  | QA | 2 | 16.825 | 33.65
Home page | 24 | 3 | Total |  |  | 139.65
SignUp/SignIn/Register | 12 | 1.5
CSI, Ma'an corporation Information | 6 | 0.75 |  | Days | Months
Date & Dashboard best practices in CSR, top performing companies& global insights | 24 | 3 | Total Effort | 139.65 | 6.9825
Links for donation & other Ma'an platforms | 16 | 2 | Delivery Timeline | 69.825 | 3.4912
Stakeholder login/registered user login | 12 | 1.5
Dashboard(Current status,areas of strengths weakness | 20 | 2.5
Recommendation & insights of user performance | 12 | 1.5
Tools, toolkits and guidelines to elevate CSR work | 12 | 1.5
Meetups,training Scheduling | 12 | 1.5
Live calls |  | 0 | <- Depends on features
Assessment & Label
Signup | 8 | 1
Enter the details of company | 8 | 1
Upload documents | 8 | 1
Validation(private/registered) | 12 | 1.5
SignIn |  | 0
Sign in using credentials | 6 | 0.75
track application status | 6 | 0.75
Self Assessment |  | 0
Answer questions(multiple choice,yes/No, Open text) | 24 | 3
Automated results from Backend | 8 | 1
hover some of the platform’s information and resources | 12 | 1.5
option to move to administered assessment /application process | 12 | 1.5
Administered Assessment |  | 0
Answer questions(multiple choice,yes/No, Open text) | 24 | 3
Upload documents | 6 | 0.75
Payment for application | 12 | 1.5
View status of application and time for assessment results | 8 | 1
Apply for label based on administered results | 12 | 1.5
Assess information and resources based on administered results | 12 | 1.5
Payment for Label | 6 | 0.75
Meetups,training & Live calls | 24 | 3
Donate fund | 6 | 0.75
Receive notification when the labels expires | 8 | 1
Reapply for label | 6 | 0.75
Awards,Incentives & Recognition
Highlights of awarded companies | 6 | 0.75
Contributions of awarded companies | 6 | 0.75
Awards | 6 | 0.75
Incentives | 6 | 0.75
Recognition | 6 | 0.75
Admin
Review,Validate & assess answers of administered Assessment | 16 | 2
Review documents | 16 | 2
Approve/reject new User registration | 8 | 1
Dashboard | 24 | 3
Master data management | 24 | 3
User Role management | 16 | 2
Add/modify/delete training schedule | 12 | 1.5
Login/Logout | 6 | 0.75
System Features
Authentication, Authorization | 16 | 2
Exception Handling and Error logging | 6 | 0.75
Automated self assessment validation | 12 | 1.5
Payment Integration | 12 | 1.5
Notification Management | 12 | 1.5
Data Integration with govt/private database | 12 | 1.5
Integration with database of the chamber of commerce for validation | 16 | 2
Integration with Ma'an websites | 16 | 2
SQA
QA & Bug fixing | 221.2 | 27.65
UAT | 40 | 5
Deployment | 8 | 1
Total | 1117.2 | 139.65