## Web
CSI Hub 21 September2020
Module | Hours | Man Days | Resources | # | Days | Total
Project Initiation |  |  | UI / UX | 1 | 8 | 8
Business analysis | 40 | 5 | BA | 1 | 5 | 5
Project Management |  | 0 | Tech Writer | 1 | 3 | 3
SRS,FS,User Manual | 24 | 3 | PM | 1 | 0 | 0
Design and Prototype | 64 | 8 | Jr Developer | 2 |  |  | 0 | 40
Development |  |  | Sr Developer | 2
Application Basic setup | 8 | 1 | Mobile API | 1 | 0 | 0
Information & Resources |  |  | QA | 2 | 6.825 | 13.65
Home page | 16 | 2 | Total |  |  | 29.65
SignUp/SignIn/Register | 8 | 1
CSI, Ma'an corporation Information | 6 | 0.75 |  | Days | Months
Date & Dashboard best practices in CSR, top performing companies & global insights | 24 | 3 | Total Effort | 29.65 | 1.4825
Links for donation & other Ma'an platforms | 16 | 2 | Delivery Timeline | 19.825 | 0.99125
Stakeholder login/registered user login | 8 | 1
Dashboard(Current status,areas of strengths weakness | 24 | 3
Recommendation & insights of user performance | 24 | 3
Tools, toolkits and guidelines to elevate CSR work | 24 | 3
Meetups,training | 24 | 3
Live calls | 40 | 5 | Using Twilio platform or zoom
Assessment & Label
Signup |  | 0
Enter the details of company | 12 | 1.5
Upload documents | 12 | 1.5
Validation(private/registered) | 12 | 1.5
SignIn |  | 0
Sign in using credentials | 6 | 0.75
track application status | 8 | 1
Self Assessment |  | 0
Answer questions(multiple choice,yes/No, Open text) | 24 | 3
Automated results from Backend | 24 | 3
hover some of the platform’s information and resources |  | 0
option to move to administered assessment /application process |  | 0
Administered Assessment |  | 0
Answer questions(multiple choice,yes/No, Open text) |  | 0
Upload documents |  | 0
Payment for application |  | 0
View status of application and time for assessment results |  | 0
Apply for label based on administered results |  | 0
Assess information and resources based on administered results |  | 0
Payment for Label |  | 0
Meetups,training & Live calls
Donate fund
Receive notification when the labels expires
Reapply for label
Awards,Incentives & Recognition
Highlights of awarded companies |  | 0
Contributions of awarded companies |  | 0
Awards |  | 0
Incentives |  | 0
Recognition |  | 0
Admin
Review,Validate & assess answers of administered Assessment
Review documents |  | 0
Approve/reject new User registration |  | 0
Dashboard |  | 0
Master data management |  | 0
User Role management |  | 0
Add/modify/delete training schedule
Login/Logout
System Features
Authentication, Authorization |  | 0
Exception Handling and Error logging |  | 0
Automated self assessment validation |  | 0
Payment Integration
Notification Management
Data Integration with govt/private database
Integration with database of the chamber of commerce for validation
Integration with Ma'an websites
SQA
QA & Bug fixing | 109.2 | 13.65
UAT |  | 0
Deployment |  | 0
Total | 557.2 | 69.65