## Web
CSI Hub 21 September2020
Module | Hours | Man Days | Resources | # | Days | Total
Project Initiation |  |  | UI / UX | 1 | 5 | 5
Business analysis | 32 | 4 | BA | 1 | 4 | 4
Project Management | 87.22 | 10.9025 | Tech Writer | 1 | 4 | 4
SRS,User Manual,weekly report | 32 | 4 | PM | 1 | 10.9025 | 10.9025
Design and Prototype (mobile & Web) | 40 | 5 | Sr Developer | 1 | 40 | 40 | 80 | 79.75
Development |  |  | Jr Developer | 1 | 40 | 40
Application Basic setup | 8 | 1 | QA | 2 | 11.8875 | 23.775
Information & Resources |  |  | Total |  |  | 127.6775
Home page | 16 | 2
Publicly available Information and Resources |  | 0 |  | Days | Months
General information on HIB, CSI & Ma’an | 6 | 0.75 | Total Effort | 127.6775 | 6.3839
Eligibility & Incentives | 8 | 1 | Delivery Timeline | 60.8875 | 3.0444
Dashboard | 12 | 1.5
Links to other Ma’an platforms | 4 | 0.5
Stakeholder specific information & Resources |  | 0
Current status of assessed companies (Strength & weakness) drill down report | 8 | 1
Reccomendation and Insight on users performance | 6 | 0.75
Tools, toolkits & guidelines | 8 | 1
Meetups and training schedules | 8 | 1
Assessment & Label
Signup / Registration |  | 0
Eligibility Questionairre & Eligibility guidelines | 16 | 2
Registration details (Name, domicile, registration # etc) | 12 | 1.5
Upload documents to verify legal status and other requirments | 4 | 0.5
Validation process(private/registered) | 8 | 1
Third party integrations for verifications | 6 | 0.75
Assign credentials & email upon successful verification | 4 | 0.5
SignIn (using assigned credentials) |  | 0
Sign in using credentials | 4 | 0.5
track application status | 6 | 0.75
Self Assessment |  | 0
Answer predefined questions (multiple choice,yes/No, Open text) | 16 | 2
Compute results based on responses | 8 | 1
View preliminary assessment results (Results may include reccomendadtions & guides) | 6 | 0.75
Information and resources eligible for companies completing self assessment | 4
Option to move to administered assessment /application process | 6 | 0.75
Administered Assessment |  | 0
Answer questions(multiple choice,yes/No, Open text) | 20 | 2.5
Upload documents | 4 | 0.5
Payment for application | 6 | 0.75
View status of application and time for assessment results | 4 | 0.5
Apply for label based on administered results | 8 | 1
Assess information and resources based on administered results | 8 | 1
Payment for Label | 6 | 0.75
Schedule Meetups & training | 12 | 1.5
Donate fund | 6 | 0.75
Receive notification when the labels expires | 6 | 0.75
Reapply for label | 8 | 1
Awards,Incentives & Recognition (Passes Administered assessment & applied for labels)
Highlights of awarded companies | 6 | 0.75
Contributions of awarded companies | 6 | 0.75
Awards | 6 | 0.75
Incentives | 6 | 0.75
Recognition | 6 | 0.75
Live calls and online collaboration | 0 | 0
Notification dashboard | 12 | 1.5
Admin
Review,Validate & assess answers of administered Assessment | 12 | 1.5
Review documents | 6 | 0.75
Approve/reject new User registration | 6 | 0.75
Dashboard | 12 | 1.5
Master data management | 16 | 2
User Role management | 6 | 0.75
Add/modify/delete training schedule | 16 | 2
Login/Logout | 2 | 0.25
Manage toolkits | 4 | 0.5
Manage guidelines | 4 | 0.5
Schedule Meetups & training | 0 | 0
Manage status | 4 | 0.5
System Features
Authentication, Authorization | 8 | 1
Exception Handling and Error logging | 4 | 0.5
Automated self assessment validation | 12 | 1.5
Payment Integration | 20 | 2.5
Notification Management | 16 | 2
Data Integration with govt/private database | 0 | 0 | 8 days | Based on twillio – May be excluded from the estimate
Integration with database of the chamber of commerce for validation | 16 | 2
Integrate LIVE calls | 0 | 0
Integration with Ma'an websites | 8 | 1
Bilingual Site (Arabic / English) | 64 | 8
Third party integrations | 32 | 4
Protection against injection attacks (SQL, CRLF) | 6 | 0.75
URL encoding, Input validation | 6 | 0.75
Cookie Encryption, Cookie replay attacks | 6 | 0.75
Session hijacking prevention | 6 | 0.75
Cross site scripting and session management | 6 | 0.75
Auditing & Logging | 6 | 0.75
Reccomendation engine for toolkits, guidelines, awards, incentives etc based on company status | 12 | 1.5
Workflow engine | 12 | 1.5
SQA
QA & Bug fixing | 190.2 | 23.775
UAT | 40 | 5
Deployment | 8 | 1
Total | 1071.42 | 133.9275
Comments/Assumptions
The effort may change after a detailed system study and also after receiving the details of the external componets to be integrated
Payment gateway details would be shared by the client
Live calls SDK/API would be shared by the client
Only english languages is considered for the application
Automated self assessment validations would be based on the objective type questions. Descriptive answers need to be manually verified.
The details of the external APIs for validating the comapany would be shared by the client [Eg:- Other government or private data-base (API)]