## Member Management
Raviz Rewards Card | July 21 2017
Friday
Module | Man Hours | Man Days | Member Management
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 16 | 2 | Designer | 1 | 64 | 8 | 8
Functional Specification | 16 | 2 | Sr.Developer | 1 | 60 | 7.5 | 7.5 | 23.75 | 24
Project Management | 17 | 2.125 | Jr Developer | 1 | 132 | 16.5 | 16.5
Solutioning | 8 | 1 | PM | 1 | 57 | 7.125 | 7.125
Graphic Design (Android App + Web application) | 48 | 6 | QA | 2 | 30.5 | 3.8125 | 7.625
Working Prototype | 16 | 2 | Total |  | 343.5 |  | 46.75 | 374
Development
Member Management Attributes | 20 | 2.5 | Total Delivery days | 28.3125 |  | Total Delivery days | 50
Membership |  | 0 | Total Man day Effort | 46.75 |  | Total Effort | 104.9
Membership type (Family, individual, corporate) |  | 0 | Installation & training | 3
membership Expiry date |  | 0
basic information (name, address, DOB, Mob, Off, email, citizenship etc) |  | 0 | Master Data
Membership tier ( Platinum, silver, gold etc) |  | 0 | Total Delivery days | 15.775
Allergies |  | 0 | Total Man day Effort | 18.775
Seniority level (calculated based on formula) |  | 0
VIP Status (Politician, high net worth, Frequent guest) |  | 0 | Property Setup
membership renewal date |  | 0 | Total Delivery days | 8.375
Family (names, ages, sex, family status etc) |  | 0 | Total Man day Effort | 8.375
membership status |  | 0
DOJ |  | 0 | Prototyping
Reservations and Bookings |  | 0 | Total Delivery days | 15.5
Room type preference (size and features wise) | 2 | 0.25 | Total Man day Effort | 31
Concierge service requirements | 2 | 0.25
Bed type preference | 4 | 0.5
Reservation history | 8 | 1
Booking history | 8 | 1
Accounting |  | 0
Dues Status | 8 | 1
Payment due date | 2 | 0.25
Pending Dues | 2 | 0.25
Payment period ( Annual, quarterly, monthly etc) | 4 | 0.5
Life time credit acquired | 8 | 1
Member credit limit | 2 | 0.25
Credit available | 4 | 0.5
View Discounts available | 8 | 1
Points received | 4 | 0.5
Points Availed | 4 | 0.5
Member Functions |  | 0
Update various personal attributes | 16 | 2
Membership payment | 12 | 1.5
Room Reservation (Select Room: room type, beds, adults, children etc) | 12 | 1.5
Apply for discounts | 6 | 0.75
Restaurant reservations( seat preference, Food preference, alc preference, Guest size, pre order ) | 8 | 1
Add referrals | 6 | 0.75
Management Functions |  | 0
Revoke Membership | 4 | 0.5
Updgrade/Downgrade Member Tier | 4 | 0.5
Add Work Order (KOT) | 8 | 1
Search Members | 8 | 1
Update member attributes | 16 | 2
Testing & Deployment |  | 0
Testing | 57 | 7.125
UAT | 4 | 0.5
Deployment Support | 4 | 0.5
Total Effort | 376 | 47
Assumptions
Device/s and required SDK and Test cards will be provided by the client
Merchant ID and other required payment gateway details will be provided by the client
Required source code of the modules should be provided if it require integration with any existing application
Access to the database will be provided to update the payment transactions

## Master Data
Development
Membership | 28 | 3.5 | Master Data Management
Membership Tier (platinum, Gold, Silver, Bronze, Guest) | 0 | 0 |  | No | Man hours | Man Days | Total Effort
Food preference (Veg, Non Veg, Jain, Vegan) | 0 | 0 | Designer | 1 | 0 | 0 | 0
Dining areas ( names of restaurants) | 0 | 0 | Sr.Developer | 1 | 24 | 3 | 3
Payment Cycles ( Yearly, Quarterly, Monthly) | 0 | 0 | Jr Developer | 1 | 88 | 11 | 11 | 14.25 | 14
Membership Types (Family, Individual, corporate) | 0 | 0 | PM | 1 |  | 0 | 0
Corporate membership Type (Access levels & priveleges) | 0 | 0 | QA | 1 | 38.2 | 4.775 | 4.775
Allergies | 0 | 0 | Total |  | 150.2 |  | 18.775
Religion (Hindu, christian, muslim, Jew etc) | 0 | 0
VIP Status (Politician: Active, inactive; High Networth, artist, Freq guest etc.) | 0 | 0 | Total Delivery days |  | 15.775
Drinking Preferences (Fresh juice, vidka, whisky etc or Alc /nonalc) | 0 | 0 | Total Man day Effort |  | 18.775
Dues collection preference (manual, Automated/recurring) | 0 | 0
Currencies | 0 | 0
Identity Type (Aadhar, PAN, DL, Passport, Visa) | 0 | 0
Payment Methods( Bank, credit, debit) | 0 | 0
Bookings And reservations | 40 | 5
Room types | 0 | 0
Room features | 0 | 0
Conceirge services | 0 | 0
Bed types | 0 | 0
Other Unique club features | 0 | 0
Club features | 0 | 0
Feature charges | 0 | 0
Reservation and bookings | 0 | 0
Reservation settings (Onhold, Confirmed etc) | 0 | 0
Room Tariffs | 0 | 0
Room discounts (corporate vs. Individual/fmly) | 0 | 0
Room Amenities | 0 | 0
Applicable taxes | 0 | 0
Room status(Dirty/clean/Work Order) | 0 | 0
Seasons & Seasonal rates | 0 | 0
Transportation requirements(tickets, taxi standby, on call, Tour assistance) | 0 | 0
Pickup requirements(airport/bus/train) | 0 | 0
Reservation type (enquiry, hold, reserve etc) | 0 | 0
Room Revenue types (Late check out, cancellation, no show, room rate) | 0 | 0
Accounting
Taxes | 8 | 1
Arbitary charges | 4 | 0.5
Payment processing | 16 | 2
KOT Types (Bar, Restaurant, Shops, conceirge, room service, Internet café, Gym) | 8 | 1
POS | 8 | 1
Holiday list | 2 | 0.25
Testing & Deployment |  | 0
Testing | 34.2 | 4.275
UAT | 4 | 0.5
Deployment Support | 4 | 0.5
Total Effort | 156.2 | 19.525

## Property Setup
Development
property setup | 32 | 4 | Master Data Management
description | 0 | 0 |  | No | Man hours | Man Days | Total Effort
facilities & attractions | 0 | 0 | Designer | 1 | 0 | 0 | 0
checkin policy | 0 | 0 | Sr.Developer | 1 | 0 | 0 | 0
hotel policy | 0 | 0 | Jr Developer | 1 | 48 | 6 | 6 | 6.25 | 6
travel directions | 0 | 0 | PM | 1 |  | 0 | 0
cancellation policy | 0 | 0 | QA | 1 | 19 | 2.375 | 2.375
things todo | 0 | 0 | Total |  | 67 |  | 8.375
parking details | 0 | 0
children & extra guest policy | 0 | 0 | Total Delivery days |  | 8.375
hotel description | 0 | 0 | Total Man day Effort |  | 8.375
booking conditions | 0 | 0
important landmarks | 0 | 0
Booking details displayed on confirmation(start-end dates, no of nights, names,no of rooms, rate plan, price etc) | 0 | 0
Images | 0 | 0
Amenities( roomwise based on room type) | 0 | 0
bulk amenities (hotel wide) | 0 | 0
Manage Rooms | 18 | 2.25
room types, bed types | 0 | 0
rate types | 0 | 0
rate plan (queen, king, king with breakfast etc) | 0 | 0
images | 0 | 0
reservation type | 0 | 0
Manage house keepers | 0 | 0
Testing & Deployment |  | 0
Testing | 15 | 1.875
UAT | 4 | 0.5
Deployment Support | 4 | 0.5
Total Effort | 73 | 9.125

## Prototyping
Prototyping
Reservation & Bookings
Guest information (Name, Address, Country) | 3 | 0.375 | Prototyping
Stay Information(Room type, room, no, services:room, room + breakfast etc.) | 3 | 0.375 |  | No | Man hours | Man Days | Total Effort
Additional details( Arrival, departure, nights, adult+child count, reservation Type) | 4 | 0.5 | Designer | 2 | 124 | 15.5 | 31
Contact Info(email, Phone, Mobile, fax) | 3 | 0.375 | Sr.Developer | 1 | 0 | 0 | 0
Others( Identity type, identity, nationality, gender, VIP status) | 3 | 0.375 | Jr Developer | 1 | 0 | 0 | 0 | 13.5 | 0
Allergies | 2 | 0.25 | PM | 1 | 0 | 0 | 0
Billing Information( rates:contract, normal, manual; billto:company, group owner, guest; tax exempt iD; Payment mode: Cash, credit,debit) | 4 | 0.5 | QA | 1 | 0 | 0 | 0
Room features (bed types, A/C, Tub, Conceirge services, room types etc.) | 2 | 0.25 | Total |  | 124 |  | 31
back office functions ( Reservation list, arrival list, departure list, release reservation, hold reservation, pending reservations, cancelled reservations,room status: FD remarks, House keeper remarks house keeper assigned, unsettled folios) | 8 | 1
Room tariffs | 3 | 0.375 | Total Delivery days |  | 15.5
KOT: Arbitary Charges( Voucher no, Tax, description) | 4 | 0.5 | Total Man day Effort |  | 31
Payments(Type, amount, voucher no, comment) | 8 | 1
Voucher details( Vno, prepared by, type, payment method , date) | 6 | 0.75
Charges( Type, amount, voucher no, comment) | 2 | 0.25
Work Orders(order no, description, room #,category(maintenance, repair, clean),block from-to, priority, assign to, status (assigned, completed, pending), deadline) | 8 | 1
Reservation report(No show, Released reservations, checked in), guest list | 6 | 0.75
Accounting
Numbering formats (GL Ref No, Sales inv, AR tran no, sales order no, vendor inv, AP tran no, sales quot no, RFQ no, part no, employess no, customer no, vendor no) | 8 | 1
Year end | 2 | 0.25
Admin Users | 6 | 0.75
Chart of accounts | 6 | 0.75
Departments | 3 | 0.375
Types of business | 6 | 0.75
Create Users | 8 | 1
User Permissions( create a/c, AP All, AP vouchers, AP create inv voucher, AP Transaction create Voucher, AR all, AR create Inv, AR transaction create voucher, assembly stock, assets admin) | 6 | 0.75
Defenition of parts | 4 | 0.5
Defenition of part groups | 4 | 0.5
Defenition of assembles ( for menu) | 4 | 0.5
Part information | 4 | 0.5
Vendor information | 4 | 0.5
Customer information | 4 | 0.5
Defenition of services | 4 | 0.5
Tax account defenitions | 4 | 0.5
Accounts receivable | 12 | 1.5
Invoices | 12 | 1.5
payments | 8 | 1
Vouchers | 8 | 1
Raise invoices | 8 | 1
Billing Statement | 8 | 1
Member Billing
Create KOT | 8 | 1
Edit KOT | 16 | 2
Cancel KOT |  | 0
KOT audit trail | 8 | 1
KOT Pre execution mode | 4 | 0.5
KOT Confirmed | 4
POS receipt | 6 | 6
Testing & Deployment
Testing |  | 0
UAT |  | 0
Deployment Support |  | 0
Total Effort | 248 | 35.75