## DOH
Standards and Policies System |  | 15/01/2019
Wednesday
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | BA/ Documentation | 1 | 6 | 6
System Study | 24 | 3 | UI Design | 1 | 2.5 | 2.5 | 33.75 | #REF! | 0 | #REF!
SRS, FRS, Project Plan, Weekly Status, Meetiings, QA plans, test cases | 24 | 3 | UI/UX/ Prototyping | 1 | 2.5 | 2.5
Design Custom | 20 | 2.5 | Developer | 1.5 | 22.5 | 33.75
Prototype - complete prototype English | 20 | 2.5 | PM | 1 | 3.575 | 3.575
Project Management | 28.6 | 3.575 | QA | 1.5 | 9.8417 | 14.7625
Application Development and Testing |  |  | Total |  | 40.9167 | 63.0875
Creating Developemt Environment PHP | 8 | 1
End User |  |  | Deliver Days | 40.9167
Internal User | 8 | 1 | Total Effort | 63.0875
Internal (DOH division/ employee) |  | 0
Division |  | 0
Department |  | 0
Section |  | 0
Employee Number |  | 0
Ext |  | 0
New/Update request, select request type, delete request, save application as draft, Cancel request unless submitted | 32 | 4
Receive notifications/alerts on status of the application, receive SMS, view status | 12 | 1.5
Dashboard: Waiting time, Planned duration, actual duration, Application Status(Save as Draft,Submitted,Clarification Required,Work in Progress,Closed,Cancelled,Aborted) | 12 | 1.5
Text box to add comments | 4 | 0.5
External User | 8 | 1
External (Community member) |  | 0
Facility/ Workplace: |  | 0
Job Position: |  | 0
Contact Details: |  | 0
Email: |  | 0
Mobile: |  | 0
New/Update request, select request type, delete request, save application as draft, Cancel request unless submitted | 24 | 3
Receive notifications/alerts on status of the application, receive SMS, view status | 16 | 2
Dashboard: Waiting time, Planned duration, actual duration, Application Status(Save as Draft,Submitted,Clarification Required,Work in Progress,Closed,Cancelled,Aborted) | 32 | 4
0
PS Officer
View submitted application | 6 | 0.75
Create project | 6 | 0.75
Assign Project/application to other staff if needed | 6 | 0.75
View History Log | 4 | 0.5
Dashboard | 16
Login/Logout | 2 | 0.25
Manager
Assign Project/application to officer | 6 | 0.75
Dashboard | 12 | 1.5
Login/Logout | 2 | 0.25
0
Admin
Assign/Reassign project to a staff | 6 | 0.75
Receive E-mails | 6 | 0.75
Dashboard | 12 | 1.5
Login/Logout | 2 | 0.25
Master data | 16 | 2
System
Notification Management | 6 | 0.75
Email / SMS management | 6 | 0.75
Auditing / Logging events | 8 | 1
Authentication / Authorization | 8 | 1
Quality Assurance
QA & Bug Fixing | 100.1 | 12.5125
UAT | 12 | 1.5
Deployment | 6 | 0.75
Total Effort | 520.7 | 63.0875
Assumption
Language : English Only