## Etisalat Academy Application
| Etisalat Academy |  | 2018-01-31
Wednesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 33 | 33
1 | Business analysis | 8 | 1 | Sr Developer | 1 | 41 | 41 | 90.5 | 91
2 | Project Management | 72.4 | 9.05 | Jr Developer | 1 | 50 | 50
3 | Project Documentation (SRS, Scope, WBS etc.) | 24 | 3 | PM | 1 | 9.05 | 9.05
4 | Complete running prototype (Admin and Front end) | 264 | 33 | BA | 1 | 4 | 4
| Development |  |  | Tech writer | 0 | 7 | 0
| Admin |  |  | QA | 2 | 19.1 | 38.2
1 | Assign roles | 12 | 1.5 | Total |  |  | 175.25
2 | Manage Users | 12 | 1.5
3 | Manage Menu | 8 | 1 | Bilingual site
| Manage Home Page | 32 | 4
| Manage About Us | 20 | 2.5 |  |  | Man Months
4 | Manage Why Choose Us | 20 | 2.5 | Total Delivery days | 102.1 | 5.105
5 | Manage Training | 28 | 3.5 | Total Effort | 175.25 | (+1 Day deployment)
| Manage Facilities | 28 | 3.5
| Manage Knowledge Centre | 20 | 2.5
| Manage Secondary Menu | 28 | 3.5
| Manage Footer Menu | 28 | 3.5
User Login - Student
1 | Sign up | 8 | 1
2 | Login and Dashboard | 16 | 2 | Business Analyst | 80 | 8 | 8
3 | Book marked courses | 8 | 1 | User Experience | 64 | 16 | 16
| Course Finder | 8 | 1 | Application Architect | 24 | 8 | 8
| Settings | 28 | 3.5 | Lead Developer | 80 | 160 | 80
| Learning Dashboard | 40 | 5 | Developer | 80 | 160 | 120
| User Login - Trainer |  |  | Database Architect | 24 | 8 | 8
| Login and Dashboard | 8 | 1 | IOS Developer | 40 | 160 | 120
| Training Dashboard | 40 | 5 | QA | 40 | 40 | 240
| Settings | 16 | 2 | Tech Writer |  |  | 24
| Front End Integration of non login pages |  |  | Total Effort | 217 Man Days |  | 1616
| Home Page | 20 | 2.5
| About Us | 16 | 2 | Total Effort Variation : | 180 - 200 days
| Why Choose Us | 16 | 2
| Training | 20 | 2.5
| Facilities | 28 | 3.5
| Knowledge Centre | 40 | 5
| Search | 10 | 1.25
| Careers | 10 | 1.25
| Contact Us | 8 | 1
| Copyrights | 4 | 0.5
| Survey | 8 | 1
| Code of Practice | 8 | 1
| Privacy Policy | 4 | 0.5
| Terms and Conditions | 4 | 0.5
| Site-map | 40 | 5
Integration With Maximizer CRM
| API Development | 40 | 5
System features
1 | Auditing & logging | 4 | 0.5
2 | Exception handling | 4 | 0.5
3 | User Manual | 24 | 3
4 | Document Archival | 8 | 1
Quality Assurance
1 | QA & Bug Fixing | 289.6 | 36.2
2 | UAT | 16 | 2
3 | Deployment | 8 | 1
| Total Effort | 1406 | 175.75
#REF!

## POM Delivery
Phase | Activity | Man Days
Pre-Dev | Designing & prototyping | 33 | [5 empty] | Design | 33
Phase 1 | Academy + System Features | 34.5 | [5 empty] | Dev | 104.5 | 5.225
Phase 2 | Portal + Admin + API integration | 56 | [5 empty] | Testing | 38.2
Phase 3 | Blog + Gallery + Training Programs | 14 | ( Min) | Max depends on complexity |  |  |  | Doc+Admin | 13.05
[8 empty] | Total | 188.75
|  | Teams | Month 1 |  | Month2 |  | Month 3 |  | Month 4
|  | Design | Academy | Portal | Blog | Misc
|  | Dev 1 |  | Academy
|  | Dev 2 |  |  |  | Portal
|  | Dev 3 |  |  |  | Blog
Testing