## connect.ae web design
| Lulu Mall |  | 2017-09-05
Tuesday
| Module | Hours | Man Days | Web Development
| Initiation |  |  |  | No | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) | 24 | 3 | Designer | 1 | #REF! | #REF!
2 | Functional Specification | 24 | 3 | Sr Developer | 1 | 18 | 18 | 0 | 58
3 | Project Management | 64 | 8 | Jr Developer | 1 | 40 | 40
| Development |  |  | PM | 1 | 8 | 8 | [6 empty] | 12.5
| Site Design |  |  | BA | 1 | 6 | 6
1 | Home page (Inspiration yellowpages.com, connect.ae) |  |  | QA | 2 | 1.5281 | 3.0562
2 | Home Page Sections |  |  | Total |  |  | #REF!
3 | Time sensitive adverts & promotions
4 | Featured company section |  |  | Total Delivery days | #REF! |  |  |  | Resource/Skill | Month 1 | Month 2 | Month 3
5 | Mobile app Download section |  |  | Total Effort | #REF! | (+1 Day deployment) |  |  | Proj. Manager | 80 | 60 | 60 | 200
6 | Header | [7 empty] | Architect | 80 | 16 | 16
7 | Logo, language Selection, login, Signup | [7 empty] | Business Analyst | 48 | 12 | 12 | 72 | 48
8 | Footer (links managed by admin) |  |  |  |  | #REF! |  |  | User Experience | 120 | 60 | 60 | 240 | #REF!
| About Us |  |  | Suggestions |  |  |  |  | Team Lead Web | 160 | 160 | 80 | 880 | 464
| Contact |  |  | Live videos |  |  |  |  | Web Developer | 160 | 160 | 160
| Advertise | [7 empty] | QA | 80 | 160 | 160 | 400 | 24.45
| Help | [7 empty] | Total Effort |  |  | 1904 | 39.3908
| Privacy | [10 empty] | #REF!
Terms of use
| Frequent Searches | [7 empty] | 0
Feedback
Site Map
| Hamburger Menu | [7 empty] | Resource/Skill | Month 1 | Month 2 | Month 3
9 | Newsletter signup | [7 empty] | Proj. Manager | 80 | 60 |  | 140
10 | Dynamic image behind search bar | [7 empty] | Architect | 80 | 16
| Social media links | [7 empty] | Business Analyst | 48 | 12 |  | 60 | 48
11 | Search Bar (location enable option + Map view results option) | [7 empty] | User Experience | 120 | 60 |  | 180 | #REF!
| Company Profile page (Refer YP.com detailed pages) | [7 empty] | Team Lead Web | 160 | 160 |  | 800 | 464
| Dynamic sections based of membership type. Sections supressed for non privileged users | [7 empty] | Web Developer | 160 | 320
| Deatailed profile pages similarr to YellowPages company directory | [7 empty] | QA | 80 | 320 |  | 400 | 24.45
| Page Details | [7 empty] | Total Effort |  |  | 1676 | 44.7494
| Tabbed (Business details, Coupons, Gallery, Reviews) | [10 empty] | 0
Business Details
Description, logo, opening hours, deep links, video, social media links
Send email to company (mobile and web)
Forward company details via SMS (mobile)
Save company details as vCard (mobile)
Click to call (mobile)
Post in social media
Web Address, Price range, neighbourhoods, categories
List of features (Child safe , cuisine, attire etc)
Order online (link)
View Menu (link or image)
Suggest an edit
Years in business
Reviews count on top connect.ae & aggregators count
Overall Rating
Reviews (tabbed)
Reviews from connect.ae
Reviews from aggregators
Image gallery,
List Reviews
Post Reviews
Related searches
Advertisement section
Generic page design (content managed by client)
Search bar features
5 dynamic search results (refer connect.ae)
Each result prepended with icons (one of briefcase, magnifying class, clock, POI)
Magnifying Glass: Directs to the search results page (results from internal source)
Briefcase: Directs to the company profile
Clock: use previous search result for the keyword in use
POI: Directs to map
For tablets and mobiles, results based on location
Search Results page (Combination of Connect.ae & YP.com)
Total results returned
List of 20 results page
map with number tags (resizable)
Sort by relevance, distance propolarity ( like connect.ae)
filter by ofder online, kid friendly etc (similar to YP.com)
About Search results
Sponsored results
Map fixed while scrolling
Sponsored advertisements on right panel
Homepage header fixed while scrolling
Suggested keywords
Reset search filters and sorting to defaults
Search results details (individual listing)
Thumbnail image, Social media links
Phone, fax & address, Number on map
Hours of operation
Description
Rating (connect.ae & aggregator)
Website addr and Menu, Order online (link), Order online (link)
Categories (list)
Clicking on map number resizes and zooms the map witn selected number and surrounding listings
Registrations
User registration
Advertisement registration
Register via social media
Directions to location (Map Details page)
Print Directions
Route on map
Directions list
Map Coordinates
SEO
Breadcrumb trails
No follow tags for hyper links
Schema tags for internal search engine (like u tube)
Human redable URLs
static content for category pages
update metatags dynamically (using varnish) esp. for category pages
Responsive design
Admin Dashboard
Screens for master data
Screen for Users, categories, adverts etc
Advertisement Revenue management
API management
System Features
102 | Authentication and Authorization | 4 | 0.5
103 | Permission based access levels | 4 | 0.5
104 | Bilingual website | 3 | 0.375
105 | Microsoft Word Integration for publishers | 3 | 0.375
106 | Version Rollback | 2 | 0.25
107 | Sheduled Publishing | 2 | 0.25
108 | Mobile friendly site | 2 | 0.25
109 | SEO Friendly | 4 | 0.5
110 | Advanced workflow and appoval process | 6 | 0.75
111 | Blog posts linked to social media | 5 | 0.625
112 | User Friendly content management for editors | 6 | 0.75
113 | Auditing and logging | 6 | 0.75
| Quality Assurance |  | 0
114 | QA | 16.45 | 2.0562
115 | UAT | 8 | 1
116 | Penetration testing | 8 | 1
117 | Deployment | 8 | 1
118 | Training & Development for Core Members | 8 | 1
| Total Effort | 207.45 | 25.9312
| Estimate Assumptions. Effort does not include languages other than English and Arabic. Creatives will be supplied by Client Development Contingent upon timely feedback from client Blog estimation assumes a simple blog similar to the current site (design included) Analytics is based on Google. Effort quoted for integration. Free without Integration | 25.9312

## Admin
Lulu Mall |  | 2017-09-05
Tuesday
Module | Hours | Man Days
Initiation
Requirements gathering and documentation (SRS) | 24 | 3
Functional Specification | 24 | 3
Project Management | 64 | 8
Development
Site Management (combined for connect admin & advertisers for simplicity)
Category management (metadata)
Time bound categories
Categories by package (Free, Visible & Ranked, The Look)
Free : Registration includes address and free categories
V&R: Free + Ranked Keywords + Keywords connected to categories
The Look: V&R + Logo, Gallery, Deep links, Text etc.
Manage Hamburger links
Advertisement management
Image, description, icon, gallery, Map coordinates, Address, Phone, Fax, Name
Category, Ranked keywords, Deeplinks, keywords related to categories, Email
Social media links, open hours, holidays, payment methods, accreditation, coupons
Coupon management
Coupon images, Description, Discount price, discount %, Refferal ID, Coupon code
coupon URL, Coupon name, Category, Company name (implied)
Newsletter
Create news letter
Manage content
Associate distribution list
Member regsitrations (Company profile)
name , email, phone, address, phone, fax
Social media links, open hours, holidays, payment methods, accreditation, coupons
Image, description, icon, gallery, Map coordinates, deep links, linked advertisements
Linked coupons, Linked categories (ranked key words, related categories etc.), category type
Template for Static Pages (managed Content)
About, Contact, Advertise, Help , Privacy, Terms of use, feedback,
Manage Time bound adverts
tag line, image, url etc
Manage Packages (categories)
Manage Searchbar background image
place holder for payed advertisement side bar
Manage footer links
Manage Web site users
Reporting with filters for date, location & segments
Company search keyword – all & specific keywords
Customer ID – company wise
Link click report
Map interaction report
Site Unique visitors/visits, pageviews, sections etc.
Most/Least viewed listings
Most/Least leads generating listings
Most/Least viewed multimedia (Videos/Pictures/Sound Clips)
Manage memcached or similar
Smart Metrics UI fro Varnish
Ranked Searchword limit
Deep link list limit
Manage access to API
Admin dashboard
Content manager roles
Manage roles (author, reviewer, publisher, editor)
Add users to roles
Adv management
Adv trafficking and delivery (behavioural and contextual targets)
Audience categorization: Traget audience age, marital status, financial outlook, time of day
Product categories, season, time of year
Advertiser preferences
Frequency capping for adverts
Pricing models (create and manage) : CPM, CPC & CPD
Built in targeting (geography, bandwidthing, browser, browser lang, OS and domain)
Customizable targeting criteria
Advertisment Revenue Reports for connect.ae & expenses for advertisers
sponsorship, rich media, leads, classifieds, digital video,
Mobile, desktop, banners, search

## System Features
| Lulu Mall |  | 2017-09-05
Tuesday
| Module | Hours | Man Days
Initiation
1 | Requirements gathering and documentation (SRS) | 24 | 3
2 | Functional Specification | 24 | 3
3 | Project Management | 64 | 8
Development
System Features
1 | Authentication and Authorization
2 | Permission based access levels
3 | Bilingual website
4 | Advanced workflow and appoval process for content management
5 | Content management framework
6 | Auditing and logging
7 | Semantic analysis of keywords
8 | Word recognition using fuzzy logic
word stemming
synonym recognition
Geographic context analysis (to enable hyper local search)
Rule based search results
parametrized search result limit
search dropdown categorization
Web Based search results
Mobile based search results
Search results based on geo fencing
Randomization of search results for results with identical priorities
9 | Advertiements
10 | Time bound advertisements
Context sensitive advertisements based on key words
11 | integration with advertisements networks
Detailed company page based on package
API calls
company
product: logo
product: homepage
product email
Product: click to call
Product: company description
permission product: Ranked search word limit
permission product: deep link
Permission product: PDF
Mobile search logic order: local, comprehensive, paid adverts first,
payment processing
CRM data flow
add customer from web to CRM
Scheduled job generates Excel sheet
move the spreadsheets to landing pad via SFTP
Advert XML generated from the spread sheet and pumped to ActiveMQ
Search Integration with 3rd party
Zomato
booking
roundmenu
Reviews integration
Zomato
Tripadvissor
Roundmenu
Connect.ae
Map Integration
Zoom in and zoom out
driving directions
Search result page
API for mobile devices
Scheduler related
CRM data flow
Sort and filter for search page
102 |  | 4 | 0.5
103 |  | 4 | 0.5
104 |  | 3 | 0.375
105 |  | 3 | 0.375
106 |  | 2 | 0.25
107 |  | 2 | 0.25
108 | System Features | 2 | 0.25
109 |  | 4 | 0.5
110 |  | 6 | 0.75
111 |  | 5 | 0.625
112 |  | 6 | 0.75
113 |  | 6 | 0.75
0
114 |  | 16.45 | 2.0562
115 |  | 8 | 1
116 |  | 8 | 1
117 |  | 8 | 1
118 |  | 8 | 1
Quality Assurance
QA
UAT
Penetration testing
Deployment
Training & Development for Core Members

## connect.ae mobile design
| Lulu Mall |  | 2017-09-05
Tuesday
| Module | Hours | Man Days
Initiation
1 | Requirements gathering and documentation (SRS) | 24 | 3
2 | Functional Specification | 24 | 3
3 | Project Management | 64 | 8
Development
Site Design
1 | Login page
2 | Design and development | 8 | 1
3 | Signup
4 | Design and development(Api integration,Validation) | 12 | 1.5
5 | Register with social media(Face book and gmail) | 16 | 2
6 | Home page
7 | Page design | 2 | 0.25
8 | Sliding menu(Hamburger Menu) | 2 | 0.25
Frequent Searches
Feedback
Newsletter signup
language Selection
Search Bar (location enable option + Map view results option)
| location enable option | 2 | 0.25
| Categories (list) | 4 | 0.5
Search Result
| List view | 8 | 1
Frequent Searches
9 | Listview | 6 | 0.75
10 | Feedback
| Feed back page design ,Api integraqtion | 6 | 0.75
11 | Newsletter signup
| Page design and Api integration | 6 | 0.75
language Selection
| Popup design , Api integration,Development and laguage integration | 16 | 2
Detail Page
| Tabbed (Business details, Coupons, Gallery, Reviews) | 16 | 2
Business details
Coupons
Gallery
Reviews
Advertisement section
| Business details Design and Api integration | 16 | 2
Description
opening hours
deep links
video
social media links
Send email to company
Forward company details via SMS
Save company details as vCard
Click to call
Post in social media
Web Address, Price range, neighbourhoods, categories
List of features (Child safe , cuisine, attire etc)
Order online (link)
View Menu (link or image)
Years in business
Reviews count on top & aggregators count
Overall Rating
Map view results
Coupons
| Page design and Api integration | 8 | 1
Gallery
| Page design and Api integration | 12 | 1.5
| Reviews | 8 | 1
Reviews from Admin
Reviews from aggregators
Post Reviews
Advertisement section
Page design and Api integration
deep links
| webview and Api | 4 | 0.5
video
| Page design,Api integration and video playe integration | 16 | 2
Send email to company
| Page design , Api integration and email integration | 16 | 2
Forward company details via SMS
| Page design , Api integration and sms gate way integration | 16 | 2
Save company details as vCard
| Page design and Development | 8 | 1
Click to call
| Api integration, Click to Call integration | 16 | 2
Post in social media(Face book)
| Development | 2 | 0.25
List of features (Child safe , cuisine, attire etc)
| Page design and Api integration | 4 | 0.25
Reviews count on top & aggregators count
| Api integration | 2 | 0.25
Map view results
| Show Directions | 6 | 0.75
Route on map
| Reviews from aggregators | 4 | 0.5
Page design and Api integration
| Post Reviews | 4 | 0.5
Page design and Api integration
Show Directions
| Create map view and drow the direction | 16 | 2
Route on map
| Create map view and drow the direction | 16 | 2
| Developer side testing and bug fixing | 32 | 4
| Page design ,lcon design in photoshop | 144 | 18
|  | Total | 56.5
update metatags dynamically (using varnish) esp. for category pages

## Sheet1
ad management server
advertising campaigns
campaign subscription page
separate commercial packages for mobile and web
SME Popular articles editorials
hamburger navigation links managed by CMS
purchase geographies
in page navigation and in page communication (show green button)
Customer login to store address (work, Home, or other named locations)
enable click to call services (chat, text, phone, voip, web cam)
static content for URLS (see SEO)
assign metatags to category pages (using varnish?/)
integrating external map navigation
site catalyst
update metatags dynamically (using varnish) esp. for category pages