## Estimates
Total Effort | Man Days | Delivery Days
Web Design | 198.0125 | 121.3937
Admin design | 206.075 | 113.8625
System design | 251.5075 | 133.4913
Android | 137.7 | 86.55
IOS | 165.24 | 108.1875 | [10 empty] | 1090
Bilingual Site | 131.3
Total | 1089.835
|  |  |  | Phase 1 |  |  | Phase2
PM | 52.62 | 8.77 | Resource/Skill | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint5 | Sprint 6 | Computed | Original
Development | 511.3 | 85.2167 | Project Manager | 11 | 10 | 5 | 11 | 10 | 5 | 52 | 52.62
IOS Dev | 88.2 | 14.7 | Business Analyst | 16 | 12 | 5 | 16 | 10 | 5 | 64 | 63.8
Android Dev | 71 | 11.8333 | User Experience | 30 | 15 | 3 | 25 | 15 | 2 | 90 | 90
QA | 212.815 | 35.4692 | Application Architect | 10 | 5 |  | 8 | 5 |  | 28 | 511.3
Design | 90 | 15 | Database Architect | 6 |  |  | 6 |  |  | 12
BA | 63.8 | 10.6333 | Technical Lead | 18 | 10 | 5 | 18 | 10 | 5 | 66 |  | 511
|  |  | Sr. Developer |  | 25 | 20 |  | 20 | 20 | 85
|  |  | Developer |  | 80 | 80 |  | 80 | 80 | 320
|  |  | Android |  | 20 | 15 | 15 | 8 | 13 | 71 | 71
|  |  | IOS |  | 20 | 20 | 15 | 20 | 15 | 90 | 88.2
|  |  | QA Manager | 8 | 8 | 8 | 8 | 7 | 6 | 214 | 212.815
|  |  | QA | 5 | 20 | 62 |  | 20 | 62 | -2.165
|  |  | Total Effort | [5 empty] | 1092 | 1092 | 1089.735
With

## UIDevelopment
| Connect.ae |  | 2017-09-05
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort | Original Effort | Adjusted Effort
| Initiation |  |  | Designer | 1 | 38 | 38
1 | Requirements gathering and documentation (SRS) | 64 | 8 | Sr Developer | 1 | 37 | 37 | 102.25 | 102
2 | Functional Specification | 24 | 3 | Jr Developer | 1 | 65 | 65
3 | HTML Design |  | 38 | PM | 1 | 10.225 | 10.225
4 | Project Management | 81.8 | 10.225 | BA | 1 | 11 | 11
| Development |  | 0 | QA | 2 | 18.3937 | 36.7875
1 | Web Development |  | 0 | Total |  |  | 198.0125
2 | Home page (Inspiration yellowpages.com, connect.ae) | 16 | 2
3 | Home Page Sections | 0 | 0
4 | Time sensitive adverts & promotions | 5 | 0.625 | Total Delivery days | 121.3937
5 | Featured company section | 5 | 0.625 | Total Effort | 198.0125 | (+1 Day deployment)
6 | Mobile app Download section | 5 | 0.625
7 | Header | 5 | 0.625
8 | Logo, language Selection, login, Signup | 8 | 1
| Footer (links managed by admin) | 8 | 1
| About Us | 4 | 0.5 |  |  |  |  | 192
| Contact | 4 | 0.5
| Advertise | 2 | 0.25
| Help | 2 | 0.25
| Privacy | 2 | 0.25
| Terms of use | 2 | 0.25
| Frequent Searches | 8 | 1
| Feedback | 2 | 0.25
| Site Map | 4 | 0.5
9 | Hamburger Menu | 16 | 2
10 | Newsletter signup | 4 | 0.5
| Dynamic image behind search bar | 8 | 1
11 | Social media links | 2 | 0.25
| Search Bar (location enable option + Map view results option) | 32 | 4
| Company Profile page (Refer YP.com detailed pages) | 0 | 0
| Dynamic sections based of membership type. Sections supressed for non privileged users | 16 | 2
| Deatailed profile pages similarr to YellowPages company directory | 16 | 2
| Page Details | 0 | 0
| Tabbed (Business details, Coupons, Gallery, Reviews) | 16 | 2
| Business Details | 0 | 0
| Description, logo, opening hours, deep links, video, social media links | 8 | 1
| Send email to company (mobile and web) | 4 | 0.5
| Forward company details via SMS (mobile) | 8 | 1
| Save company details as vCard (mobile) | 8 | 1
| Click to call (mobile) | 16 | 2
| Post in social media | 4 | 0.5
| Web Address, Price range, neighbourhoods, categories | 6 | 0.75
| List of features (Child safe , cuisine, attire etc) | 12 | 1.5
| Order online (link) | 16 | 2
| View Menu (link or image) | 4 | 0.5
| Suggest an edit | 4 | 0.5
| Years in business | 2 | 0.25
| Reviews count on top connect.ae & aggregators count | 4 | 0.5
| Overall Rating | 4 | 0.5
| Reviews (tabbed) | 16 | 2
| Reviews from connect.ae | 8 | 1
| Reviews from aggregators | 8 | 1
| Image gallery, | 8 | 1
| List Reviews | 8 | 1
| Post Reviews | 8 | 1
| Related searches | 8 | 1
| Advertisement section | 8 | 1
| Generic page design (content managed by client) | 0 | 0
| Search bar features | 0 | 0
| 5 dynamic search results (refer connect.ae) | 48 | 6
| Each result prepended with icons (one of briefcase, magnifying class, clock, POI) | 6 | 0.75
| Magnifying Glass: Directs to the search results page (results from internal source) | 6 | 0.75
| Briefcase: Directs to the company profile | 6 | 0.75
| Clock: use previous search result for the keyword in use | 6 | 0.75
| POI: Directs to map | 6 | 0.75
| For tablets and mobiles, results based on location | 0 | 0
| Search Results page (Combination of Connect.ae & YP.com) | 0 | 0
| Total results returned | 4 | 0.5
| List of 20 results page | 8 | 1
| map with number tags (resizable) | 16 | 2
| Sort by relevance, distance propolarity ( like connect.ae) | 16 | 2
| filter by ofder online, kid friendly etc (similar to YP.com) | 32 | 4
| About Search results | 4 | 0.5
| Sponsored results | 16 | 2
| Map fixed while scrolling | 12 | 1.5
| Sponsored advertisements on right panel | 8 | 1
| Homepage header fixed while scrolling | 4 | 0.5
| Suggested keywords | 8 | 1
| Reset search filters and sorting to defaults | 8 | 1
| Search results details (individual listing) | 0 | 0
| Thumbnail image, Social media links | 8 | 1
| Phone, fax & address, Number on map | 8 | 1
| Hours of operation | 2 | 0.25
| Description | 2 | 0.25
| Rating (connect.ae & aggregator) | 8 | 1
| Website addr and Menu, Order online (link), Order online (link) | 4 | 0.5
| Categories (list) | 8 | 1
| Clicking on map number resizes and zooms the map witn selected number and surrounding listings | 16 | 2
| Registrations | 0 | 0
| User registration (home address, Office address) | 16 | 2
| Advertisement registration | 28 | 3.5
| Register via social media | 16 | 2
| Directions to location (Map Details page) | 0 | 0
| Print Directions | 16 | 2
| Route on map | 32 | 4
| Directions list | 32 | 4
| Map Coordinates | 4 | 0.5
| SEO | 40 | 5
| Breadcrumb trails | 0 | 0
| No follow tags for hyper links | 0 | 0
| Schema tags for internal search engine (like u tube) | 0 | 0
| Human redable URLs | 0 | 0
| static content for category pages | 0 | 0
| update metatags dynamically (using varnish) esp. for category pages | 0 | 0
| Responsive design | 0 | 0
116
117 | Quality Assurance
| QA | 286.3 | 35.7875
| UAT | 8 | 1
| Deployment | 8 | 1
| total effort |  | 199.2625

## Admin
2017-09-05
Connect.ae |  |  | Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort | Original Effort | Adjusted Effort
| Initiation |  |  | Designer | 1 | 0 | 0
| Requirements gathering and documentation (SRS) | 64 | 8 | Sr Developer | 1 | 43 | 43 | 133.5 | 133
| Functional Specification | 32 | 4 | Jr Developer | 1 | 90 | 90
| Project Management | 106.8 | 13.35 | PM | 1 | 13.35 | 13.35
|  |  |  | BA | 1 | 12 | 12
| Development |  |  | QA | 2 | 23.8625 | 47.725
| Site Management (Admin & Advertisers) |  |  | Total |  |  | 206.075
| Category management (metadata) | 0 | 0
| Time bound categories | 24 | 3
| Categories by package (Free, Visible & Ranked, The Look) | 0 | 0 | Total Delivery days | 113.8625
| Free : Registration includes address and free categories | 40 | 5 | Total Effort | 206.075 | (+1 Day deployment)
| V&R: Free + Ranked Keywords + Keywords connected to categories | 56 | 7
| The Look: V&R + Logo, Gallery, Deep links, Text etc. | 40 | 5
| Manage Hamburger links | 8 | 1
| Advertisement management | 96 | 12
| Image, description, icon, gallery, Map coordinates, Address, Phone, Fax, Name | 0 | 0
| Category, Ranked keywords, Deeplinks, keywords related to categories, Email | 0 | 0
| Social media links, open hours, holidays, payment methods, accreditation, coupons | 0 | 0
| Coupon management | 120 | 15
| Coupon images, Description, Discount price, discount %, Refferal ID, Coupon code | 0 | 0
| coupon URL, Coupon name, Category, Company name (implied) | 0 | 0
| Newsletter | 0 | 0
| Create news letter | 16 | 2
| Manage content | 8 | 1
| Associate distribution list | 8 | 1
| Member regsitrations (Company profile) | 32 | 4
| name , email, phone, address, phone, fax | 0 | 0
| Social media links, open hours, holidays, payment methods, accreditation, coupons | 0 | 0
| Image, description, icon, gallery, Map coordinates, deep links, linked advertisements | 0 | 0
| Linked coupons, Linked categories (ranked key words, related categories etc.), category type | 0 | 0
| Template for Static Pages (managed Content) | 16 | 2
| About, Contact, Advertise, Help , Privacy, Terms of use, feedback, | 0 | 0
| Manage Time bound adverts | 0 | 0
| tag line, image, url etc | 8 | 1
| Manage Packages (categories) | 40 | 5
| Manage Searchbar background image | 8 | 1
| place holder for payed advertisement side bar | 16 | 2
| Manage footer links | 8 | 1
| Manage Web site users | 16 | 2
| Reporting with filters for date, location & segments | 0 | 0
| Company search keyword – all & specific keywords | 12 | 1.5
| Customer ID – company wise | 12 | 1.5
| Link click report | 8 | 1
| Map interaction report | 24 | 3
| Site Unique visitors/visits, pageviews, sections etc. | 8 | 1
| Most/Least viewed listings | 8 | 1
| Most/Least leads generating listings | 8 | 1
| Most/Least viewed multimedia (Videos/Pictures/Sound Clips) | 16 | 2
| Manage memcached or similar | 32 | 4
| Smart Metrics UI from Varnish | 24 | 3
| Ranked Searchword limit | 24 | 3
| Deep link list limit | 4 | 0.5
| Manage access to API | 16 | 2
| Admin dashboard | 24 | 3
| Content manager roles | 0 | 0
| Manage roles (author, reviewer, publisher, editor) | 24 | 3
| Add users to roles | 8 | 1
| Adv management (campaigns) | 0 | 0
| Adv trafficking and delivery (behavioural and contextual targets) | 0 | 0
| Audience categorization: Traget audience age, marital status, financial outlook, time of day | 24 | 3
| Product categories, season, time of year | 24 | 3
| Advertiser preferences | 12 | 1.5
| Frequency capping for adverts | 12 | 1.5
| Pricing models (create and manage) : CPM, CPC, CPD etc. | 24 | 3
| Customizable targeting criteria | 56 | 7
| Advertisment Revenue Reports for connect.ae & expenses for advertisers | 0 | 0
| sponsorship, rich media, leads, classifieds, digital video, etc | 80 | 10
| Mobile, desktop, banners, search | 24 | 3
| QA |  | 0
| UAT | 373.8 | 46.725
| Deployment | 8 | 1
Total Effort
206.575

## SystemFeatures
| Connect.ae |  | 2017-09-05
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort | Original Effort | Adjusted Effort
| Initiation |  |  | Designer | 1 | 0 | 0
1 | Requirements gathering and documentation (SRS) | 64 | 8 | Sr Developer | 1 | 50 | 50 | 145.25 | 145
2 | Functional Specification | 56 | 7 | Jr Developer | 1 | 95 | 95
3 | Project Management | 116.2 | 14.525 | PM | 1 | 14.525 | 14.525
| Development |  |  | BA | 1 | 15 | 15
| 380 |  |  | QA | 2 | 38.4913 | 76.9825
1 | Authentication and Authorization | 24 | 3 | Total |  |  | 251.5075
2 | Permission based access levels | 32 | 4
3 | Bilingual website | 0 | 0
4 | Advanced workflow and appoval process for content management | 32 | 4 | Total Delivery days | 133.4913
5 | Content management framework | 40 | 5 | Total Effort | 251.5075 | (+1 Day deployment)
6 | Auditing and logging | 16 | 2
7 | Semantic analysis of keywords | 0 | 0
8 | Word recognition using fuzzy logic | 40 | 5
| word stemming | 32 | 4
| synonym recognition | 32 | 4
| Geographic context analysis (to enable hyper local search) | 32 | 4
| Rule based search results | 32 | 4
| parametrized search result limit | 32 | 4
| search dropdown categorization | 12 | 1.5
| Web Based search results | 24 | 3
| Mobile based search results | 32 | 4
| Search results based on geo fencing | 40 | 5
| Randomization of search results for results with identical priorities | 8 | 1
9 | Advertiements | 0 | 0
10 | Time bound advertisements | 40 | 5
| Context sensitive advertisements based on key words | 32 | 4
11 | integration with advertisements networks | 16 | 2
| Detailed company page based on package | 16 | 2
| API calls | 0 | 0
| company | 2 | 0.25
| product: logo | 2 | 0.25
| product: homepage | 2 | 0.25
| product email | 2 | 0.25
| Product: click to call | 2 | 0.25
| Product: company description | 2 | 0.25
| permission product: Ranked search word limit | 2 | 0.25
| permission product: deep link | 2 | 0.25
| Permission product: PDF | 2 | 0.25
| Mobile search logic order: local, comprehensive, paid adverts first, | 2 | 0.25
| payment processing | 2 | 0.25
| CRM data flow | 0 | 0
| add customer from web to CRM | 8 | 1
| Scheduled job generates Excel sheet | 8 | 1
| move the spreadsheets to landing pad via SFTP | 8 | 1
| Advert XML generated from the spread sheet and pumped to ActiveMQ | 16 | 2
| Search Integration with 3rd party | 0 | 0
| Zomato | 32 | 4
| booking | 32 | 4
| roundmenu | 0 | 0
| Reviews integration | 0 | 0
| Zomato | 24 | 3
| Tripadvissor | 24 | 3
| Roundmenu | 24 | 3
| Connect.ae | 24 | 3
| Map Integration | 0 | 0
| Zoom in and zoom out | 32 | 4
| driving directions | 24 | 3
| Search result page | 16 | 2
| API for mobile devices | 240 | 30
| Scheduler related | 48 | 6
| Sort and filter for search page | 16 | 2 |  |  |  | 200
Quality Assurance
| QA | 615.86 | 76.9825
| UAT | 8
| Total effort | 2022.06 | 251.7575
252.7575

## AndroidDev
| Connect.ae |  | 2017-09-05
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort | Original Effort | Adjusted Effort
| Initiation |  |  | Designer | 1 | 20 | 20
1 | Requirements gathering and documentation (SRS) | 64 | 8 | Sr Developer | 1 | 15 | 15 | 66 | 66
2 | Functional Specification | 48 | 6 | Jr Developer | 1 | 51 | 51
3 | Project Management | 52.8 | 6.6 | PM | 1 | 6.6 | 6.6
| Development |  | 0 | BA | 1 | 14 | 14
| Site Design |  | 0 | QA | 2 | 15.55 | 31.1
1 | Login page |  | 0 | Total |  |  | 137.7
2 | Design and development | 8 | 1
3 | Signup |  | 0
4 | Design and development(Api integration,Validation) | 16 | 2 | Total Delivery days | 86.55
5 | Register with social media(Face book and gmail) | 16 | 2 | Total Effort | 137.7 | (+1 Day deployment)
6 | Home page |  | 0
7 | Page design | 16 | 2
8 | Sliding menu(Hamburger Menu) | 16 | 2
| Frequent Searches | 4 | 0.5
| Feedback | 4 | 0.5
| Newsletter signup | 4 | 0.5
| language Selection | 4 | 0.5
| Search Bar (location enable option + Map view results option) | 4 | 0.5
| location enable option | 4 | 0.5
| Categories (list) | 4 | 0.5
| Search Result | 4 | 0.5
| List view | 8 | 1
| Frequent Searches | 4 | 0.5
9 | Listview | 6 | 0.75
10 | Feedback |  | 0
| Feed back page design ,Api integraqtion | 6 | 0.75
11 | Newsletter signup |  | 0
| Page design and Api integration | 6 | 0.75
| language Selection | 8 | 1
| Popup design , Api integration,Development and laguage integration | 16 | 2
| Detail Page |  | 0
| Tabbed (Business details, Coupons, Gallery, Reviews) | 16 | 2
| Business details | 4 | 0.5
| Coupons | 4 | 0.5
| Gallery | 4 | 0.5
| Reviews | 4 | 0.5
| Advertisement section | 4 | 0.5
| Business details Design and Api integration | 16 | 2
| Description | 4 | 0.5
| opening hours | 4 | 0.5
| deep links | 4 | 0.5
| video | 4 | 0.5
| social media links | 4 | 0.5
| Send email to company | 4 | 0.5
| Forward company details via SMS | 4 | 0.5
| Save company details as vCard | 4 | 0.5
| Click to call | 4 | 0.5
| Post in social media | 4 | 0.5
| Web Address, Price range, neighbourhoods, categories | 4 | 0.5
| List of features (Child safe , cuisine, attire etc) | 4 | 0.5
| Order online (link) | 4 | 0.5
| View Menu (link or image) | 4 | 0.5
| Years in business | 4 | 0.5
| Reviews count on top & aggregators count | 4 | 0.5
| Overall Rating | 4 | 0.5
| Map view results | 4 | 0.5
| Coupons | 4 | 0.5
| Page design and Api integration | 8 | 1
| Gallery |  | 0
| Page design and Api integration | 12 | 1.5
| Reviews | 8 | 1
| Reviews from Admin | 4 | 0.5
| Reviews from aggregators | 4 | 0.5
| Post Reviews | 4 | 0.5
| Advertisement section | 4 | 0.5
| Page design and Api integration | 4 | 0.5
| deep links | 4 | 0.5
| webview and Api | 4 | 0.5
| video |  | 0
| Page design,Api integration and video playe integration | 16 | 2
| Send email to company | 4 | 0.5
| Page design , Api integration and email integration | 16 | 2
| Forward company details via SMS |  | 0
| Page design , Api integration and sms gate way integration | 16 | 2
| Save company details as vCard |  | 0
| Page design and Development | 8 | 1
| Click to call |  | 0
| Api integration, Click to Call integration | 16 | 2
| Post in social media(Face book) | 4 | 0.5
| Development | 4 | 0.5
| List of features (Child safe , cuisine, attire etc) | 4 | 0.5
| Page design and Api integration | 4 | 0.5
| Reviews count on top & aggregators count | 4 | 0.5
| Api integration | 4 | 0.5
| Map view results |  | 0
| Show Directions | 6 | 0.75
| Route on map |  | 0
| Reviews from aggregators | 4 | 0.5
| Page design and Api integration | 4 | 0.5
| Post Reviews | 4 | 0.5
| Page design and Api integration | 4 | 0.5
| Show Directions |  | 0
| Create map view and drow the direction | 16 | 2
| Route on map |  | 0
| Create map view and drow the direction | 16 | 2
| Developer side testing and bug fixing | 32 | 4
| Page design ,lcon design in photoshop | 160 | 20
| QA | 240.8 | 30.1
| UAT | 8 | 1
| Total Effort | 1101.6 | 137.7
137.7

## UIUX
Sl. No | Site Design & Development | Design |  | HTML
|  | Hours | Man Days | Hours | Man Days
Home page (Inspiration yellowpages.com, connect.ae)
1 | Home Page Sections | 16 | 2 | 24 | 3
Time sensitive adverts & promotions
Featured company section
Mobile app Download section
Header
Logo, language Selection, login, Signup
Frequent Searches
Footer (links managed by admin)
Hamburger Menu
Newsletter signup
Dynamic image behind search bar
Social media links
Search Bar (location enable option + Map view results option)
2 | Company Profile page (Refer YP.com detailed pages) | 12 | 1.5 | 28 | 3.5
Dynamic sections based of membership type. Sections supressed for non privileged users
Deatailed profile pages similarr to YellowPages company directory
Page Details
Tabbed (Business details, Coupons, Gallery, Reviews)
Business Details
Description, logo, opening hours, deep links, video, social media links
Send email to company (mobile and web)
Forward company details via SMS (mobile)
Save company details as vCard (mobile)
Click to call (mobile)
Post in social media
Web Address, Price range, neighbourhoods, categories
List of features (Child safe , cuisine, attire etc)
Order online (link)
View Menu (link or image)
Suggest an edit
Years in business
Reviews count on top connect.ae & aggregators count
Overall Rating
Reviews (tabbed)
Reviews from connect.ae
Reviews from aggregators
Image gallery,
List Reviews
Post Reviews
Related searches
Advertisement section
3 | Generic page design (content managed by client)
| About Us | 4 | 0.5 | 4 | 0.5
| Contact | 4 | 0.5 | 4 | 0.5
| Advertise | 8 | 1 | 8 | 1
| Help | 4 | 0.5 | 4 | 0.5
| Privacy | 4 | 0.5 | 4 | 0.5
| Terms of use | 4 | 0.5 | 4 | 0.5
| Feedback | 4 | 0.5 | 4 | 0.5
| Site Map | 4 | 0.5 | 4 | 0.5
4 | Search Results page (Combination of Connect.ae & YP.com) | 32 | 4 | 32 | 4
Total results returned
List of 20 results page
map with number tags (resizable)
Sort by relevance, distance propolarity ( like connect.ae)
filter by ofder online, kid friendly etc (similar to YP.com)
About Search results
Sponsored results
Map fixed while scrolling
Sponsored advertisements on right panel
Homepage header fixed while scrolling
Suggested keywords
Reset search filters and sorting to defaults
5 | Registrations
| User registration | 8 | 1 | 8 | 1
| Advertisement registration | 8 | 1 | 8 | 1
6 | Admin Dashboard
| Dashboard | 8 | 1 | 8 | 1
| 1 Listing (table with filter) | 8 | 1 | 8 | 1
| 1 Add page (form) | 8 | 1 | 16 | 2
| Total Effort | 136 | 17 | 168 | 21

## Sheet1
ad management server
advertising campaigns
campaign subscription page
separate commercial packages for mobile and web
SME Popular articles editorials
hamburger navigation links managed by CMS
purchase geographies
in page navigation and in page communication (show green button)
Customer login to store address (work, Home, or other named locations)
enable click to call services (chat, text, phone, voip, web cam)
static content for URLS (see SEO)
assign metatags to category pages (using varnish?/)
integrating external map navigation
site catalyst