## Combined Estimate
Web Application
Resource | No | Man Days | Total Effort |  | Web Application
Designer | 1 | 8 | 8 |  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4
Sr Developer | 1 | 30 | 30 |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
Jr Developer | 2 | 39 | 78 |  | Month 1 Week 1: Proj. Initiation & Req. Gathering; Month 2 Week 5: Development; Month 3 Week 9: Development / Testing; Month 4 Week 13: Testing / UAT / Deployment
PM | 1 | 10.675 | 10.675 |  | Month 1 Week 1: Scope & Understanding; Month 2 Week 5: Daily Scrum Meeting; Month 3 Week 9: Daily Scrum Meeting; Month 4 Week 13: Deployment document
BA | 1 | 5 | 5 |  | Month 1 Week 1: Business Analysis; Month 2 Week 5: Daily Status updates; Month 3 Week 9: Daily Status updates; Month 4 Week 13: User Manual
Tech writer | 1 | 4 | 4 |  | Month 1 Week 1: Project Schedule (high level); Month 2 Week 5: Meeting Minutes; Month 3 Week 9: Meeting Minutes; Month 4 Week 13: Source Code
QA | 2 | 21.3562 | 42.7125 |  | Month 1 Week 1: Communication Plan; Month 2 Week 5: Test cases & Test Scenarios; Month 3 Week 9: Test cases & Test Scenarios; Month 4 Week 13: Consolidated defect reports
Total | 9 | 118.0312 | 178.3875 |  | Month 1 Week 1: Escalation Matrix; Month 2 Week 5: Sprint Backlog (development details); Month 3 Week 9: Sprint Backlog (development details); Month 4 Week 13: UAT Sign-off
- | - | - | - |  | Month 1 Week 1: Resources & Roles; Month 2 Week 5: UI /UX design updates; Month 3 Week 9: Defect reports; Month 4 Week 13: Updates SRS
Effort | 178.3875 | + 4 Day (Deployment) |  | 9.1194 | Month 1 Week 1: Product backlog; Month 2 Week 5: Content Matrix (Arabic / English); Month 3 Week 9: Test results; Month 4 Week 13: Go-Live approval
Delivery Time | 73.3563 | + 4 Day (Deployment) |  | 3.8678 | Month 1 Week 1: SRS; Month 3 Week 9: Test Summary; Month 4 Week 13: Sign-off document
[5 empty] | Design & Prototype | [7 empty] | Content Matrix (Arabic / English) |  |  |  | Project Closure
Mobile Application |  |  |  |  | Month 1 Week 1: RTM; Month 3 Week 9: UAT test Cases; Month 4 Week 13: Training Sessions
Resource | No | Man Days | Total Effort |  | Month 1 Week 1: Test plan; Month 3 Week 9: Integration Test cases
Designer | 1 | 4 | 4 |  | Month 1 Week 1: Change management
Android Developer | 1 | 28.5 | 28.5 |  | Month 1 Week 1: Updated Site Map
iOS Developer | 1 | 28.5 | 28.5 |  | Month 1 Week 1: User Journeys & task flows
QA | 2 | 11.4 | 22.8 |  | Month 1 Week 1: Mobile (Android + IOS)
UAT | 2 | 4 | 8 |  | Month 1 Week 1: Design & Prototype; Month 2 Week 5: Development; Month 3 Week 9: Development / Testing; Month 4 Week 13: Testing / UAT / Deployment
Total | 7 | 72.4 | 91.8 | bar: Month 1 Week 1 to Month 1 Week 4; Month 2 Week 7 to Month 4 Week 15
Effort | 91.8 | + 1 Day (Deployment)
Delivery Time | 47.9 | + 1 Day (Deployment)

## FCA
| FCA_UTC |  | 2020-06-04
Monday
| Module | Hours | Man Days | Resource | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 8 | 8
1 | Business analysis | 40 | 5 | Sr Developer | 1 | 30 | 30 | 107.75 | 118.675 | 107.75 | 108
2 | Project Management | 85.4 | 10.675 | Jr Developer | 2 | 39 | 78
3 | SRS,FS,User Manual | 32 | 4 | PM | 1 | 10.675 | 10.675
4 | Design and Prototype | 64 | 8 | BA | 1 | 5 | 5
| Development |  |  | Tech writer | 1 | 4 | 4
5 | Application basic setup | 8 | 1 | QA | 2 | 21.3562 | 42.7125
| Trader registration |  |  | Total | 9 | 118.0312 | 178.3875
| Register new user | 8 | 1 | - | - | - | -
| User Name, Trade Name, Official mail ID, mobile Number |  | 0 | Effort | 178.3875 | + 4 Day (Deployment)
| LDAP integration, Smart pass, UAE pass | 24 | 3 | Delivery Time | 73.3563 | + 4 Day (Deployment)
| Key cloak integration | 32 | 4
| OTP Authentication | 16 | 2
| Receive login credentials | 4 | 0.5
| Authentication / Authorization / Access control | 12 | 1.5
User/Trader
| Login/Logout | 4 | 0.5
| Dashboard(View application status in grid form,renewal date,etc) | 24 | 3
| New UTC application | 12 | 1.5
| Apply for UTC | 12 | 1.5
| Enter Ownership, sponsorship, partnership, licensing details, manager information, business categorization details(requires integration with local customs and governmental entities) | 12 | 1.5
| Save application as draft | 12 | 1.5
| Edit saved application if not send/submitted | 12 | 1.5
| Upload documents(doc,PDF,excel) | 12 | 1.5
| Submit for vertification | 6 | 0.75
| Renew Application | 8 | 1
| Renewal on expiry entering details(ownership,sponsorship,etc) |  | 0
| Modify application | 8 | 1
| After approval,requested modifications shall be made & submitted |  | 0
| Application on-hold(kept onhold by admin) | 8 | 1
| Edit application on hold |  | 0
| Risk module | 32 | 4
| business categorization (black, red, green, gray, yellow) based on activities | 16 | 2
| Payment | 16 | 2
Front end Admin
| Login/logout | 6 | 0.75
| Dashboard | 14 | 1.75
| Browse application | 12 | 1.5
| Advanced search, sorting and filtering | 32 | 4
| Individual application preview | 12 | 1.5
Backend Admin
| Login/logout | 4 | 0.5
| Dashboard | 10 | 1.25
| Browse application | 8 | 1
| Advanced search, sorting and filtering | 20 | 2.5
| Individual application preview | 6 | 0.75
| Approval workflow (Approve, reject, redirect for modification) | 16 | 2
| User role management | 6 | 0.75
| Control application | 6 | 0.75
| Generate reports(graphical & statistical) | 32 | 4
| Download as PDF, excel files | 12 | 1.5
Customizable features:
| Notifications | 12 | 1.5
| User’s requests | 12 | 1.5
| system theme | 16 | 2
| Language | 6 | 0.75
| Font size | 6 | 0.75
| Customize main page | 12 | 1.5
Home Page
| About | 6 | 0.75
| Rules & Regulations | 6 | 0.75
| Documents & Tutorials | 16 | 2
| Project Objectives | 6 | 0.75
| Trader login & Registration | 6 | 0.75
| Contact | 6 | 0.75
| Chat with us | 32 | 4
| Search site | 8 | 1
System Features
| Link between the companies’ based on the ownership, sponsorship, partnership, and leadership | 12 | 1.5
| Capability to suspend the company’s transactions | 8 | 1
| Multi-lingual (Arabic and English). | 24 | 3
| Connection with the FCA Database | 12 | 1.5
| Auditing and Logging | 8 | 1
| Exception Handling and error handling | 8 | 1
| REDIS integration | 12 | 1.5
| MinIO integration | 12 | 1.5
| Elastic Search integration | 12 | 1.5
| Reminder notifications (renew application, corrections, emails) | 8 | 1
Security
| Protection against injection (SQL, CRLF, LDAP) | 12 | 1.5
| URL encoding, Input validation | 6 | 0.75
| Cookie Encryption, Cookie replay attacks | 6 | 0.75
| Session hijacking prevention | 6 | 0.75
| Cross site scripting and session management | 6 | 0.75
Integration Requirements
| Integration with the local customs and governmental entities based on FCA request. | 32 | 4
| Payment Integration | 16 | 2
| future integrations with UAE pass and other systems |  | 0
| integration with the PMO Happiness Meter. | 6 | 0.75
| SMS, email | 12 | 1.5
Quality Assurance
| QA & Bug Fixing | 301.7 | 37.7125
| UAT | 40 | 5
| Deployment per instance | 32 | 4
| Total Effort |  | 182.1375
Assumptions
The effort may change after a detailed system study

## mobile
FCA_UTC |  |  |  | 2020-06-04
Monday
Module | Android |  | iOS |  | Resource | No | Man Days | Total Effort
| Hours | Man Days | Hours | Man Days | Designer | 1 | 4 | 4
Development |  |  |  |  | Android Developer | 1 | 28.5 | 28.5 | 28.5 | 57 | 28.5 | 57
[5 empty] | iOS Developer | 1 | 28.5 | 28.5
Trader registration |  |  |  |  | QA | 2 | 11.4 | 22.8
Splash Screen | 6 | 0.75 | 6 | 0.75 | UAT | 2 | 4 | 8
Register new user |  |  |  |  | Total | 7 | 72.4 | 91.8
User Name, Trade Name, Official mail ID, mobile Number | 8 | 1 | 8 | 1
OTP Authentication | 6 | 0.75 | 6 | 0.75 | Effort | 91.8 | + 1 Day (Deployment)
Receive login credentials | 6 | 0.75 | 6 | 0.75 | Delivery Time | 47.9 | + 1 Day (Deployment)
|  | 0 | 0 | 0
User/Trader
Login/Logout | 8 | 1 | 8 | 1
Dashboard(View application status in grid form,renewal date,etc) | 8 | 1 | 8 | 1
New UTC application |  | 0 |  | 0
Apply for UTC | 8 | 1 | 8 | 1
Enter Ownership, sponsorship, partnership, licensing details, manager information, business categorization details(requires integration with local customs and governmental entities) | 8 | 1 | 8 | 1
Save application as draft | 8 | 1 | 8 | 1
Edit saved application if not send/submitted | 6 | 0.75 | 6 | 0.75
Upload documents(doc,PDF,excel) | 8 | 1 | 8 | 1
Submit for vertification | 6 | 0.75 | 6 | 0.75
Renew Application |  | 0 |  | 0
Renewal on expiry entering details(ownership,sponsorship,etc) | 8 | 1 | 8 | 1
Modify application |  | 0 |  | 0
After approval,requested modifications shall be made & submitted | 8 | 1 | 8 | 1
Application on-hold(kept onhold by admin) |  | 0 |  | 0
Edit application on hold | 6 | 0.75 | 6 | 0.75
Payment | 24 | 3 | 24 | 3
|  | 0 | 0 | 0
Customizable features:
Notifications | 8 | 1 | 8 | 1
Device shake features | 24 | 3 | 24 | 3
User’s requests | 8 | 1 | 8 | 1
system theme | 16 | 2 | 16 | 2
Language | 8 | 1 | 8 | 1
Font size | 8 | 1 | 8 | 1
Customize main page | 8 | 1 | 8 | 1
Read speaker | 16 | 2 | 16 | 2
|  | 0 | 0 | 0
Quality Assurance
QA & Bug Fixing | 91.2 | 11.4 | 91.2 | 11.4
UAT |  | 0 | 0 | 0
Deployment per instance |  | 0 | 0 | 0
Total Effort | 319.2 | 39.9 | 319.2 | 39.9
Assumptions 1.The estimation may be vary with variation in new features or design. 2.The estimation is done only for protrait mode.