## Sheet1
Activity Description | Hours | Days
Initiation
Business Analysss | 32 | 4 | Resource | # | Days | Total
Documentation (SRS, Weekly Reports, SFS, MOM etc) | 24 | 3 | BA | 1 | 7 | 7
Project Management | 53.6 | 6.7 | PM | 1 | 6.7 | 6.7
UI / UX | 40 | 5 | UI/UX | 1 | 5 | 5
Development |  |  | Developer | 2 | 33.5 | 67
System Administration |  |  | QA | 2 | 19.64 | 39.28
Dashboard administration | 16 | 2 | Total |  | 65.14 | 124.98
Users / User roles (Reporter, EHS Units, EHS Committee, Health & safety specialist, department heads etc) | 16 | 2
Practice Area Management (Campus, Project, Location, Assessment practitioner, Assessment date, Ref #) | 8 | 1 |  | Man Days | Man Months
Reccurence Schedule Management | 6 | 0.75 | Total Effort | 124.98 | 6.249
Communication Management | 6 | 0.75 | Delivery | 65.14 | 3.257
Risk Category / Risk Frequency / Risk Severity | 12 | 1.5
Hazard Categories | 4 | 0.5
Campus, Location, Department Management | 12 | 1.5
Audience Types | 4 | 0.5
Active directory management | 6 | 0.75
Activity Management |  | 0
Hazard Identification | 16 | 2
Work Area |  | 0
Hazard description |  | 0
Effected Audience |  | 0
Hazard ill effects |  | 0
Risk Evaluation | 16 | 2
Existing risk control |  | 0
incident severity |  | 0
Frequency for re-occurrence |  | 0
Risk |  | 0
Risk Control | 16 | 2
Additional risk control measures |  | 0
HCT / OSH procedures |  | 0
Legal requirment register |  | 0
MOC Reference |  | 0
Risk Evaluation | 16 | 2
Severity of incident |  | 0
Likelyhood of re-occurrence |  | 0
Residual risk |  | 0
Follow up department / committee/ person |  | 0
Follow up Schedule |  | 0
Remarks |  | 0
Application Users |  | 0
Incident management forms |  | 0
Annual Drill Plan. | 20 | 2.5
Emergency Drill Report. | 20 | 2.5
Classrooms Evacuation Card | 20 | 2.5
Assembly point Card | 20 | 2.5
Fire Warden Card | 20 | 2.5
HCT Risk Assessment Form. | 20 | 2.5
Risk Register Form. | 20 | 2.5
Opportunity Register Form. | 20 | 2.5
Hazard Walkthrough Form. | 20 | 2.5
Risk Assessment Specific Form – for specific uses (e.g. HCT events, contractors unaware or do not have a risk assessment for a job requiring a work permit etc.) | 20 | 2.5
Spill Drill report | 20 | 2.5
User Dahboards | 32 | 4
In app Communication via emails | 16 | 2
Workflow (Incident reporting forms, Manual & Auto assign users and groups (escalation when needed) based on category, severity etc., Follow up procedure - issue mitigation and results, scheduled rechecks based on re-occurrence frequency) | 64 | 8
System Funtions
Authentication and Authorization | 8 | 1
Auditing and logging | 8 | 1
exception handling | 8 | 1
Messaging (emails) | 6 | 0.75
Scheduled jobs | 8 | 1
Active directory integration | 4 | 0.5
Login / forgot password / remember password / verfification | 8 | 1
QA
Test cases, RTM, Test scenarios, Integration tests, Defect reports | 274.24 | 34.28
UAT | 40 | 5
Deployment | 12 | 1.5
Total | 1011.84 | 126.48