## LMS-Web
| LMS Web | April 24 2017
Monday
| Module | Man Days | LMS Web
| Initiation |  |  | No | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) | 0 | Designer | 1 | 15 | 15
2 | Functional Specification | 0 | Sr Developer | 1 | 15 | 15 | 92 | 93
3 | Project Management | 0 | Jr Developer | 2 | 39 | 78
4 | Finalising and purchase of HTML Theme & Images (~20 - ~30 Screens) | 0 | PM | 1 | 0 | 0
5 | Complete running prototype | 15 | QA | 2 | 20 | 40
| Development |  | Total |  |  | 148
| Registration | 2
6 | Student profile |  | Total Delivery days | 74
7 | instructor Profile |  | Total Effort | 148
8 | Admin profile
| Student Workflow | 10 | Tablet Development
9 | Student Quick Guide (~6 screens) |  |  | No | Man Days | Total Effort
10 | Dashboard (My courses, My grades, Favourite instructors, Messages, Preferences, edit profile, Calendar and course schedule) |  | Designer | 1 | 14 | 14 |  |  | 0
11 | Class Selection (Request for class) |  | Sr Developer | 1 | 8 | 8 | 25.125 | 25
12 | instructor Selection (request for instructor) |  | Jr Developer | 1 | 17 | 17
13 | instructor ratings (Comments and stars) |  | QA | 2 | 5.025 | 10.05
14 | Submit request |  | Total |  |  | 49.05
15 | Request Timeout
16 | Request escalation (to admin and then superadmin) |  | Total Delivery days | 36.025 | X2 | (IOS+Android)
17 | Make payment online via payment processor |  | Total Effort | 49.05
18 | Create calender entry and reminders
19 | Send specific information to instructor |  | Phone Development
20 | Attend class online (Record class) |  |  | No | Man Days | Total Effort
21 | Request clarification or post questions to instructor |  | Designer | 1 | 14 | 14
22 | Rate instructor & add instructor as favourite |  | Sr Developer | 1 | 15 | 15 | 53.75 | 54
23 | Access assignment ( Attachments) |  | Jr Developer | 1 | 39 | 39
24 | Submit assignment (upload assignments, take quizz etc) |  | QA | 2 | 10.75 | 21.5
25 | Assignment history withy grades |  | Total |  |  | 89.5
26 | Receive Course certificates
| Instructor Workflow | 22 | Total Delivery days | 63.75 | X2 | (IOS+Android)
27 | instructors Quick Guide (~6 screens) |  | Total Effort | 89.5
28 | Dashboard (My Students, Messages, Preferences, edit profile, Calendar and course schedule, Rating)
29 | CV builder |  | Cumulative Total
30 | Billing information |  | Delivery Days | 80
31 | References |  | Effort | 425.1
32 | Specialization
33 | Set availability and calendar
34 | Upload Course content
35 | Links to external sites for reference material
36 | Accept Student request
37 | Cancel Request
38 | Update calendar & create reminders
39 | Conduct classes (one on One)
40 | Answer student questions or doubts
41 | Upload assignments or create quizzes
42 | Review assigments and assign grade
43 | Receive payment
| Admin (principal) Workflow | 8
44 | Admin Quickguide (~6 screens)
45 | Upload CV
46 | Add refernces
47 | Add billing information
48 | Access and manage student, instructor calenders.
49 | Reassign instructors
50 | Reschedule instructor and student classes
51 | Approve Review
52 | resolve instructor student issues
| Super Admin | 8
53 | Manage students
54 | Manage instructors
55 | Manage Admins (principals)
56 | Manage Courses
57 | re-associate instructors to courses
58 | Dashboard (Active Students, Active instructors, Active courses, edit profile, Messages-pending reviews, Latest ratings)
59 | Post site wide messages or to individuals
60 | Blacklist instructors
61 | Quizz management*
| Parent Workflow | 6
62 | register Student
63 | Review grades
64 | View student course schedule
65 | View Messages from Admin, superadmin, instructor
66 | View student calendar
| System Features | 12
67 | Authentication and authorization
68 | Logging and auditing with notifications
69 | Payment processing
70 | File management
71 | Roles and permissions
72 | Password salting
73 | Email authentication and management
74 | SMS authentication (mobile devices)
75 | Password policy
76 | Cron Jobs for scheduling
77 | Export or email reports
| Reports and Analytics | 10
78 | Student demographics
79 | Inactive users
80 | Student Activity Summary (Most Active Students)
81 | Student grades Compared to Course Average (Compared to Course Average)
82 | Revenue Generation
83 | Demographic report
84 | Revenue by student
85 | Revenue by instructors
86 | Login statistics (by students and instructors)
87 | Available courses and student enrollment
88 | Available courses and staffing
89 | File utilization by student and instructor
90 | Activity stats summary (logins, total course time spent)
91 | Past due assignments
92 | Course utilization report
93 | Incomplete student teacher sessions
94 | Student-teacher reassignments
95 | Teacher review
96 | Mobile API Development | 14
97 | Create Deployable installshield solution
Testing & Deployment
| Testing | 40
UAT
Deployment
| Total Effort | 147
| Estimate Assumptions: | 1. Recording will be a column for the report (student , Teacher & Admin), not included in filter. 2. Tutorial - static content 3. Request (teacher) workflow escalation period is hardcoded in DB 4. " Wait for the review different admin to receive the fees" in the admin worflow - Need clarification 5. Technology not considered 6. customer will procure templates, SSL certificates & Payement processor 7. UI development is 2-4 hrs per screen 8. Effort for deployment not considered 9. Reporting and analytics for mobile devices will be imported from the web 10. Both mobile and tablet have similar design 11. Estimated with default Android and IOS design, Custom design will take more effort
| Out of Scope | 1. Adobe connect integration 2. Payment processing for Teacher 3. Quiz assignmets for students by teacher 4. Documentation & Project planning

## LMS-Tablet
| LMS - Tablet | April 24 2017
Monday
Sl. No. | Module | Man Days | Tablet Development
| Initiation |  |  | No | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) |  | Designer | 1 | 14 | 14
2 | Functional Specification |  | Sr Developer | 1 | 8 | 8 | 25.125 | 25
3 | Project Management |  | Jr Developer | 1 | 17 | 17
4 | Complete running prototype | 14 | QA | 2 | 5.025 | 10.05
| Development |  | Total |  |  | 49.05
Registration
5 | Student profile | 0.5 | Total Delivery days | 36.025
6 | instructor Profile | 0.5 | Total Effort | 49.05
7 | Admin profile | 0.5
Student Workflow
8 | Student Quick Guide (~6 screens) | 1
9 | Dashboard (My courses, My grades, Favourite instructors, Messages, Preferences, edit profile, Calendar and course schedule) | 0.5
10 | Class Selection (Request for class) | 0.5
11 | instructor Selection (request for instructor) | 0.5
12 | instructor ratings (Comments and stars) | 0.25
13 | Submit request | 0.125
14 | Request Timeout | 0.5
15 | Request escalation (to admin and then superadmin)
16 | Make payment online via payment processor | 1
17 | Create calender entry and reminders | 1
18 | Send specific information to instructor | 0.5
19 | Attend class online (Record class)
20 | Request clarification or post questions to instructor | 0.25
21 | Rate instructor & add instructor as favourite | 0.25
22 | Access assignment ( Qizz, Attachments) | 0.5
23 | Submit assignment (upload assignments, take quizz etc) | 0.5
24 | Assignment history withy grades | 0.75
25 | Receive Course certificates | 1
Instructor Workflow
27 | instructors Quick Guide (~6 screens) | 1
28 | Dashboard (My Students, Messages, Preferences, edit profile, Calendar and course schedule, Rating) | 0.5
29 | CV builder | 1
30 | Billing information | 1
31 | References
32 | Specialization
33 | Set availability and calendar | 0.5
34 | Upload Course content | 0.5
35 | Links to external sites for reference material | 0.25
36 | Upload Course Video | 0.5
37 | Accept Student request | 0.25
38 | Cancel Request | 0.125
39 | Update calendar & create reminders | 0.5
40 | Conduct classes (one on One)
41 | Answer student questions or doubts | 0.5
42 | Upload assignments or create quizzes | 0.5
43 | Review assigments and assign grade | 0.75
44 | Receive payment
Admin (principal) Workflow
45 | Admin Quickguide (~6 screens) | 1
46 | Upload CV | 0.375
47 | Add refernces
48 | Add billing information
49 | Access and manage student, instructor calenders. | 1
50 | Reassign instructors | 0.25
51 | Reschedule instructor and student classes | 0.25
52 | Approve Review | 0.125
53 | resolve instructor student issues | 1
Parent Workflow
54 | register Student | 0.5
55 | Review grades | 0.5
56 | View student course schedule | 0.5
57 | View Messages from Admin, superadmin, instructor | 0.5
58 | View student calendar | 0.625
Reports and Analytics
59 | Student demographics
60 | Inactive users
61 | Student Activity Summary (Most Active Students)
62 | Student grades Compared to Course Average (Compared to Course Average)
63 | Revenue Generation
64 | Demographic report
65 | Revenue by student
66 | Revenue by instructors
67 | Login statistics (by students and instructors)
68 | Available courses and student enrollment
69 | Available courses and staffing
70 | File utilization by student and instructor
71 | Activity stats summary (logins, total course time spent)
72 | Past due assignments
73 | Course utilization report
74 | Incomplete student teacher sessions
75 | Student-teacher reassignments
76 | Teacher review
77 | Create Deployable installshield solution
Testing & Deployment
78 | Testing | 10.05
79 | UAT
80 | Deployment
| Total Effort | 49.175
Assumptions
Both mobile and tablet are in same design
Reports and Analytics will be taken care in web part
Live streaming is not considered
Estimated with android default design, Custom design will take more effort

## LMS-Phone
| LMS - Phone | April 24 2017
Monday
Sl. No. | Module | Man Days | LMS-Phone
| Initiation |  |  | No | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) |  | Designer | 1 | 14 | 14
2 | Functional Specification |  | Sr Developer | 1 | 15 | 15 | 53.75 | 54
3 | Project Management |  | Jr Developer | 1 | 39 | 39
4 | Complete running prototype | 14 | QA | 2 | 10.75 | 21.5
| Development |  | Total |  |  | 89.5
Registration
5 | Student profile | 1 | Total Delivery days | 63.75
6 | instructor Profile | 1 | Total Effort | 89.5
7 | Admin profile | 1
Student Workflow
8 | Student Quick Guide (~6 screens) | 1.5
9 | Dashboard (My courses, My grades, Favourite instructors, Messages, Preferences, edit profile, Calendar and course schedule) | 1
10 | Class Selection (Request for class) | 0.75
11 | instructor Selection (request for instructor) | 1
12 | instructor ratings (Comments and stars) | 0.5
13 | Submit request | 0.25
14 | Request Timeout | 0.5
15 | Request escalation (to admin and then superadmin)
16 | Make payment online via payment processor | 4
17 | Create calender entry and reminders | 12
18 | Send specific information to instructor | 0.75
19 | Attend class online (Record class)
20 | Request clarification or post questions to instructor | 0.75
21 | Rate instructor & add instructor as favourite | 0.5
22 | Access assignment ( Qizz, Attachments) | 1
23 | Submit assignment (upload assignments, take quizz etc) | 1
24 | Assignment history withy grades | 0.75
25 | Receive Course certificates | 1
Instructor Workflow
26 | instructors Quick Guide (~6 screens) | 1
27 | Dashboard (My Students, Messages, Preferences, edit profile, Calendar and course schedule, Rating) | 0.5
28 | CV builder | 2
29 | Billing information | 1
30 | References
31 | Specialization
32 | Set availability and calendar | 1
33 | Upload Course content | 1
34 | Links to external sites for reference material | 0.5
35 | Upload Course Video | 1
36 | Accept Student request | 0.5
37 | Cancel Request | 1
38 | Update calendar & create reminders | 1
39 | Conduct classes (one on One)
40 | Answer student questions or doubts | 1
41 | Upload assignments or create quizzes | 1
42 | Review assigments and assign grade | 1
43 | Receive payment | need clarity
Admin (principal) Workflow
44 | Admin Quickguide (~6 screens) | 1
45 | Upload CV | 1
46 | Add refernces
47 | Add billing information
48 | Access and manage student, instructor calenders. | 2
49 | Reassign instructors | 0.5
50 | Reschedule instructor and student classes | 0.5
51 | Approve Review | 0.25
52 | resolve instructor student issues | 0.5
Parent Workflow
53 | register paent | 1
54 | Review grades | 0.75
55 | View student course schedule | 0.75
56 | View Messages from Admin, superadmin, instructor | 0.75
57 | View student calendar | 1
Reports and Analytics
58 | Student demographics
59 | Inactive users
60 | Student Activity Summary (Most Active Students)
61 | Student grades Compared to Course Average (Compared to Course Average)
62 | Revenue Generation
63 | Demographic report
64 | Revenue by student
65 | Revenue by instructors
66 | Login statistics (by students and instructors)
67 | Available courses and student enrollment
68 | Available courses and staffing
69 | File utilization by student and instructor
70 | Activity stats summary (logins, total course time spent)
71 | Past due assignments
72 | Course utilization report
73 | Incomplete student teacher sessions
74 | Student-teacher reassignments
75 | Teacher review
76 | Create Deployable installshield solution
| Testing & Deployment |  |  | S
| Testing | 21.5
UAT
Deployment
| Total Effort | 89.25
Assumptions
Both mobile and tablet are in same design
Reports and Analytics will be taken care in web part
Live streaming is not considered
Estimated with android default design, Custom design will take more effort