## Web
|  | WriTalk - WEB | 19/4/2020
Monday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 0
1 | Business analysis |  | 0 | Sr Developer | 1 | 0 |  | 3 | 0 | 0
2 | Project Management |  | 0 | Jr Developer | 1 | 0
3 | SRS,FS,User Manual |  | 0 | PM | 1 | 0
4 | UI / UX (Web & Moile IOS) |  | 0 | BA | 1 | 0
| Development |  |  | Tech writer | 1 | 0
5 | Application basic setup |  | 0 | QA | 1 | 0
| Website |  |  | Total | 7 | 0
Home page
| About Us |  | 0 | Effort | 0 | + 1 Day (Deployment)
| Privacy policy |  | 0 | Delivery Time | 0 | + 1 Day (Deployment)
| Contact us |  | 0
Why Writalk
How dos it work?
Download App
| Testimonials |  | 0
Terms & Conditions
| Social media |  | 0
| Login (including social media) |  | 0
Registration (students) - Generate ID
| Registration (Tutors) - Generate ID |  | 0
Email verification
OTP authentication
| Remember password |  | 0
| Forgot password |  | 0
| Jobs |  | 0
| Student profile (age, location, about, Needs, image, ID verification) |  | 0
Tutor profile (about, specialities, qualification, experince, certifications, video intro, image, location, ID proof )
Admin
Metrics
Subscribers
Tutors
Users (paid vs unpaid suscribers)
Sessions
Students
Churn Rate
By Hour, day, month, year, Country (Applicable to all)
Revenue by time(daily,monthly, yearly, quarter), tutor, country
Verify tutor
Create skills / categories / specialization (for tutors)
Set tutor schedule cancellation policy (flexible, early late)
Set student cancellation policies
Ban student / tutor
Session history (tutor name, date, duration, student rates erc)
login stats (by users, subscribers, teachers)
Manage Subscriptions
Create limited time offers and coupons 1. Tutors 2. Students
Disburse coupons
Super admin
Analytics
Student demographics ( by age, country, speciality required)
Tutor Demographics (by age, country, speciality)
Inactive users
Revenue by student demographics
Revenue generated by teacher demographics
System errors (down time, compliants, vedio quality ratings etc)
cancelled sessions ( by student / tutor)
Incomplete student teacher sessions
Revenue ( daily, monthly, quarterly etc)
Past due payments
Customer Support
User Search (by ID, Name, Email)
Search results
Block / unblock user
Marketing (Optional - Costing separate depending on implementation)
One signal API Integtration (Create Notification, create segments, Send notifications, Notification history)
Send push messages
Send in-app messages
Send email messages
One signal analytics API integration
Influencers page
Discount offers
Free trial subscription
Free sessions
Template creation and management
Chat integration for web site (optional)
Tutor
| Tutors quick guide (~6 screens) | 12
| Dashboard (Students, messages, preferences, edit profile, calendar, schedule, profile page, insights - current balance, rating, total payments, sessions completed, # of cancellations) | 32
Guaranteed hours (set availability, cancel schedule)
me
Dashboard style Live stream (with up to 3 students) / chat window with reactions / save notes / corrections / save video / Save chat transcripts / upload assignments / list of upcoming streams
Billing information
Accept / reject student request (guranteed hours)
Cancel Scheduled sessions
Update calendar / reschedule / create reminders
Report Student
Trial user / subscriber entitlements
Rate students
Refer a friend( Tutor / Sudent)
Avail Offers
Student
Student Quick guide (~6 screens)
Dashboard ( schedule, favourite tutors, messages, preferences, edit profile, calendar, billing, payment history, upcoming payments, profile page)
Browse tutors (filter by country , rate, gender, speciality) : shows tutor live status
View tutor profile
View tutor schedule
Schedule and book Session
Buy Subscription
Rate tutors & add favourites
Start scheduled live stream ( whoever starts the stream waits for the other), choose video quality, switch to audio using Twilio
Report teacher
Refer a friend
Avail Offers
Documentation
Admin guide
Tutor guide
Student guide
System
List tutors based on algorithm ex. 1. Prioritize Guaranteed hours 2. Rated tutors 3. Country
Disburse payments for tutors
Manage reminders
Reminder notifications - Email & SMS
Downgrade the video quality system wide
Switch to audio system wide
Authentication, Authorization, Entitlements
Auditing & logging
Exception logging & error handling
Flag cancellations and apply policies
Guaranteed hours workflow management
Subscription management
Cupons and offer management
Security
| Protection against injection attacks (SQL, CRLF) | 12 | 1.5
| URL encoding, Input validation | 6
| Cookie Encryption, Cookie replay attacks | 6 | 0.75
| Session hijacking prevention | 6 | 0.75
| Cross site scripting and session management | 6
Integration
Payment Integration
REDIS integraion
Minio Integration
Keycloak integration
ELK stack integration
TWILIO integration
OneSignal (optional)
Quality Assurance
| QA & Bug Fixing |  | 0
| UAT |  | 0
| Deployment per instance |  | 0
| Total Effort |  | 3
Assumptions
The effort may change after a detailed system study

## mobile
WriTalk - Mobile (IOS) |  | 19/4/2020
Sunday
Module | iOS |  |  | No | Man Days | Total Effort
| Hours | Man Days | Mobile Design (Different from UI/UX) | 1 | 4 | 4
Development |  |  | Sr Developer | 1 | 20 | 20 | 29 | 40 | 44.75 | 40
Application basic setup | 6 | 0.75 | Jr Developer | 1 | 20 | 20
Student |  |  | qa | 1 | 25.1375 | 25.1375
Registraion | 16 | 2 | API Development | 1 | 20 | 20
Verify by email | 8 | 1 | Total |  |  | 89.1375
verify by OTP | 6 | 0.75 | Effort | 89.1375 | + 1 Day (Deployment)
Login (stay signed in) | 6 | 0.75 | Delivery Time | 49.1375 | + 1 Day (Deployment)
Allow access location, Allow notification | 8 | 1
Legal agreement | 3 | 0.375
Generate ID | 3 | 0.375
Create Profile | 8 | 1
Dashboard (Learn - my schedule , Me, Wallet - payment options (3), Buy subscription) | 24 | 3
Browse Tutors (6 profiles per page) - With live status | 16 | 2
Search / filter (multiple) tutors | 8 | 1
View Tutor profile (picture, video, personal details, certifications etc) | 6 | 0.75
schedule session with tutor | 8 | 1
Manage Profile (view / edit) | 6 | 0.75
Manage Wallet (payment options) | 8 | 1
Buy subscriptions | 16 | 2
Refer a friend | 2 | 0.25
Settings (reset password, currency) | 6 | 0.75
Get help (Q&A) | 6 | 0.75
Contact US (with info on app version, device info, OS version etc) | 6 | 0.75
Live stream with chat and reactions using Twilio | 24 | 3
Rate session | 6 | 0.75
Rate tutor | 6 | 0.75
Join guaranteed session | 8 | 1
Avail coupons, limited time offers | 6 | 0.75
Messages | 6 | 0.75
Teacher
Registraion | 8 | 1
Verify by email | 6 | 0.75
verify by OTP | 6 | 0.75
Login (stay signed in) | 6 | 0.75
Allow access location, Allow notification | 6 | 0.75
Legal agreement | 3 | 0.375
Generate ID | 3 | 0.375
Create Profile (video, image, certifications etc) | 12 | 1.5
Dashboard (Schedule , Me, balance, wallet- bank info) | 18 | 2.25
Refer a friend | 2 | 0.25
Rate Student | 6 | 0.75
Schedule guaranteed sessions | 12 | 1.5
Cancel sessions (csheduled and guranteed) | 6 | 0.75
Messages (from admin, students, Warnings, Desciplinary etc) | 6 | 0.75
Avail offers | 2 | 0.25
Live stream with chat and reactions using Twilio | 24 | 3
API development | 161.1 | 20.1375
QA & UAT
QA | 161.1 | 20.1375 | 161.1
UAT | 40 | 5
Deployments | 8 | 1
Total Effort | 596.2 | 74.525
ASSUMPTION 1. The estimation may vary with change in functionalities. 2.The estimation is done only for portrait mode.