## Web
|  | WriTalk - WEB | 19/4/2020
Monday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 15 | 15
1 | Business analysis | 32 | 4 | Sr Developer | 1 | 33 | 33 | 125.25 | 140.125 | 127.25 | 128
2 | Project Management | 97 | 12.125 | Jr Developer | 2 | 47.5 | 95
3 | SRS,FS,User Manual | 32 | 4 | PM | 1 | 12.125 | 12.125
4 | UI / UX (Web & Moile IOS) | 120 | 15 | BA | 1 | 4 | 4
| Documentation |  |  | Tech writer | 1 | 8.5 | 8.5
| Admin guide | 12 | 1.5 | QA | 2 | 26.2188 | 52.4375
| Tutor guide | 12 | 1.5 | Total | 9 | 146.3438 | 220.0625
| Student guide | 12 | 1.5 |  | Man Days |  |  |  |  | Man Months
| Development |  |  | Effort | 220.0625 | + 2 Day (Deployment) |  |  |  | 11.0031
5 | Application basic setup | 8 | 1 | Delivery Time | 92.7188 | + 2 Day (Deployment) |  |  |  | 4.6359
Website
| Home page | 16 | 8
| About Us | 4 | 0.5
| Privacy policy | 4 | 0.5
| Contact us | 4 | 0.5
| Why Writalk | 4 | 0.5
| How dos it work? | 8 | 1
| Download App | 2 | 0.25
| Testimonials | 4 | 0.5
| Terms & Conditions | 4 | 0.5
| Social media | 4 | 0.5
| Login (including social media) | 6 | 0.75
| Registration (students) - Generate ID | 6 | 0.75
| Registration (Tutors) - Generate ID | 6 | 0.75
| Email verification | 2 | 0.25
| OTP authentication | 2 | 0.25
| Remember password | 2 | 0.25
| Forgot password | 2 | 0.25
| Jobs (simple listing) | 4 | 0.5
| Student profile (age, location, about, Needs, image, ID verification) | 12 | 1.5
| Tutor profile (about, specialities, qualification, experince, certifications, video intro, image, location, ID proof ) | 24 | 3
Admin
Metrics (Kibana)
| Subscribers | 8 | 1
| Tutors | 8 | 1
| Users (paid vs unpaid suscribers) | 4 | 0.5
| Sessions | 4 | 0.5
| Students | 4 | 0.5
| Churn Rate | 8 | 1
| By Hour, day, month, year, Country (Applicable to all) |  | 0
| Verify tutor | 4 | 0.5
| Create skills / categories / specialization (for tutors) | 4 | 0.5
| Set tutor schedule cancellation policy (flexible, early late) | 6 | 0.75
| Set student cancellation policies | 6 | 0.75
| Ban student / tutor | 4 | 0.5
| Session history (tutor name, date, duration, student rates erc) | 8 | 1
| login stats (by users, subscribers, teachers) | 6 | 0.75
| Manage Subscriptions | 8 | 1
| Create limited time offers and coupons 1. Tutors 2. Students | 16 | 2
| Disburse coupons | 8 | 1
Super admin
Analytics (Kibana)
| Student demographics ( by age, country, speciality required) | 6 | 0.75
| Tutor Demographics (by age, country, speciality) | 6 | 0.75
| Inactive users | 6 | 0.75
| Revenue by student demographics | 6 | 0.75
| Revenue generated by teacher demographics | 6 | 0.75
| System errors (down time, compliants, vedio quality ratings etc) | 6 | 0.75
| cancelled sessions ( by student / tutor) | 6 | 0.75
| Incomplete student teacher sessions | 6 | 0.75
| Revenue ( daily, monthly, quarterly etc) | 6 | 0.75
| Past due payments | 6 | 0.75
| Customer Support |  |  | 40 - 120 hrs 40 - basic integration 120 - integrating within the application using SDK and API
| User Search (by ID, Name, Email) | 12 | 1.5
| Search results | 16 | 2
| Block / unblock user | 4 | 0.5
Marketing (Optional - Costing separate depending on implementation)
One signal API Integtration (Create Notification, create segments, Send notifications, Notification history)
Send push messages
Send in-app messages
Send email messages
One signal analytics API integration
Influencers page
Discount offers
Free trial subscription
Free sessions
Template creation and management
Chat integration for web site (optional)
Tutor
| Tutors quick guide (~6 screens) | 16 | 2
| Dashboard (Students, messages, preferences, edit profile, calendar, schedule, profile page, insights - current balance, rating, total payments, sessions completed, # of cancellations) | 32 | 4
| Guaranteed hours (set availability, cancel schedule) | 16 | 2
| me | 8 | 1
| Dashboard style Live stream (with up to 3 students) / chat window with reactions / save notes / corrections / save video / Save chat transcripts / upload assignments / list of upcoming streams, Select streaming bandwidth when bandwith is low. Switch to audio in worst case | 64 | 8
| Billing information | 8 | 1
| Accept / reject student request (guranteed hours) | 6 | 0.75
| Cancel Scheduled sessions | 6 | 0.75
| Update calendar / reschedule / create reminders | 16 | 2
| Report Student | 4 | 0.5
| Trial user / subscriber entitlements | 16 | 2
| Rate students | 4 | 0.5
| Refer a friend( Tutor / Sudent) | 4 | 0.5
| Avail Offers | 6 | 0.75
Student
| Student Quick guide (~6 screens) | 16 | 2
| Dashboard ( schedule, favourite tutors, messages, preferences, edit profile, calendar, billing, payment history, upcoming payments, profile page) | 32 | 4
| Browse tutors (filter by country , rate, gender, speciality) : shows tutor live status | 16 | 2
| View tutor profile | 16 | 2
| View tutor schedule | 16 | 2
| Schedule and book Session | 6 | 0.75
| Buy Subscription | 6 | 0.75
| Rate tutors & add favourites | 6 | 0.75
| Start scheduled live stream ( whoever starts the stream waits for the other), choose video quality, switch to audio when bandwidth is low) - using Twilio | 40 | 5
| Report teacher | 4 | 0.5
| Refer a friend | 4 | 0.5
| Avail Offers | 4 | 0.5
System
| List tutors based on algorithm ex. 1. Prioritize Guaranteed hours 2. Rated tutors 3. Country | 12 | 1.5
| Disburse payments for tutors | 6 | 0.75
| Manage reminders | 8 | 1
| Reminder notifications - Email & SMS | 8 | 1
| Downgrade the video quality system wide | 8 | 1
| Switch to audio system wide | 8 | 1
| Authentication, Authorization, Entitlements | 16 | 2
| Auditing & logging | 6 | 0.75
| Exception logging & error handling | 6 | 0.75
| Flag cancellations and apply policies | 12 | 1.5
| Guaranteed hours workflow management | 14 | 1.75
| Subscription management | 14 | 1.75
| Cupons and offer management | 14 | 1.75
| Autorenewals | 8 | 1
Security
| Protection against injection attacks (SQL, CRLF) | 12 | 1.5
| URL encoding, Input validation | 6 | 0.75
| Cookie Encryption, Cookie replay attacks | 6 | 0.75
| Session hijacking prevention | 6 | 0.75
| Cross site scripting and session management | 6 | 0.75
Integration
| Payment Integration | 16 | 2
| REDIS integraion | 16 | 2
| Minio Integration | 16 | 2
| Keycloak integration | 16 | 2
| ELK stack integration | 16 | 2
| TWILIO integration | 16 | 2
| OneSignal (optional) |  |  | 16 hours
Quality Assurance
| QA & Bug Fixing | 339.5 | 42.4375
| UAT | 80 | 10
| Deployment per instance | 16 | 2
| Total Effort |  | 221.3125
Assumptions
The effort may change after a detailed system study

## mobile
WriTalk - Mobile (IOS) |  |  |  | 19/4/2020
Sunday
Module | iOS |  |  | No | Man Days | Total Effort
| Hours | Man Days | Mobile Design (Different from UI/UX) | 1 | 4 | 4
Development |  |  | Sr Developer | 1 | 32 | 32 | 64.8875 | 65 | 44.75 | 65 | 65
Application basic setup | 6 | 0.75 | Jr Developer | 1 | 33 | 33
Student |  |  | qa | 1 | 25.1375 | 25.1375
Registraion | 16 | 2 | API Development | 1 | 20 | 20
Verify by email | 8 | 1 | Total |  |  | 114.1375
verify by OTP | 6 | 0.75 | Effort | 114.1375 | + 1 Day (Deployment) | 5.7069
Login (stay signed in) | 6 | 0.75 | Delivery Time | 61.1375 | + 1 Day (Deployment) | 3.0569
Allow access location, Allow notification | 8 | 1
Legal agreement | 3 | 0.375
Generate ID | 3 | 0.375
Create Profile | 8 | 1
Dashboard (Learn - my schedule , Me, Wallet - payment options (3), Buy subscription) | 24 | 3
Browse Tutors (6 profiles per page) - With live status | 16 | 2
Search / filter (multiple) tutors | 8 | 1
View Tutor profile (picture, video, personal details, certifications etc) | 6 | 0.75
schedule session with tutor | 8 | 1
Manage Profile (view / edit) | 6 | 0.75
Manage Wallet (payment options) | 8 | 1
Buy subscriptions | 16 | 2
Refer a friend | 2 | 0.25
Settings (reset password, currency) | 6 | 0.75
Get help (Q&A) | 6 | 0.75
Contact US (with info on app version, device info, OS version etc) | 6 | 0.75
Live stream with chat and reactions using Twilio | 24 | 3
Rate session | 6 | 0.75
Rate tutor | 6 | 0.75
Join guaranteed session | 8 | 1
Avail coupons, limited time offers | 6 | 0.75
Messages | 6 | 0.75
Teacher
Registraion | 8 | 1
Verify by email | 6 | 0.75
verify by OTP | 6 | 0.75
Login (stay signed in) | 6 | 0.75
Allow access location, Allow notification | 6 | 0.75
Legal agreement | 3 | 0.375
Generate ID | 3 | 0.375
Create Profile (video, image, certifications etc) | 12 | 1.5
Dashboard (Schedule , Me, balance, wallet- bank info) | 18 | 2.25
Refer a friend | 2 | 0.25
Rate Student | 6 | 0.75
Schedule guaranteed sessions | 12 | 1.5
Cancel sessions (csheduled and guranteed) | 6 | 0.75
Messages (from admin, students, Warnings, Desciplinary etc) | 6 | 0.75
Avail offers | 2 | 0.25
Live stream with chat and reactions using Twilio | 24 | 3
API development | 161.1 | 20.1375
QA & UAT
QA | 161.1 | 20.1375 | 161.1
UAT | 40 | 5
Deployments | 8 | 1
Total Effort | 596.2 | 74.525