## Estimate
Project Name : Crowd Invest Mobile Development Estimate ( Android )
Inputs |  | Estimation Summary (Hours and Business days)
Risk and/or "unknown" (25% ; 50% ; 25% ; 10%) | 10 | Optimistic hours | 409.2 | 29.2286 |  | 34.1
Project Complexity scale Extreme(100%); high(50%) ; medium(25%) ; low(10%) | 10 | Most likely hours** | 470.58 | 33.6129 | 192000 | 34.1
Average productive hours per day | 7 | Pessimistic hours* | 531.96 | 37.9971 |  | 122.76 | Holidays in 2016 | Date
Estimation parameters | Hours | [5 empty] | New Year's Day | 2016-01-01
Requirement gathering | 8 | Expected Duration |  | Hours |  |  | Republic Day | 2016-01-26
Research and analysis | 8 | Triangular distribution method |  | 33.6129 |  |  | Monty Thursday | 2016-03-24
Development | 220 | Beta distribution (PERT technique) |  | 33.6129 |  |  | Good Friday | 2016-03-25
Design | 20 | [5 empty] | Vishu | 2016-04-14
Testing | 44 | Finish Date |  |  |  |  | May Day | 2016-05-01
Training | 0 | Earliest start date | 5/2/2016 |  |  |  | Assembly Elections | 2016-05-16
Documentation | 8 | Earliest completion date | 2016-06-13 | Optimistic |  |  | Onam | 2016-09-13
Meetings | 16 | Earliest completion date | 2016-06-17 | Most likely |  |  | Onam | 2016-09-14
Migration (data or content) | 0 | Earliest completion date | 2016-06-23 | Pessimistic |  |  | Onam | 2016-09-15
Project management | 11 | [5 empty] | Gandhu Jayanthi | 2016-10-02
Reports | 0 | Latest start date | 2016-05-09 |  |  |  | Deepavali | 2016-10-29
UAT | 0 | Latest completion date | 2016-06-20 | Optimistic |  |  | Christmas | 2016-12-26
Accessibility test | 0 | Latest completion date | 2016-06-24 | Most likely
Pre deployment process | 1 | Latest completion date | 2016-06-30 | Pessimistic
Deployment | 4
Post production testing | 0 | Pessimistic case buffer (in percentage) |  | 30
Knowledge transfer/ Service transition | 1 | No of resources (This will impact the number of business days to complete and finish date calculation.) on average |  | 2
Marketing | 0
Project retrospective | 0
* Pessimistic hours= Best case hours+ Pessimistic case buffer **Most likely=(Optimistic + Pessimistic )/2 ***Excluded Saturdays, Sundays and state holidays
Total | 341
Note on E13: Prashant Thomas: Please enter your estimated start date here

## Hybrid App
| Crowdinvest Mobile app | 2016-06-01
Sl. No. | Product Log | Days | Comments
1 | Splash Screen |  | TBD
2 | Welcome / Home Screen | 0.5 | Icons will tiled on the home screen
Logo (Common in all screen)
Icon for Home and search on the navigation bar
Icons for Prospectus, Courses, Sample Videos, About Us, Journals & Contact Us
3 | Prospectus Download | 1 | Will the prospectus be entered as a text or will it be uploaded as a PDF of Word document. If the prospectus is entered as text, then a predefined template has to be created to display the textual information
List Prospectus
View prospectus
Template for text (optional)
4 | Courses | 1 | New courses and course descriptions can be maintained from the back end of the web application. The register for course is a link to the course registration page.
Display Course List
Display Course description
Course description template
Register for course
5 | Sample MBA Videos | 0.5 | We suggest that videos be hosted on Youtube privately. Reason being saving videos on our server would warrant the creation and embedding of video plugins within the mobile app. This means we have to take into consideration that low resoulution videos be served for low bandwidth customers. (and a whole other can of worms)
Display videos on u tube player
6 | About Us | 0
Static page
7 | MBA Journals | 1
List Journals
Display Journals
Journal templates (optional)
8 | Contact Us | 0.5
Static Display page with form submission
9 | Search (optional) | 1 | Dynamic search that will return results on journals, course content vidoes etc. For simplicity Google search can be implemented or something similar.
Search for content on the site
Display content
10 | LMS |  | Theme development can vary between 1 -4 days dpending on weather a theme is purchased or not.
| Sys Admin* | 3
Application Installation and Sever Configuration ( APP server, Mail, Database)
Application configuration (plugins, Theming, Cron Jobs)
Configure default Sitewide Settings
| API Integration* (development) | 4
Configure users for self registration (teachers and students)
| Site Admin* | 1
New Users and Roles and permissions (Student, Teacher)
Create/Update Courses, course categories and (grades : optional)
Create Course content and format
Course assignment for students
| Theme Development (optional) | 4
| Integration with Payment processing (optional) | 1
Application can be configured so that students can choose to opt for class registration and payment within the LMS App, as opposed to payments outside LMS
11 | Payment Processing | 3 | Payment processor of your choice. Will not be tied to the LMS platform, but it can be, if needed
API Integration
SSL Implementation and other security features such as CORS
12 | LMS Integration |  | Irrespective of what LMS is chosen, it has to be customized and be made fit for purpose. The time involved for customization depends on the level of detail and functionality. But no matter what, a minimal amount of time is required for customization irrespective of the outcome of the final solution
LMS Customization
LMS Implementation and integration
LMS API interface for the Mobile App
13 | Hybrid IOS APP | 1
conversion of Web App to Hybrid mobile App using PhoneGap and Cordova
| Hybrid Android App | 1
conversion of Web App to Hybrid mobile App using PhoneGap and Cordova
| ADMIN (Back End Functionality ) | 4
Database Design
Manage Prospectus
Mange Course Content (Course List + description)
Manage MBA Video (you tube link)
Manage MBA Journals
Manage Course Registration
User Administartion
| Total | 27.5
| Cumulative Total | 220

## Sheet4
Hybrid IOS/Android Mobile App
Sl. No. | Module | Comments
1 | Splash Screen
2 | Welcome / Home Screen | Icons will tiled on the home screen
Logo (Common in all screen)
Icon for Home and search on the navigation bar
Icons for Prospectus, Courses, Sample Videos, About Us, Journals & Contact Us
3 | Prospectus Download | Will the prospectus be entered as a text or will it be uploaded as a PDF of Word document. If the prospectus is entered as text, then a predefined template has to be created to display the textual information
List Prospectus
View prospectus
Template for text (optional)
4 | Courses | New courses and course descriptions can be maintained from the back end of the web application. The register for course is a link to the course registration page.
Display Course List
Display Course description
Course description template
Register for course
5 | Sample MBA Videos | We suggest that videos be hosted on Youtube privately. Reason being saving videos on our server would warrant the creation and embedding of video plugins within the mobile app. This means we have to take into consideration that low resoulution videos be served for low bandwidth customers. (and a whole other can of worms)
Display videos on u tube player
6 | About Us
Static page
7 | MBA Journals
List Journals
Display Journals
Journal templates (optional)
8 | Contact Us
Static Display page with form submission
9 | Search (optional) | Dynamic search that will return results on journals, course content vidoes etc. For simplicity Google search can be implemented or something similar.
Search for content on the site
Display content
10 | LMS | Theme development can vary between 1 -4 days dpending on weather a theme is purchased or not.
Sys Admin*
Application Installation and Sever Configuration ( APP server, Mail, Database)
Application configuration (plugins, Theming, Cron Jobs)
Configure default Sitewide Settings
11 | API Integration* (development)
Configure users for self registration (teachers and students)
Site Admin*
New Users and Roles and permissions (Student, Teacher)
12 | Create/Update Courses, course categories and (grades : optional)
Create Course content and format
Course assignment for students
Theme Development (optional)
Integration with Payment processing (optional)
13 | Application can be configured so that students can choose to opt for class registration and payment within the LMS App, as opposed to payments outside LMS
| Payment Processing | Payment processor of your choice. Will not be tied to the LMS platform, but it can be, if needed
API Integration
SSL Implementation and other security features such as CORS
| LMS Integration | Irrespective of what LMS is chosen, it has to be customized and be made fit for purpose. The time involved for customization depends on the level of detail and functionality. But no matter what, a minimal amount of time is required for customization irrespective of the outcome of the final solution
LMS Customization
LMS Implementation and integration
LMS API interface for the Mobile App
Hybrid IOS APP
conversion of Web App to Hybrid mobile App using PhoneGap and Cordova
Hybrid Android App
conversion of Web App to Hybrid mobile App using PhoneGap and Cordova
ADMIN (Back End Functionality )
Database Design
Manage Prospectus
Mange Course Content (Course List + description)
Manage MBA Video (you tube link)
Manage MBA Journals
Manage Course Registration
User Administartion