## Consolidated
Web Site | [10 empty] | Mobile App
Web Site | [10 empty] | Mobile APP
Estimate for All services on the website | [10 empty] | All services on web site
Role | Resources | Days | Total Days | [8 empty] | No | Man Days | Total Effort
Designer | 1.5 | 5.3333 | 8 | [7 empty] | Mobile Design (Different from UI/UX) | 1 | 4 | 4
Sr Developer | 2 | 58.5 | 117 | 233 | 257.3 | 233 | 234 |  |  |  | Sr Developer | 1 | 70 | 70
Jr Developer | 2 | 58.5 | 117 | [7 empty] | Jr Developer | 1 | 70 | 70
PM | 1 | 23.3 | 23.3 | [7 empty] | qa | 1.5 | 45.3708 | 68.0563
BA | 1 | 15 | 15 | [7 empty] | API Development | 1
Tech writer | 1 | 5 | 5 | [7 empty] | Total |  |  | 212.0563 |  | Man Months
QA | 2 | 59.925 | 119.85 | [7 empty] | Effort | 212.0563 | + 1 Day (Deployment) |  |  | 10.6028
Total | 10.5 | 225.5583 | 405.15 | [7 empty] | Delivery Time | 119.3708 | + 1 Day (Deployment) |  |  | 5.9685
0 | 0 | 0 |  |  |  | Man Months
Effort | 405.15 | + 2 Days (Deployment) |  |  |  | 20.2575
Delivery Time | 143.7583 | + 2 Days (Deployment) |  |  |  | 7.1879
0
0
PDF Only Estimate | [10 empty] | PDF only Estimate
Role | Resources | Days | Total days | [8 empty] | No | Man Days | Total Effort
Designer | 1.5 | 5.3333 | 8 | 0 | 0 | 0 | 0 |  |  |  | Mobile Design (Different from UI/UX) | 1 | 4 | 4
Sr Developer | 2 | 37.5 | 75 | 744 | 170.45 | 154.5 | 155 |  |  |  | Sr Developer | 1 | 40 | 40 | 17 | 41 | 40.125 | 41
Jr Developer | 2 | 40 | 80 | [7 empty] | Jr Developer | 1 | 42 | 42
PM | 1 | 15.45 | 15.45 | [7 empty] | qa | 1.5 | 27.7458 | 41.6187
BA | 1 | 8 | 8 | [7 empty] | API Development | 1 |  | 0
Tech writer | 1 | 4 | 4 | [7 empty] | Total |  |  | 127.6188 |  | Man Months
QA | 2 | 38.7625 | 77.525 | [7 empty] | Effort | 127.6188 | + 1 Day (Deployment) |  |  | 6.3809
Total | 10.5 | 149.0458 | 267.975 | [7 empty] | Delivery Time | 73.7458 | + 1 Day (Deployment) |  |  | 3.6873
0 | 0 | 0 | 0 |  |  | Man Months
Effort | 267.975 | + 2 Days (Deployment) |  |  |  | 13.3988
Delivery Time | 96.0958 | + 2 Days (Deployment) |  |  |  | 4.8048
[9 empty] | Man Days | Man Months
[8 empty] | Total Effort (All) | 617.2063 | 30.8603
[8 empty] | Total Effort (PDF ) | 395.5938 | 19.7797
[8 empty] | Delivery TIme All | 143.7583 | 7.1879
[8 empty] | Delivery Time PDF | 96.0958 | 4.8048

## mobile
WriTalk - Mobile (IOS) |  |  | 19/4/2020
Sunday
All services on web site
Module | Mobile |  |  |  | No | Man Days | Total Effort
| Hours | Days (PDF) | Man Days | Mobile Design (Different from UI/UX) | 1 | 4 | 4
Development |  |  |  | Sr Developer | 1 | 70 | 70 | 52.125 | 140 | 140.125 | 140
Application basic setup | 8 | 1 | 1 | Jr Developer | 1 | 70 | 70
Registration/Create MOCCAE account | 8 | 1 | 1 | qa | 1.5 | 45.3708 | 68.0563
Login with username and password or Login with UAE pass | 16 | 2 | 2 | API Development | 1
Chatbot and live chat | 20 | 2.5 | 2.5 | Total |  |  | 212.0563
PushNotification | 10 | 1.25 | 1.25 | Effort | 212.0563 | + 1 Day (Deployment)
Help and support(faq and live chat) | 10 | 1.25 | 1.25 | Delivery Time | 119.3708 | + 1 Day (Deployment)
Happiness meter | 8 | 1 | 1
Dashboard | 10 | 1.25 | 1.25
Service Request Tracking Feature | 10 | 1.25 | 1.25 |  | No | Man Days | Total Effort
Events and News | 10 | 1.25 | 1.25 | Mobile Design (Different from UI/UX) | 1 | 4 | 4
Rate and share | 12 | 1.5 | 1.5 | Sr Developer | 1 | 40 | 40 | 17 | 82 | 81.375 | 82
Customer location,working hours and services to be displayed. | 16 | 2 | 2 | Jr Developer | 1 | 42 | 42
Create Incident | 16 | 2 | 2 | qa | 1.5 | 27.7458 | 41.6187
Welcome message as push notification(within 100M range) | 10 | 1.25 | 1.25 | API Development | 1 |  | 0
Contact us,privacy , terms and condition | 10 | 1.25 | 1.25 | Total |  |  | 127.6188
LICENSING |  |  |  | Effort | 127.6188 | + 1 Day (Deployment)
New / Renew Fishing Boat License | 24 | 3 | 3 | Delivery Time | 73.7458 | + 1 Day (Deployment)
Accreditation / renew of food establishment to export outside UAE - New | 18 | 2.25 | 2.25
Add or Replace Fishing Boat's Engine | 12 | 1.5 | 1.5
Agricultural Extension Request | 8 |  | 1
Change Fishing Method | 6 | 0.75 | 0.75
Issuae / renew of Aquaculture Farm Establishment License | 15 | 1.875 | 1.875
Issue / renew a License for Manufacturing a Fertilizer/Soil Conditioner | 16 | 2 | 2
Issue / renew a license of practicing animal activity | 16 | 2 | 2
Issue / renew a Plant Nursery License | 16 | 2 | 2
Issue a Temporary License of a Practicing the Profession for Veterinarians | 6 | 0.75 | 0.75
Issue / renew a Veterinary Establishment License | 16 | 2 | 2
Issue / Renew an Agricultural Activity License | 16 | 2 | 2
Issue / renew an Export License (Local Aquatic Organisms’ Products) | 10 | 1.25 | 1.25
Issue an Import Permit of Agricultural Consignment | 6 |  | 0.75
Issue / renew Import License (Broodstock and Larvae/ Fishing Tools and Equipment) | 10 | 1.25 | 1.25
Issue / renew a license for animal production farm | 10 | 1.25 | 1.25
Issuing a license for practicing the profession for veterinarians and assisting veterinary professions | 6 | 0.75 | 0.75
Modification or Cancellation of Basic Data of Agricultural Holdings | 6 |  | 0.75
Preliminary approval to license an animal production farm | 10 | 1.25 | 1.25
Primary approval on licensing a veterinary facility | 10 | 1.25 | 1.25
Renew issuance license of practicing the profession for veterinarians and for the assistant vet | 6 | 0.75 | 0.75
Replacement of Fishing Boat | 6 | 0.75 | 0.75
Request ٍSubsidies for Farmers | 6 |  | 0.75
Request ٍSubsidies for Fishermen’s | 6 |  | 0.75
Sale of Fishing Boat's Body | 6 | 0.75 | 0.75
new / renew Slaughterhouse Accreditation Outside UAE | 10 | 1.25 | 1.25
Transfer Fishing Boat Ownership ( also to heirs) | 6 | 0.75 | 0.75
Veterinary Extension Request | 6 |  | 0.75
issue / renew Vice-Captain Card Issuance | 6 | 0.75 | 0.75
PERMITS
Adopting Veterinary Raw Materials for Importation | 10 |  | 1.25
Apply for Release Permit (Fishing Tools and Equipment) | 8 |  | 1 | 211.05
Approve Disinfectants, Veterinary Equipment and Supplies, and Animal Care Supplies for Distribution | 8 |  | 1
Issuance Import permit for Semen or Embryos | 10 |  | 1.25
Issuance of Re-export of Vegetable Feed Permission | 8 |  | 1
Issue a Permanent or Temporary Horse import permit | 8 |  | 1
Issue a Permit to Import Ozone Depleting Substances (ODS) | 8 |  | 1
Issue a Permit to Import Pesticides | 6 |  | 0.75
Issue a permit to re-export ozone depleting substances (ODS) | 8 |  | 1
Issue a Re-Export Permit (Aquatic Organisms Products) | 8 |  | 1
Issue an agricultural consignment release | 8 |  | 1
Issue an Export Permit (Local Aquatic Organisms’ Products) | 8 |  | 1
Issue an Export Permit of Hazardous Waste | 6 |  | 0.75
Issue an Import Permit (Broodstock or Larvae) | 8 |  | 1
Issue an Import Permit (Fishing Tools and Equipment) | 8 |  | 1
Issue an Import Permit for Animal Products or By-Products | 8 |  | 1
Issue an Import Permit for Feed and Processed Animal Feed | 8 |  | 1
Issue an Import permit for live animals, Birds and Ornamental fish | 6 |  | 0.75
Issue an Import Permit for Pets - Cats or Dogs | 6 |  | 0.75
Issue an Import Permit of Fertilizers or Soil Conditioners (Restricted) | 6 |  | 0.75
Issue an Import Permit of Fertilizers or Soil Conditioners (Unrestricted) | 6 |  | 0.75
Issue an Import permit of Pheromones, Attracting materials, Extruding materials, Additives and Materials with mechanical or physical in pest control | 8 |  | 1
Issue import permit for non-manufactured feed for aquatic organisms | 8 |  | 1
Issuing an Import Permit for Disinfectants, Veterinary Equipment and Supplies, and Animal Care Supplies | 8 |  | 1
Issuing export permit of animal samples | 8 |  | 1
Issuing Import Permit for Veterinary Products | 8 |  | 1
Issuing import permit of animal samples | 8 |  | 1
Issuing Import Permit of Veterinary Raw Materials | 8 |  | 1
Release of Locally Manufactured Fertilizers | 6 |  | 0.75
CITES
Cancellation of Species Ownership Listed in CITES Appendices | 8 |  | 1
Issue a CITES Export/Re-export Certificate | 8 |  | 1
Issue a CITES Import Certificate | 8 |  | 1
Issue a Falcon passport in accordance with the Federal Law on CITES | 6 |  | 0.75
Issue a to whom it may concern letter in accordance with the federal law on CITES | 6 |  | 0.75
Ownership Registration of Species Listed in CITES Appendices | 8 |  | 1
Request for Falcon Identification Rings | 8 |  | 1
Transfer Species Ownership Listed in CITES Appendices | 8 |  | 1
CERTIFICATES
Approved of Phermions, Attracting materials, Extruding materials, Additives and Materials with mechanical or physical in pest control | 8 |  | 1
Issuance of Good Manufacturing Certificate GMP | 8 |  | 1
Issue a license to practice the profession of agricultural engineer and occupations related to agricultural activities | 6 |  | 0.75
Issue a Registration Certificate for a Fertilizer or a Soil Conditioner | 8 |  | 1
Issue a Veterinary Health Certificate for Exporting Equine Semen | 8 |  | 1
Issue a Veterinary Health Certificate for Exporting or Re-Exporting Animal and Fish Products or byproducts and Manufactured Feed | 8 |  | 1
Issue a Veterinary Health Certificate for Exporting or Re-Exporting Horses | 8 |  | 1
Issue a Veterinary Health Certificate for Exporting or Re-Exporting Live Animals | 6 |  | 0.75
Issue an Phytosanitary Certificate for Export or Re-Export | 8 |  | 1
Issue Certificate of Heat Treatment Facility Approval | 8 |  | 1
Issue license to re-export aquatic organisms | 6 |  | 0.75
Issue Pesticide Registration Certificate | 8 |  | 1
Issue Registration Certificate of Veterinary Product Companies | 8 |  | 1
Issuing a Free Sale Certificate for a Veterinary Product | 6 |  | 0.75
Issuing Registration Certificate of Veterinary Products | 6 |  | 0.75
Renew license to re-export aquatic organisms | 8 |  | 1
Renewal registration certificate of veterinary product | 8 |  | 1
Renewal a license to practice the profession of agricultural engineer and occupations related to agricultural activities | 8 |  | 1
Renewal of Good Manufacturing Certificate GMP | 8 |  | 1
Renewal Registration Certificate of Veterinary Product Companies | 8 |  | 1
INTEGRATIONS
Integration of Emirates ID | 20 | 2.5 | 2.5
Integration with portal CMS | 20 | 2.5 | 2.5
Integration with mail/exchange server | 20 | 2.5 | 2.5
Integration of Bio-Security | 20 | 2.5 | 2.5
Integration with current eservices | 20 | 2.5 | 2.5 |  |  | 320 | 40
Integration with qmatic system | 20 | 2.5 | 2.5
Integration of happiness meter sdk | 20 | 2.5 | 2.5
Integration of UAE pass | 24 | 3 | 3
Payment Gateway Integartion | 24 | 3 | 3
Bilingual (English, Arabic, Urdu) | 32 | 4 | 4
Quality Assurance
QA & Bug Fixing | 504.45 | 36.6187 | 63.0562
UAT | 40 | 5 | 5
Deployment per instance | 8 | 1 | 1
Total Effort | 1673.45 | 123.9938 | 209.1813

## Web
|  | MOCCAE Services |  | 2020-05-05
Tuesday
Estimate for All services on the website
| Module | Hours | Man Days (PDF) | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  |  | Designer | 1.5 | 5.3333 | 8
1 | Business analysis | 120 | 8 | 15 | Sr Developer | 2 | 58.5 | 117 | 233 | 257.3 | 233 | 234
2 | Project Management | 186.4 | 15.45 | 23.3 | Jr Developer | 2 | 58.5 | 117
3 | SRS,FS,User Manual | 40 | 4 | 5 | PM | 1 | 23.3 | 23.3
4 | UI / UX (Web & Moile IOS) inclusive of 3 sample designs | 64 | 8 | 8 | BA | 1 | 15 | 15
| Development (Effort estimated for shaded region) |  |  |  | Tech writer | 1 | 5 | 5
5 | Application basic setup | 8 | 1 | 1 | QA | 2 | 59.925 | 119.85
| Website |  |  |  | Total | 10.5 | 225.5583 | 405.15
LICENSING
| Renew / New Fishing Boat License | 12 | 2 | 1.5 | Effort | 405.15 | + 2 Days (Deployment) |  |  |  | 20.2575
| New / renew Accreditation of food establishment to export outside UAE - New | 12 | 2 | 1.5 | Delivery Time | 143.7583 | + 2 Days (Deployment) |  |  |  | 7.1879
| Add or Replace Fishing Boat's Engine | 12 | 2 | 1.5
| Agricultural Extension Request | 12 |  | 1.5
| Change Fishing Method | 12 | 2 | 1.5 | Estimate for services mentioned on the PDF
| Issuance / Renew of Aquaculture Farm Establishment License | 12 | 2 | 1.5 |  | No | Man Days | Total Effort
| Issue / renew a License for Manufacturing a Fertilizer/Soil Conditioner | 12 | 2 | 1.5 | Designer | 1.5 | 5.3333 | 8
| Issue / renew a license of practicing animal activity | 12 | 2 | 1.5 | Sr Developer | 2 | 37.5 | 75 | 744 | 170.45 | 154.5 | 155
| Issue / renew a Plant Nursery License | 12 | 2 | 1.5 | Jr Developer | 2 | 40 | 80
| Issue / renew a Veterinary Establishment License | 12 | 2 | 1.5 | PM | 1 | 15.45 | 15.45
| Issue / renew an Agricultural Activity License | 12 | 2 | 1.5 | BA | 1 | 8 | 8
| Issue / renew an Export License (Local Aquatic Organisms’ Products) | 12 | 2 | 1.5 | Tech writer | 1 | 4 | 4
| Issue an Import Permit of Agricultural Consignment | 12 |  | 1.5 | QA | 2 | 38.7625 | 77.525
| Issue Renew Import License (Broodstock and Larvae/ Fishing Tools and Equipment) | 12 | 2 | 1.5 | Total | 10.5 | 149.0458 | 267.975
| Issue / renewal / preliminary approval license for animal production farm | 12 | 2 | 1.5
| Issue / renew / temp license for practicing the profession for veterinarians and assisting veterinary professions | 12 | 2 | 1.5 | Effort | 267.975 | + 2 Days (Deployment) |  |  |  | 13.3988
| Modification or Cancellation of Basic Data of Agricultural Holdings | 12 |  | 1.5 | Delivery Time | 96.0958 | + 2 Days (Deployment) |  |  |  | 4.8048
| Primary approval on licensing a veterinary facility | 12 | 2 | 1.5
| Registration of agricultural holdings | 12 |  | 1.5
| Issue / Renew Vice-Captain's Card | 12 | 2 | 1.5
| Replacement of Fishing Boat | 12 | 2 | 1.5
| Request ٍSubsidies for Farmers | 12 |  | 1.5
| Request ٍSubsidies for Fishermen’s | 12 |  | 1.5
| Sale of Fishing Boat's Body | 12 | 2 | 1.5
| New / renew Slaughterhouse Accreditation Outside UAE | 12 | 2 | 1.5
| Transfer Fishing Boat Ownership (includingo heirs) | 12 | 2 | 1.5
| Veterinary Extension Request | 12 |  | 1.5
PERMITS
| Adopting Veterinary Raw Materials for Importation | 12 |  | 1.5
| Apply for Release Permit (Fishing Tools and Equipment) | 12 |  | 1.5
| Approve Disinfectants, Veterinary Equipment and Supplies, and Animal Care Supplies for Distribution | 12 |  | 1.5
| Issue Import permit for Semen or Embryos | 12 |  | 1.5
| Issue of Re-export of Vegetable Feed Permission | 12 |  | 1.5
| Issue a Permanent or Temporary Horse import permit | 12 |  | 1.5
| Issue a Permit to Import Ozone Depleting Substances (ODS) | 12 |  | 1.5
| Issue a Permit to Import Pesticides | 12 |  | 1.5
| Issue a permit to re-export ozone depleting substances (ODS) | 12 |  | 1.5
| Issue a Re-Export Permit (Aquatic Organisms Products) | 12 |  | 1.5
| Issue an agricultural consignment release | 12 |  | 1.5
| Issue an Export Permit (Local Aquatic Organisms’ Products) | 12 |  | 1.5
| Issue an Export Permit of Hazardous Waste | 12 |  | 1.5
| Issue an Import Permit (Broodstock or Larvae) | 12 |  | 1.5
| Issue an Import Permit (Fishing Tools and Equipment) | 12 |  | 1.5
| Issue an Import Permit for Animal Products or By-Products | 12 |  | 1.5
| Issue an Import Permit for Feed and Processed Animal Feed | 12 |  | 1.5
| Issue an Import permit for live animals, Birds and Ornamental fish | 12 |  | 1.5
| Issue an Import Permit for Pets - Cats or Dogs | 12 |  | 1.5
| Issue an Import Permit of Fertilizers or Soil Conditioners (Restricted) | 12 |  | 1.5
| Issue an Import Permit of Fertilizers or Soil Conditioners (Unrestricted) | 12 |  | 1.5
| Issue an Import permit of Pheromones, Attracting materials, Extruding materials, Additives and Materials with mechanical or physical in pest control | 12 |  | 1.5
| Issue import permit for non-manufactured feed for aquatic organisms | 12 |  | 1.5
| Issue an Import Permit for Disinfectants, Veterinary Equipment and Supplies, and Animal Care Supplies | 12 |  | 1.5
| Issue export permit of animal samples | 12 |  | 1.5
| Issue Import Permit for Veterinary Products | 12 |  | 1.5
| Issue import permit of animal samples | 12 |  | 1.5
| Issue Import Permit of Veterinary Raw Materials | 12 |  | 1.5
| Release of Locally Manufactured Fertilizers | 12 |  | 1.5
CITES
| Cancellation of Species Ownership Listed in CITES Appendices | 12 |  | 1.5
| Issue a CITES Export/Re-export Certificate | 12 |  | 1.5
| Issue a CITES Import Certificate | 12 |  | 1.5
| Issue a Falcon passport in accordance with the Federal Law on CITES | 12 |  | 1.5
| Issue a to whom it may concern letter in accordance with the federal law on CITES | 12 |  | 1.5
| Ownership Registration of Species Listed in CITES Appendices | 12 |  | 1.5
| Request for Falcon Identification Rings | 12 |  | 1.5
| Transfer Species Ownership Listed in CITES Appendices | 12 |  | 1.5
CERTIFICATES
| Approved of Phermions, Attracting materials, Extruding materials, Additives and Materials with mechanical or physical in pest control | 12 |  | 1.5
| Issue / renewal of Good Manufacturing Certificate GMP | 12 |  | 1.5
| Issue / renew license to practice the profession of agricultural engineer and occupations related to agricultural activities | 12 |  | 1.5
| Issue a Registration Certificate for a Fertilizer or a Soil Conditioner | 12 |  | 1.5
| Issue a Veterinary Health Certificate for Exporting Equine Semen | 12 |  | 1.5 |  | Site logo
| Issue a Veterinary Health Certificate for Exporting or Re-Exporting Animal and Fish Products or byproducts and Manufactured Feed | 12 |  | 1.5 |  | Arab & urdu CMS
| Issue a Veterinary Health Certificate for Exporting or Re-Exporting Horses | 12 |  | 1.5
| Issue a Veterinary Health Certificate for Exporting or Re-Exporting Live Animals | 12 |  | 1.5 |  | Arabic and Urdu UI
| Issue an Phytosanitary Certificate for Export or Re-Export | 12 |  | 1.5
| Issue Certificate of Heat Treatment Facility Approval | 12 |  | 1.5
| Issue / renew license to re-export aquatic organisms | 12 |  | 1.5
| Issue Pesticide Registration Certificate | 12 |  | 1.5
| Issue / Renew Registration Certificate of Veterinary Product Companies | 12 |  | 1.5
| Issuing a Free Sale Certificate for a Veterinary Product | 12 |  | 1.5
| Issue / renew Registration Certificate of Veterinary Products | 12 |  | 1.5
External Integrations
| Dubai Economic Department | 16 | 2 | 2
| Sharjah Economic Department | 16 | 2 | 2
| Abu-Dhabi economic development | 16 | 2 | 2
| Ministry of Human Resources and Emiratization (Veterinarian License) | 16 | 2 | 2
| Ministry of Human Resources and Emiratization (Agricultural Engineer License) | 16 | 2 | 2
| MOCCAE smart inspection internal application regarding inspection step | 16 | 2 | 2
| MOF e-DHS payment getaway to allow the user to pay service fees/charges | 16 | 2 | 2
| Critical Infrastructure and Coastal Protection Authority for Fisher services for NOC letter | 16 | 2 | 2
| Mail / Exchange Server for sending SMS & email as template to the customers /staff based on configuration in the new digital services | 16 | 2 | 2
| Emirates ID as currently this integration is available for current eservices | 16 | 2 | 2
| Integration with current eservice regarding user profiles & logged users (SSO) and information/views required for other existing services like import requests, etc | 16 | 2 | 2
| MOCCAE GIS integration related to location (store and display the map) | 16 | 2 | 2
| Payment gateway integration | 16 | 2 | 2
| Chat bot integration | 8 | 1 | 1
System Features
| Multi level approval service (workflow engine) | 20 | 2.5 | 2.5
| CMS for managing Site logo and foreign languages (Arabic & Urdu), Service name changes, events, news | 20 | 2.5 | 2.5
| Multi lingual website (Arabic, Urdu & English) | 20 | 2.5 | 2.5
| License Auto-renewal process ( Send renewal notification to customers) | 20 | 2.5 | 2.5
| License Auto-renewal managment service | 20 | 2.5 | 2.5
| SLA managment service (Escalations via dashboard and emails) | 20 | 2.5 | 2.5
| Customer Dashboard with SLA, Status, Notification messages, action items | 20 | 2.5 | 2.5
| Dashboard Admin with escalations, service status, SLA , advanced search, sorting, pagination etc. | 20 | 2.5 | 2.5
| Dashboard Employee with escalations, service status, SLA , advanced search, recent requests etc. | 20 | 2.5 | 2.5
| Advanced search | 20 | 2.5 | 2.5
| Federated Login (Emirates ID intergation) | 20 | 2.5 | 2.5
| Multi factor authentication | 20 | 2.5 | 2.5
| Unified User Experience ( Avoid already saved and redundant information) | 20 | 2.5 | 2.5
| Pagination service | 20 | 2.5 | 2.5
| Wizard based service pages with attachments (includes License New / renewal / cancellation / save as draft / QR Codes / payment voucher) | 20 | 2.5 | 2.5
| Google Captcha | 16 | 2 | 2
| Customer management | 20 | 2.5 | 2.5
| Employee management | 20 | 2.5 | 2.5
| Audit Trail | 20 | 2.5 | 2.5
| Reports | 40 | 5 | 5
| Data migration | 40 | 5 | 5
| User registration / login/ forgot password / remember password / email verification | 20 | 2.5 | 2.5
| API Integration for mobile App | 80 | 10 | 10
| Rate the service, Feed back | 8 | 1 | 1
| Events and News (CMS) | 8 | 1 | 1
| FAQ | 12 | 1.5 | 1.5
Security
| Protection against injection attacks (SQL, CRLF) | 12 | 1.5 | 1.5
| URL encoding, Input validation | 8 | 1 | 1
| Cookie Encryption, Cookie replay attacks | 8 | 1 | 1
| Session hijacking prevention | 8 | 1 | 1
| Cross site scripting and session management | 8 | 1 | 1
Application Integration
| REDIS | 16 | 2 | 2
| Minio | 16 | 2 | 2
| Identity server | 16 | 2 | 2
| ELK stack | 16 | 2 | 2
| Tableu | 8 | 1 | 1
Other
Train the trainer
End User training
Quality Assurance
| QA & Bug Fixing | 838.8 | 69.525 | 104.85
| UAT | 120 | 8 | 15
| Deployment per instance | 16 | 2 | 2
| Total Effort |  | 270.475 | 407.15
Assumptions
The effort may change after a detailed system study
UI path pricing not included

## PDF
Renew Fishing Boat License
Accreditation of food establishment to export outside UAE - New
Add or Replace Fishing Boat's Engine
Change Fishing Method
Issuance of Aquaculture Farm Establishment License
Issue a License for Manufacturing a Fertilizer/Soil Conditioner
Issue a license of practicing animal activity
Issue a Plant nursery license
Issue a temporary license of a practicing the profession for veterinarians
Issue a veterinary establishment license
Issue an agricultural activity license
Issue an Export License (Local Aquatic Organisms’ Products)
Issue Import License (Broodstock and Larvae/ Fishing Tools and Equipment)
Issuing a license for animal production farm
Issuing a license for practicing the profession for veterinarians and assisting veterinary professions
Preliminary approval to license an animal production farm
Primary approval on licensing a veterinary facility
Renew Aquaculture Farm Establishment License
Renew Import License (Broodstock and Larvae/ Fishing Tools and Equipment)
Renew issuance license of practicing the profession for veterinarians and for the assistant vet
Renew Plant nursery license
Renew Veterinary Establishment Licence
Renew Vice-Captain's Card
Renewal a license for manufacture fertilizers and soil conditioner
Renewal Issue a license of practicing animal activity
Renewal of accreditation of food establishment to export outside UAE
Renewal of agricultural activity license
Renewal of an Export License (Local Aquatic Organisms’ Products)
Renewal of Slaughterhouse Accreditation Outside UAE
Renewal of the license of an animal production farm
Replacement of Fishing Boat
Sale of Fishing Boat's Body
Slaughterhouse accreditation outside UAE
Transfer Fishing Boat Ownership
Transfer Fishing Boat's Ownership to Heirs
Vice-Captain Card Issuance

## UIPATH
Document verification using UIPath | Hours | Days
Inspection Report from CICPA | 16 | 2
Inspection report related to hygene regulations | 16 | 2
Delisting certificate of marine engine | 16 | 2
Purchase invoice of the boat engine | 16 | 2
Trade License - Aquaculture farm | 16 | 2
Environmental license (Approval) - Aquaculture farm | 16 | 2
Industrial license from Ministry of Economy Fertilizer / soil conditioner | 16 | 2
Veterinarian license | 16 | 2
Payment receipts | 16 | 2
Insurance policy | 8 | 1
Preliminary approval (Plant Nursery) or commercial license | 8 | 1
Site Lease (Plant Nursery) | 8 | 1
Proof of ownership (Plant Nursery) | 8 | 1
Trade License -Veterinary establishment | 8 | 1
Passport | 8 | 1
Phytosanitary certificate | 8 | 1
Germination and purity examination certificate | 8 | 1
bill of lading | 8 | 1
Customs manifest (Declaration) | 8 | 1
Delivery authorization | 8 | 1
Origin certificate | 8 | 1
Scientific certificates (Veterinary) | 8 | 1
Employment Contract | 8 | 1
Emirates Identity card | 8 | 1
Boat sailing license | 8 | 1
Industrial license (general) | 8 | 1
Declaration certificate for storing and transporting aquatic organisms | 8 | 1
Certificate of registration for slaughterhouse | 8 | 1
Certificate for food safety management | 8 | 1
Delisting certificate of maritime transport | 8 | 1
Technical inspection report by CICPA | 8 | 1
Salary certificate | 8 | 1
Certificate of unemployment | 8 | 1
Technical inspection certificate of fishing boat | 8 | 1
Certificate of good conduct | 8 | 1
Fishing License | 8 | 1
Medical fitness certificate | 8 | 1
Notification of inheritance | 8 | 1
Agent appointment certificate issued by the Sharia Court | 8 | 1
Medical inability certificate (Boat owner) | 8 | 1
GMP certificate | 8 | 1
* It takes approx 8-16 hrs to create a robot for document verfification |  | 50
Product analysis certificate
CITES certificate
Healt certificate
Certification of origin (Fishing tools)
Import permit
Free sale certificate
Veterinary health certificate
Customs declaration of consignment (Vegetable feed)
Horse passport
Vaccination document (horse)
NO Objection certificate from arabain horse assosiation
Packaging certificate (Fish processing factory)
Heat treatment certificate
Certificate of analysis for pesticide residues (Plant products)
Movement Document (Hazardous waste)
Notification document (Hazardous waste)
Import-export contract for hazardous material
Certificate of treatment (Animal product)
Veterinarian certificate (Non-treated animal products)
Immunization document
Certificate of composition (Phermones, pest control)
Certificate of analysis (Disinfectants)
Operating analysis certificate from the manufacturer Animal Samples
No Objection certificate from veterinary authority (Exporting Country)