## Web
|  | MOCCAE - WEB | 19/4/2020
Monday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 0
1 | Business analysis |  | 0 | Sr Developer | 1 | 0 |  | 3 | 0 | 0
2 | Project Management |  | 0 | Jr Developer | 1 | 0
3 | SRS,FS,User Manual |  | 0 | PM | 1 | 0
4 | UI / UX (Web & Moile IOS) |  | 0 | BA | 1 | 0
| Development |  |  | Tech writer | 1 | 0
5 | Application basic setup |  | 0 | QA | 1 | 0
| Website |  |  | Total | 7 | 0
LICENSING
| Renew Fishing Boat License |  | 0 | Effort | 0 | + 1 Day (Deployment)
| Accreditation of food establishment to export outside UAE - New |  | 0 | Delivery Time | 0 | + 1 Day (Deployment)
| Add or Replace Fishing Boat's Engine |  | 0
Agricultural Extension Request
Change Fishing Method
Issuance of Aquaculture Farm Establishment License
| Issue a License for Manufacturing a Fertilizer/Soil Conditioner |  | 0
Issue a license of practicing animal activity
| Issue a Plant Nursery License |  | 0
| Issue a Temporary License of a Practicing the Profession for Veterinarians |  | 0
Issue a Veterinary Establishment License
| Issue an Agricultural Activity License |  | 0
Issue an Export License (Local Aquatic Organisms’ Products)
Issue an Import Permit of Agricultural Consignment
| Issue Import License (Broodstock and Larvae/ Fishing Tools and Equipment) |  | 0
| Issuing a license for animal production farm |  | 0
| Issuing a license for practicing the profession for veterinarians and assisting veterinary professions |  | 0
| Modification or Cancellation of Basic Data of Agricultural Holdings |  | 0
Preliminary approval to license an animal production farm
Primary approval on licensing a veterinary facility
Registration of agricultural holdings
Renew Aquaculture Farm Establishment License
Renew Import License (Broodstock and Larvae/ Fishing Tools and Equipment)
Renew issuance license of practicing the profession for veterinarians and for the assistant vet
Renew Plant Nursery License
Renew Veterinary Establishment Licence
Renew Vice-Captain's Card
Renewal a License for Manufacture Fertilizers and Soil Conditioner
Renewal Issue a license of practicing animal activity
Renewal of Accreditation of food Establishment to Export Outside UAE
Renewal of agricultural activity license
Renewal of an Export License (Local Aquatic Organisms’ Products)
Renewal of Slaughterhouse Accreditation Outside UAE
Renewal of the license of an animal production farm
Replacement of Fishing Boat
Request ٍSubsidies for Farmers
Request ٍSubsidies for Fishermen’s
Sale of Fishing Boat's Body
Slaughterhouse Accreditation Outside UAE
Transfer Fishing Boat Ownership
Transfer Fishing Boat's Ownership to Heirs
Veterinary Extension Request
Vice-Captain Card Issuance
PERMITS
Adopting Veterinary Raw Materials for Importation
Apply for Release Permit (Fishing Tools and Equipment)
Approve Disinfectants, Veterinary Equipment and Supplies, and Animal Care Supplies for Distribution
Issuance Import permit for Semen or Embryos
Issuance of Re-export of Vegetable Feed Permission
Issue a Permanent or Temporary Horse import permit
Issue a Permit to Import Ozone Depleting Substances (ODS)
Issue a Permit to Import Pesticides
Issue a permit to re-export ozone depleting substances (ODS)
Issue a Re-Export Permit (Aquatic Organisms Products)
Issue an agricultural consignment release
Issue an Export Permit (Local Aquatic Organisms’ Products)
Issue an Export Permit of Hazardous Waste
Issue an Import Permit (Broodstock or Larvae)
Issue an Import Permit (Fishing Tools and Equipment)
Issue an Import Permit for Animal Products or By-Products
Issue an Import Permit for Feed and Processed Animal Feed
Issue an Import permit for live animals, Birds and Ornamental fish
Issue an Import Permit for Pets - Cats or Dogs
Issue an Import Permit of Fertilizers or Soil Conditioners (Restricted)
Issue an Import Permit of Fertilizers or Soil Conditioners (Unrestricted)
Issue an Import permit of Pheromones, Attracting materials, Extruding materials, Additives and Materials with mechanical or physical in pest control
Issue import permit for non-manufactured feed for aquatic organisms
| Issuing an Import Permit for Disinfectants, Veterinary Equipment and Supplies, and Animal Care Supplies | 12
| Issuing export permit of animal samples | 32
Issuing Import Permit for Veterinary Products
Issuing import permit of animal samples
Issuing Import Permit of Veterinary Raw Materials
Release of Locally Manufactured Fertilizers
CITES
Cancellation of Species Ownership Listed in CITES Appendices
Issue a CITES Export/Re-export Certificate
Issue a CITES Import Certificate
Issue a Falcon passport in accordance with the Federal Law on CITES
Issue a to whom it may concern letter in accordance with the federal law on CITES
Ownership Registration of Species Listed in CITES Appendices
Request for Falcon Identification Rings
Transfer Species Ownership Listed in CITES Appendices
CERTIFICATES
Approved of Phermions, Attracting materials, Extruding materials, Additives and Materials with mechanical or physical in pest control
Issuance of Good Manufacturing Certificate GMP
Issue a license to practice the profession of agricultural engineer and occupations related to agricultural activities
Issue a Registration Certificate for a Fertilizer or a Soil Conditioner
Issue a Veterinary Health Certificate for Exporting Equine Semen
Issue a Veterinary Health Certificate for Exporting or Re-Exporting Animal and Fish Products or byproducts and Manufactured Feed
Issue a Veterinary Health Certificate for Exporting or Re-Exporting Horses
Issue a Veterinary Health Certificate for Exporting or Re-Exporting Live Animals
Issue an Phytosanitary Certificate for Export or Re-Export
Issue Certificate of Heat Treatment Facility Approval
Issue license to re-export aquatic organisms
Issue Pesticide Registration Certificate
Issue Registration Certificate of Veterinary Product Companies
Issuing a Free Sale Certificate for a Veterinary Product
Issuing Registration Certificate of Veterinary Products
Renew license to re-export aquatic organisms
Renewal registration certificate of veterinary product
Renewal a license to practice the profession of agricultural engineer and occupations related to agricultural activities
Renewal of Good Manufacturing Certificate GMP
Renewal Registration Certificate of Veterinary Product Companies
Security
| Protection against injection attacks (SQL, CRLF) | 12 | 1.5
| URL encoding, Input validation | 6
| Cookie Encryption, Cookie replay attacks | 6 | 0.75
| Session hijacking prevention | 6 | 0.75
| Cross site scripting and session management | 6
Integration
Payment Integration
REDIS integraion
Minio Integration
Keycloak integration
ELK stack integration
TWILIO integration
OneSignal (optional)
Quality Assurance
| QA & Bug Fixing |  | 0
| UAT |  | 0
| Deployment per instance |  | 0
| Total Effort |  | 3
Assumptions
The effort may change after a detailed system study

## mobile
MOCCAE- Mobile |  | 2020-05-05
Tuesday
Module | Mobile |  |  | No | Man Days | Total Effort
| Hours | Man Days | Mobile Design (Different from UI/UX) | 1 | 4 | 4
Development |  |  | Sr Developer | 1 | 20 | 20 | 49.75 | 40 | 61.75 | 40
|  |  | Jr Developer | 1 | 20 | 20
Application basic setup | 8 | 1 | qa | 1 | 2 | 2
Registration/Create MOCCAE account | 8 | 1
Login with username and password or Login with UAE pass | 16 | 2
Chatbot and live chat | 20 | 2.5
PushNotification | 10 | 1.25
Help and support(faq and live chat) | 10 | 1.25
Happiness meter | 8 | 1
Dashboard | 10 | 1.25
Service Request Tracking Feature | 10 | 1.25
Events and News | 10 | 1.25
Rate and share | 12 | 1.5
Customer location,working hours and services to be displayed. | 16 | 2
Create Incident | 16 | 2
Welcome message as push notification(within 100M range) | 10 | 1.25
Contact us,privacy , terms and condition | 10 | 1.25
LICENSING |  |  | API Development | 1 | 20 | 20
Renew Fishing Boat License | 16 | 2 | Total |  |  | 66
Accreditation of food establishment to export outside UAE - New | 12 | 1.5 | Effort | 66 | + 1 Day (Deployment)
Add or Replace Fishing Boat's Engine | 12 | 1.5 | Delivery Time | 26 | + 1 Day (Deployment)
Agricultural Extension Request | 8 | 1
Change Fishing Method | 6 | 0.75
Issuance of Aquaculture Farm Establishment License | 10 | 1.25
Issue a License for Manufacturing a Fertilizer/Soil Conditioner | 10 | 1.25
Issue a license of practicing animal activity | 10 | 1.25
Issue a Plant Nursery License | 10 | 1.25
Issue a Temporary License of a Practicing the Profession for Veterinarians | 6 | 0.75
Issue a Veterinary Establishment License | 12 | 1.5
Issue an Agricultural Activity License | 10 | 1.25
Issue an Export License (Local Aquatic Organisms’ Products) | 6 | 0.75
Issue an Import Permit of Agricultural Consignment | 6 | 0.75
Issue Import License (Broodstock and Larvae/ Fishing Tools and Equipment) | 6 | 0.75
Issuing a license for animal production farm | 6 | 0.75
Issuing a license for practicing the profession for veterinarians and assisting veterinary professions | 6 | 0.75
Modification or Cancellation of Basic Data of Agricultural Holdings | 6 | 0.75
Preliminary approval to license an animal production farm | 10 | 1.25
Primary approval on licensing a veterinary facility | 10 | 1.25
Registration of agricultural holdings | 10 | 1.25
Renew Aquaculture Farm Establishment License | 6 | 0.75
Renew Import License (Broodstock and Larvae/ Fishing Tools and Equipment) | 6 | 0.75
Renew issuance license of practicing the profession for veterinarians and for the assistant vet | 6 | 0.75
Renew Plant Nursery License | 6 | 0.75
Renew Veterinary Establishment Licence | 6 | 0.75
Renew Vice-Captain's Card | 6 | 0.75
Renewal a License for Manufacture Fertilizers and Soil Conditioner | 6 | 0.75
Renewal Issue a license of practicing animal activity | 6 | 0.75
Renewal of Accreditation of food Establishment to Export Outside UAE | 6 | 0.75
Renewal of agricultural activity license | 6 | 0.75
Renewal of an Export License (Local Aquatic Organisms’ Products) | 6 | 0.75
Renewal of Slaughterhouse Accreditation Outside UAE | 6 | 0.75
Renewal of the license of an animal production farm | 6 | 0.75
Replacement of Fishing Boat | 6 | 0.75
Request ٍSubsidies for Farmers | 6 | 0.75
Request ٍSubsidies for Fishermen’s | 6 | 0.75
Sale of Fishing Boat's Body | 6 | 0.75
Slaughterhouse Accreditation Outside UAE | 6 | 0.75
Transfer Fishing Boat Ownership | 6 | 0.75
Transfer Fishing Boat's Ownership to Heirs | 6 | 0.75
Veterinary Extension Request | 6 | 0.75
Vice-Captain Card Issuance | 6 | 0.75
PERMITS
Adopting Veterinary Raw Materials for Importation | 10 | 1.25 | 222.3
Apply for Release Permit (Fishing Tools and Equipment) | 8 | 1
Approve Disinfectants, Veterinary Equipment and Supplies, and Animal Care Supplies for Distribution | 8 | 1
Issuance Import permit for Semen or Embryos | 10 | 1.25
Issuance of Re-export of Vegetable Feed Permission | 8 | 1
Issue a Permanent or Temporary Horse import permit | 8 | 1
Issue a Permit to Import Ozone Depleting Substances (ODS) | 8 | 1
Issue a Permit to Import Pesticides | 6 | 0.75
Issue a permit to re-export ozone depleting substances (ODS) | 8 | 1
Issue a Re-Export Permit (Aquatic Organisms Products) | 8 | 1
Issue an agricultural consignment release | 8 | 1
Issue an Export Permit (Local Aquatic Organisms’ Products) | 8 | 1
Issue an Export Permit of Hazardous Waste | 6 | 0.75
Issue an Import Permit (Broodstock or Larvae) | 8 | 1
Issue an Import Permit (Fishing Tools and Equipment) | 8 | 1
Issue an Import Permit for Animal Products or By-Products | 8 | 1
Issue an Import Permit for Feed and Processed Animal Feed | 8 | 1
Issue an Import permit for live animals, Birds and Ornamental fish | 6 | 0.75
Issue an Import Permit for Pets - Cats or Dogs | 6 | 0.75
Issue an Import Permit of Fertilizers or Soil Conditioners (Restricted) | 6 | 0.75
Issue an Import Permit of Fertilizers or Soil Conditioners (Unrestricted) | 6 | 0.75
Issue an Import permit of Pheromones, Attracting materials, Extruding materials, Additives and Materials with mechanical or physical in pest control | 8 | 1
Issue import permit for non-manufactured feed for aquatic organisms | 8 | 1
Issuing an Import Permit for Disinfectants, Veterinary Equipment and Supplies, and Animal Care Supplies | 8 | 1
Issuing export permit of animal samples | 8 | 1
Issuing Import Permit for Veterinary Products | 8 | 1
Issuing import permit of animal samples | 8 | 1
Issuing Import Permit of Veterinary Raw Materials | 8 | 1
Release of Locally Manufactured Fertilizers | 6 | 0.75
CITES
Cancellation of Species Ownership Listed in CITES Appendices | 8 | 1
Issue a CITES Export/Re-export Certificate | 8 | 1
Issue a CITES Import Certificate | 8 | 1
Issue a Falcon passport in accordance with the Federal Law on CITES | 6 | 0.75
Issue a to whom it may concern letter in accordance with the federal law on CITES | 6 | 0.75
Ownership Registration of Species Listed in CITES Appendices | 8 | 1
Request for Falcon Identification Rings | 8 | 1
Transfer Species Ownership Listed in CITES Appendices | 8 | 1
CERTIFICATES
Approved of Phermions, Attracting materials, Extruding materials, Additives and Materials with mechanical or physical in pest control | 8 | 1
Issuance of Good Manufacturing Certificate GMP | 8 | 1
Issue a license to practice the profession of agricultural engineer and occupations related to agricultural activities | 6 | 0.75
Issue a Registration Certificate for a Fertilizer or a Soil Conditioner | 8 | 1
Issue a Veterinary Health Certificate for Exporting Equine Semen | 8 | 1
Issue a Veterinary Health Certificate for Exporting or Re-Exporting Animal and Fish Products or byproducts and Manufactured Feed | 8 | 1
Issue a Veterinary Health Certificate for Exporting or Re-Exporting Horses | 8 | 1
Issue a Veterinary Health Certificate for Exporting or Re-Exporting Live Animals | 6 | 0.75
Issue an Phytosanitary Certificate for Export or Re-Export | 8 | 1
Issue Certificate of Heat Treatment Facility Approval | 8 | 1
Issue license to re-export aquatic organisms | 6 | 0.75
Issue Pesticide Registration Certificate | 8 | 1
Issue Registration Certificate of Veterinary Product Companies | 8 | 1
Issuing a Free Sale Certificate for a Veterinary Product | 6 | 0.75
Issuing Registration Certificate of Veterinary Products | 6 | 0.75
Renew license to re-export aquatic organisms | 8 | 1
Renewal registration certificate of veterinary product | 8 | 1
Renewal a license to practice the profession of agricultural engineer and occupations related to agricultural activities | 8 | 1
Renewal Registration Certificate of Veterinary Product Companies | 8 | 1
Renewal of Good Manufacturing Certificate GMP | 8 | 1
Integration of Emirates ID | 20 | 2.5
Integration with portal CMS | 20 | 2.5
Integration with mail/exchange server | 20 | 2.5
Integration of Bio-Security | 20 | 2.5
Integration with current eservices | 20 | 2.5
Integration with qmatic system | 20 | 2.5
Integration of happiness meter sdk | 20 | 2.5
Integration of UAE pass | 24 | 3
Payment Gateway Integartion | 24 | 3
Bilingual (English and Arabic) | 16 | 2
Quality Assurance
QA & Bug Fixing | 452 | 56.5
UAT | 0 | 0
Deployment per instance | 0 | 0
Total Effort | 1582 | 197.75
Assumptions 1.The estimated time may vary with change in functionality. 2.The estimation is for portrait mode.