## EYCC
MOCCAE |  | 2019-04-20
Saturday
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Designer | 1.5 | 15 | 22.5
Business Analysis | 40 | 5 | Sr Developer | 2 | 40 | 80 | 161 | 178.1 | 161 | 162
Project Management | 128.8 | 16.1 | Jr Developer | 2 | 41 | 82
Design and Prototype | 120 | 15 | PM | 1 | 16.1 | 16.1
Documentation (SRS, FS, Weekly Reports, User Manual) | 48 | 6 | BA | 1 | 5 | 5
Development |  |  | TechWriter | 1 | 6 | 6
BEEATNA.AE (Static pages) |  |  | QA | 2 | 32.65 | 65.3
Home Page | 24 | 3
UAE Environment | 6 | 0.75 | Total |  | 155.75 | 276.9
Defenition of climate change | 8 | 1 |  |  | 0
National efforts to address climate change | 8 | 1 | [7 empty] | BA + UI/UX | 27.5
Biodiversity and environment | 6 | 0.75
National Biodiversity Strategy | 6 | 0.75
Air quality | 6 | 0.75 |  |  | 3 | days for deployment
Wastes and chemicals | 4 | 0.5 |  | Days | Months
Food safety | 4 | 0.5 | Total Delivery Days | 93.65 | 4.6825
Agriculture development and health | 4 | 0.5 | Total Effort | 276.9
Animal development and health | 4 | 0.5
Marine environement and fisheries sustainability | 4 | 0.5
Ecotourism | 4 | 0.5
Environmental authorities | 4 | 0.5
Environmental-Authorities-in-UAE | 4 | 0.5
Envronmental reports | 4 | 0.5
Events | 4 | 0.5
Seniar | 4 | 0.5
terms and conditions | 2 | 0.25
Privacy policy | 2 | 0.25
Contact Us | 16 | 2
Social media links | 2 | 0.25
Bilingual | 16 | 2
Google Translate plugin | 12 | 1.5
MOCCAE.gov.ae
CMS for dynamic content
Services content pages | 16 | 2
About the ministry Pages | 16 | 2
Add new legislations | 16 | 2
Knowledge with | 24 | 3
Related legislations |  | 0
Strategies |  | 0
Initiatives & projects |  | 0
Conventions |  | 0
Reports and studies |  | 0
Bulletins / guides |  | 0
Terminology |  | 0
Knowledge -> Biosecurity | 16 | 2
Manage Terminology | 16 | 2
Blog | 16 | 2
Polls | 16 | 2
surveys | 16 | 2
Video library | 16 | 2
Photo Gallery | 8 | 1
News | 8 | 1
Publications | 8 | 1
Logos | 8 | 1
Activities and Events | 16 | 2
Audio Gallery | 12 | 1.5
Archive | 16 | 2
Initiatives | 16 | 2
Open Data | 16 | 2
Government Links | 8 | 1
Manage appointments | 16 | 2
Happiness center | 16 | 2
Post careers | 16 | 2
English / Arabic | 72 | 9
Projects page (New) | 16 | 2
50th Plan | 12 | 1.5
Seminars | 12 | 1.5
IRINA | 12 | 1.5
Establishment License service | 12 | 1.5
Metadata Services | 12 | 1.5
Registered Dertilizers service | 12 | 1.5
Slaughterhouse Service | 12 | 1.5
Static Content & Page templates
Knowledge -> Biosecurity | 8 | 1
Social media | 8 | 1
Eparticipation (8 Pages) | 32 | 4
GIS MAP | 6 | 0.75
Request Data | 6 | 0.75
Submit Data | 6 | 0.75
Register | 8 | 1
Login | 8 | 1
Search Advanced Search | 16 | 2
Contact | 4 | 0.5
Sitemap | 4 | 0.5
Accessibility Settings | 16 | 2
Personalize | 24 | 3
Night Mode | 24 | 3
Social media | 4 | 0.5
RSS Feeds | 4 | 0.5
Remarks and suggestions | 4 | 0.5
Share | 4 | 0.5
Chatbot | 12 | 1.5
Chat | 12 | 1.5
Print page | 4 | 0.5
Font settings | 12 | 1.5
Home page | 40 | 5
About the ministry | 8 | 1
Legislation | 8 | 1
Our services | 24 | 3
Knowledge | 8 | 1
E-Participation | 12 | 1.5
Media center | 8 | 1
Open Data | 12 | 1.5
Book Appointments | 12 | 1.5
Electronic refunds | 12 | 1.5
Eservice user manual | 8 | 1
View appointment | 8 | 1
Subscribe to news letter | 6 | 0.75
Call US | 4 | 0.5
Copyright notice | 4 | 0.5
Privacy | 4 | 0.5
terms & conditions | 4 | 0.5
Disclaimer | 4 | 0.5
Visitor count | 2 | 0.25
FAQ | 12 | 1.5
contact Us | 4 | 0.5
Careers | 12 | 1.5
Search Legislations | 12 | 1.5
Terminology | 12 | 1.5
newsletter | 8 | 1
New Requirements (Templates)
Web page for Projects (template) | 14 | 1.75
50th Plan | 14 | 1.75
Seminars | 14 | 1.75
IRINA | 14 | 1.75
Establishment License | 12 | 1.5
Registered Fertilizers | 12 | 1.5
Slaughterhouse | 12 | 1.5
Administraion
User Management | 20 | 2.5
Authentication and Authorization | 16 | 2
Logging and Auditing | 12 | 1.5
Tags & Category Management | 12 | 1.5
0
Quality Assurance
QA & Bug Fixing (Functional testing + Performance testing + Compatibility testing with well known Devices and Browsers) | 442.4 | 55.3
UAT | 80 | 10
Deployment per instance | 24 | 3
Total Effort |  | 271.4
Assumptions
The effort might change after a detailed system study
The sample format for extraction of bills and PBX records will be provided during the system study
Please check if the client use AD for authentication/ Or we might need to do the usermanagement

## Schedule
Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5
Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15 | Wk16 | Wk17 | Wk18 | Wk19 | Wk20
Discovery + Plan |  |  | Structure + Prototyping |  |  |  | Implementation | [7 empty] | Closure
`