## EYCC
MOCCAE |  | 2019-04-20
Saturday
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Designer | 1.5 | 10 | 15
Business Analysis | 40 | 5 | Sr Developer | 2 | 38 | 76 | 153.375 | 169.3375 | 153.375 | 154
Project Management | 122.7 | 15.3375 | Jr Developer | 2 | 39 | 78
Design and Prototype | 120 | 15 | PM | 1 | 15.3375 | 15.3375
Documentation (SRS, FS, Weekly Reports, User Manual) | 40 | 5 | BA | 1 | 5 | 5
Development |  |  | TechWriter | 1 | 5 | 5
BEEATNA.AE (Static pages) |  |  | QA | 2 | 31.3156 | 62.6313
Home Page | 24 | 3
UAE Environment | 6 | 0.75 | Total |  | 143.6531 | 256.9688
Defenition of climate change | 8 | 1 |  |  | 0
National efforts to address climate change | 8 | 1 | [7 empty] | BA + UI/UX | 20
Biodiversity and environment | 6 | 0.75
National Biodiversity Strategy | 6 | 0.75
Air quality | 6 | 0.75 |  |  | 3 | days for deployment
Wastes and chemicals | 4 | 0.5 |  | Days | Months
Food safety | 4 | 0.5 | Total Delivery Days | 85.3156 | 4.2658
Agriculture development and health | 4 | 0.5 | Total Effort | 256.9688
Animal development and health | 4 | 0.5
Marine environement and fisheries sustainability | 4 | 0.5
Ecotourism | 4 | 0.5
Environmental authorities | 4 | 0.5
Environmental-Authorities-in-UAE | 4 | 0.5
Envronmental reports | 4 | 0.5
Events | 4 | 0.5
Seniar | 4 | 0.5
Terms and conditions | 2 | 0.25
Privacy policy | 2 | 0.25
Contact Us | 6 | 0.75
Social media links | 0 | 0
Bilingual | 20 | 2.5
Google Translate plugin | 8 | 1
MOCCAE.gov.ae
CMS for dynamic content
Services content pages | 16 | 2
About the ministry Pages | 16 | 2
Add new legislations | 16 | 2
Knowledge with | 24 | 3
Related legislations |  | 0
Strategies |  | 0
Initiatives & projects |  | 0
Conventions |  | 0
Reports and studies |  | 0
Bulletins / guides |  | 0
Terminology |  | 0
Knowledge -> Biosecurity | 16 | 2
Manage Terminology | 16 | 2
Blog | 16 | 2
Polls | 16 | 2
surveys | 16 | 2
Video library | 16 | 2
Photo Gallery | 8 | 1
News | 8 | 1
Publications | 8 | 1
Logos | 8 | 1
Activities and Events | 16 | 2
Audio Gallery | 12 | 1.5
Archive | 16 | 2
Initiatives | 16 | 2
Open Data | 16 | 2
Government Links | 8 | 1
Manage appointments | 16 | 2
Happiness center | 16 | 2
Post careers | 16 | 2
English / Arabic | 72 | 9
Projects page (New) | 16 | 2
50th Plan | 12 | 1.5
Seminars | 12 | 1.5
IRINA | 12 | 1.5
Establishment License service | 12 | 1.5
Metadata Services | 12 | 1.5
Registered Dertilizers service | 12 | 1.5
Slaughterhouse Service | 12 | 1.5
Static Content & Page templates
Social media | 8 | 1
Eparticipation (8 Pages) | 32 | 4
GIS MAP | 6 | 0.75
Request Data | 6 | 0.75
Submit Data | 6 | 0.75
Register | 8 | 1
Login | 8 | 1
Search Advanced Search | 16 | 2
Contact | 4 | 0.5
Sitemap | 4 | 0.5
Accessibility Settings | 20 | 2.5
Personalize | 24 | 3
Night Mode | 24 | 3
Social media | 4 | 0.5
RSS Feeds | 4 | 0.5
Remarks and suggestions | 4 | 0.5
Share | 2 | 0.25
Chatbot | 6 | 0.75
Chat | 6 | 0.75
Print page | 4 | 0.5
Font settings | 12 | 1.5
Home page | 32 | 4
About the ministry | 8 | 1
Legislation | 8 | 1
Our services | 24 | 3
Knowledge | 8 | 1
E-Participation | 12 | 1.5
Media center | 8 | 1
Open Data | 12 | 1.5
Book Appointments | 12 | 1.5
Electronic refunds | 12 | 1.5
Eservice user manual | 8 | 1
View appointment | 8 | 1
Subscribe to news letter | 6 | 0.75
Call US | 2 | 0.25
Copyright notice | 2 | 0.25
Privacy | 2 | 0.25
terms & conditions | 2 | 0.25
Disclaimer | 2 | 0.25
Visitor count | 1 | 0.125
FAQ | 8 | 1
contact Us | 4 | 0.5
Careers | 12 | 1.5
Search Legislations | 12 | 1.5
Terminology | 12 | 1.5
New Requirements (Templates)
Web page for Projects (template) | 14 | 1.75
50th Plan | 14 | 1.75
Seminars | 14 | 1.75
IRINA | 14 | 1.75
Establishment License | 12 | 1.5
Registered Fertilizers | 12 | 1.5
Slaughterhouse | 12 | 1.5
Administraion
User Management | 20 | 2.5
Authentication and Authorization | 16 | 2
Logging and Auditing | 12 | 1.5
Tags & Category Management | 12 | 1.5
0
Quality Assurance
QA & Bug Fixing (Functional testing + Performance testing + Compatibility testing with well known Devices and Browsers) | 421.05 | 52.6313
UAT | 80 | 10
Deployment per instance | 24 | 3
Total Effort |  | 259.3438
Assumptions
The effort might change after a detailed system study

## Schedule
Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5
Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9 | Wk10 | Wk11 | Wk12 | Wk13 | Wk14 | Wk15 | Wk16 | Wk17 | Wk18 | Wk19 | Wk20
Discovery + Plan |  |  | Structure + Prototyping |  |  |  | Implementation | [7 empty] | Closure
`