## EYCC
MOE-Early Years Child Care |  | 2019-04-20
Saturday
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Designer | 1 | 10 | 10
Business Analysis | 24 | 3 | Sr Developer | 1 | 16 | 16 | 0 | 36 | 0 | 36
Project Management | 0 | 0 | Jr Developer | 1 | 20 | 20
Design and Prototype | 80 | 10 | PM | 1 | 0 | 0
Documentation (SRS, FS, Weekly Reports, User Manual) | 48 | 6 | BA | 1 | 3 | 3
Development |  |  | TechWriter | 1 | 6 | 6
User management (Users and Roles) |  |  | QA | 1 | 0 | 0
Schools
EYCC Coordinators |  |  | Total |  | 55 | 0
IT Support |  |  | Total Delivery days | 30
Evaluators / Inspectors
Evaluator Leads
QA
Report Editors |  |  | Total Effort | 0 | (+1 Day deployment)
System Functions
School Calendar Management (National Holidays, School holidays, Events, reminders)
Document management (versions, category, tags, school, process - subprocess type, Sharing etc)
Quality Assurance
QA & Bug Fixing | 0 | 0
UAT | 32 | 4
Deployment per instance | 16 | 2
Total Effort |  | 25
Assumptions
The effort might change after a detailed system study
The sample format for extraction of bills and PBX records will be provided during the system study
Please check if the client use AD for authentication/ Or we might need to do the usermanagement