## EYCC
MOE-Early Years Child Care |  | 2019-04-20
Saturday
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Designer | 1 | 15 | 15
Business Analysis (Web + Mobile) | 40 | 5 | Sr Developer | 1 | 60 | 60 | 111 | 132 | 120 | 120
Project Management | 96 | 12 | Jr Developer | 1 | 60 | 60
Design and Prototype (WEB + Mobile) | 120 | 15 | PM | 1 | 12 | 12
Documentation (SRS, FS, Weekly Reports, User Manual) | 48 | 6 | BA | 1 | 5 | 5
Development |  |  | TechWriter | 1 | 6 | 6
User management (Users and Roles front end) |  |  | QA | 1.5 | 28 | 42
Schools | 8 | 1
EYCC Coordinators | 8 | 1 | Total |  | 186 | 200
IT Support | 8 | 1 | Total Delivery days | 103 | 5.15
Evaluators / Inspectors profiles | 8 | 1
Evaluator Leads | 8 | 1
QA | 8 | 1
Report Editors | 16 | 2 | Total Effort | 200 | (+1 Day deployment)
Inspection Cycles | 16 | 2
Inspection Cycles - Schools | 16 | 2
Task Creation | 16 | 2
Tasks - Inspections | 16 | 2
Inspection Cycles - Tasks - Schools | 16 | 2
Teams & team leads | 16 | 2
Document Categories | 16 | 2
Aspect Descriptors (Outstanding, very good etc.) | 16 | 2
School information categories and sub categories | 16 | 2
Flexible weighing systems | 16 | 2
School Management |  | 0
School Calendar Management (National Holidays, School holidays, Events, reminders) | 16 | 2
Document management (versions, category, tags, school, process - subprocess type, Sharing etc) | 16 | 2
Messaging | 16 | 2
Staff on duty | 16 | 2
Staff turnover | 16 | 2
School information submission (Assessment, attendance, behavioral etc.) | 16 | 2
Self Evaluation Forms | 16 | 2
Inspection Reports | 16 | 2
Self improvement planning | 16 | 2
Evaluation Criteria |  | 0
Standards | 16 | 2
Indicators (Evaluation Category) | 16 | 2
Elements (Evaluation Subcategory) | 16 | 2
Quality Descriptors | 16 | 2
Journal entries | 16 | 2
Judgments | 16 | 2
System |  | 0
Archiving | 8 | 1
Offline mode | 8 | 1
Intelligent Search | 16 | 2
Authentication and Authorization | 8 | 1
Auditing and logging | 8 | 1
exception handling | 8 | 1
Pre-inspection / Evaluation |  | 0
Team creation | 16 | 2
Team assignments | 16 | 2
Pre Evaluation briefing | 16 | 2
PEB approval | 16 | 2
Pre inspection activity | 16 | 2
Record Evidence |  | 0
Activity based electronic evidence | 16 | 2
eERF's for lesson observation, learning walking, document analysis, work evaluation, discussion, data analysis etc. | 16 | 2
Record evidence and narratives | 16 | 2
Calculation Engine |  | 0
Generate average judgements from multiple aspects (integer or otherwise) | 16 | 2
Generate indicator judgements | 16 | 2
Judgements by school | 16 | 2
Reports, heat maps etc. | 16 | 2
Add Judgement formula | 16 | 2
Dashboards |  | 0
Reporting platform with emerging judgments at element and indicator levels | 16 | 2
QA platform that supports search and triangulation | 16 | 2
Reports with filters, sorting | 16 | 2
Export reports (CSV, PDF) | 16 | 2
Offline mode for mobile apps | 16 | 2
Mobile API | 80 | 10
Bilingual | 72 | 9
Quality Assurance |  | 0
QA & Bug Fixing | 336 | 42
UAT | 32 | 4
Deployment per instance | 16 | 2
Total Effort |  | 206
Assumptions
The effort might change after a detailed system study
The sample format for extraction of bills and PBX records will be provided during the system study
Please check if the client use AD for authentication/ Or we might need to do the usermanagement

## Mobile
Development | Hours | Days
Dashboards
School | 8 | 1 | IOS developer | 1 | 56 | 56
QA | 8 | 1 | PM | 1 | 4.6 | 4.6
IT Support | 8 | 1 | BA | 1 | 3 | 3
Evaluator Leads | 8 | 1 | TechWriter | 1 | 3 | 3
Jotter | 8 | 1 | QA | 1.5 | 13.7333 | 20.6
Subject Evidence | 8 | 1
lesson observation | 8 | 1 | Total |  | 80.3333 | 87.2
Phase 3 | 8 | 1
Phase 4 | 8 | 1 | delivery time | 72.7333 | 3.6367
ERF Subject Data | 8 | 1 | Total Effort | 87.2
Social judgements indicators | 8 | 1
Data Analysis | 0 | 0
internal attainment | 8 | 1
external attainment | 8 | 1
NAP attainment | 8 | 1
Discussion | 0 | 0
Heads of subject | 8 | 1
Student after one lesson | 8 | 1
Work Evaluation |  | 0
Phase 3 | 8 | 1
Phase 4 | 8 | 1
Learning skills | 8 | 1
attainment | 8 | 1
progress | 8 | 1
Document Analysis |  | 0
Curriculum | 8 | 1
Self evaluation | 8 | 1
School improvement | 8 | 1
Curriculum adaptation | 8 | 1
Subject leadership (operational) | 8 | 1
Subject leadership (Educational) | 8 | 1
Indicator Journal (IJ) |  | 0
Discussion |  | 0
Students | 8 | 1
teachers | 8 | 1
parents | 8 | 1
Documents |  | 0
Student suryey | 8 | 1
Student community activity | 8 | 1
Extra curricular | 8 | 1
Health | 8 | 1
Attendance and punctuality | 8 | 1
Observations |  | 0
Health & Safety | 8 | 1
Assemblies | 8 | 1
Canteen & common areas | 8 | 1
Judgments |  | 0
IJ:Moral education & Well being | 8 | 1
IJ:curriculum | 8 | 1
ERF Documents |  | 0
Prompts | 8 | 1
Surveys | 8 | 1
Extra & co-curricular | 8 | 1
Pre-inspection briefing (PIB) |  | 0
PIB-Social studies | 8 | 1
PIB-Moral development and well being | 8 | 1
PIB-curriculum | 8 | 1
Offline mode | 40 | 5
Bilingual | 40 | 5
QA | 156.8 | 19.6
Deployment | 8 | 1
Total | 612.8 | 76.6