## MOE
| Scholarship Student Record System |  | 14/62020
Sunday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 10 | 10
1 | Business analysis | 40 | 5 | Sr Developer | 1 | 32 | 32 | 92 | 101.2 | 92 | 92
2 | Project Management | 73.6 | 9.2 | Jr Developer | 1.5 | 40 | 60
3 | SRS,FS,User Manual | 40 | 5 | PM | 1 | 9.2 | 9.2
4 | Design and Prototype | 80 | 10 | BA | 1 | 5 | 5
| Development |  |  | Tech writer | 1 | 5 | 5
5 | Application basic setup | 8 | 1 | QA | 2 | 19.6 | 39.2
| Student Profile |  |  | Total | 8.5 | 120.8 | 160.4
| Bio Demographics - Name, Country, Contact details at the time of registration etc. | 6 | 0.75
| Academic Details - Details of the institution where they are enrolled, duration of study etc. | 6 | 0.75 | Effort | 160.4 | + 1 Day (Deployment)
| Visa and Passport Details – Details of students passport and UAE visa | 6 | 0.75 | Delivery Time | 74.6 | + 1 Day (Deployment)
| send notification alerts to users before expiry of the visa. | 6 | 0.75
| Bank Account details | 6 | 0.75
| Language Test details | 6 | 0.75
| Employment history | 4 | 0.5
| General Attachments | 3 | 0.375
| Known Languages | 3 | 0.375
| Decree Details | 2 | 0.25
| Allowances paid to the student – including allowance types, amount, periodic / non-periodic etc.B65 | 4 | 0.5
| High School Graduation Details | 2 | 0.25
| Health insurance Details – Option to send notification alerts before expiry | 2 | 0.25
| Transcripts –recording of detailed transcript for different years, and attachments against each record. | 2 | 0.25
| Warnings issued – Details of warnings issued to the student | 6 | 0.75
| Application number: Reference number for tracking purposes | 2 | 0.25
Student e-services / Self-Service for students
| Login, forgot pwd, remember pwd | 6 | 0.75
| Raising requests, complaints, sending suggestions or inquiries, submitting feedback | 16 | 2
| Update profile(after approval in some cases) | 6 | 0.75
| Submit Request | 6 | 0.75
| Fill forms | 4 | 0.5
| View application status (In Progress / Accepted / Rejected) | 4 | 0.5
| Receive notification alerts upon action on the request | 6 | 0.75
Admin Functions
| Add users (other admins) and University Team members granting them access to the system | 8 | 1
| Import student profiles to populate data for each student | 8 | 1
| View / Edit Student profiles | 8 | 1
| Manage Lookups like Universities, Embassies, Specialization, Majors, Contact Type etc. | 8 | 1
| Manage User permissions and access | 16 | 2
| Manage application labels and fields | 16 | 2
| Manage service catalogue requests by creating forms with different types of fields as per the service | 16 | 2
| Configuring workflow approval to service requests | 16 | 2
| Adding acceptance criteria for each stage of the service request | 16 | 2
| Assigning system users as approvers for acceptance criteria | 8 | 1
| Assigning SLA for acceptance criteria | 8 | 1
| Form builder to create different types of forms | 40 | 5
0
University Admin functions
| Receive notification alerts (actions to submitted forms by students) | 6 | 0.75
| View student profiles of all students assigned to their universities | 8 | 1
| Based on permissions granted, add / edit / delete functionality on student profiles | 8 | 1
| Dashboard displays all open and closed applications (with statuses) for e-service requests raised by students under their admin | 16 | 2
| Accept / reject / request more information / return for correction for the requests that are in their queue | 6 | 0.75
Embassy users Access
| Receive notification alerts (actions to submitted forms by students) | 6 | 0.75
| View student profiles of all students from their countries | 8 | 1
| Based on permissions granted, add / edit / delete functionality on student profiles | 8 | 1
| Access to a dashboard that displays all open and closed applications (with statuses) for e-service requests raised by students under their admin | 24 | 3
| Accept / reject / request more information / return for correction for the requests that are in their queue | 6 | 0.75
Ministry of Foreign Affairs users Access
| Dashboard and report access | 32 | 4
Usability Requirements
| Mobile responsive | 6 | 0.75
| Exception handling | 6 | 0.75
| Prompt error messages | 6 | 0.75
| in app notification | 6 | 0.75
Security requirements
| role base access control (RBAC) for application logs | 6 | 0.75
| Secure Integration connections | 6 | 0.75
| System level access Audit logs | 6 | 0.75
| Proper user and group access management. | 6 | 0.75
| capture activity dates and activity users,maintain the audit tables for all transactional related data | 6 | 0.75
| Access Logs | 16 | 2
| Date and time of access | 0 | 0
| Source IP – End user IP address | 0 | 0
| Destination Port - The server port number that is configured for the service | 0 | 0
| User name - The name of the authenticated user who accessed your server | 0 | 0
| URI Stem - The target of the action, for example, Default.htm | 0 | 0
| HTTP Status | 0 | 0
| Method - The requested action (like Get/Post) | 0 | 0
| Bytes Sent - The number of bytes that the server sent | 0 | 0
| Bytes Received - The number of bytes that the server received | 0 | 0
| Time Taken - The length of time that the action took | 0 | 0
| User-Agent - The browser type that the client used | 0 | 0
| Protocol Sub status - The sub status error code | 0 | 0
| Audit Logs | 12 | 1.5
| User authentication details | 0 | 0
| User creation/deletion | 0 | 0
| User creation/deletion | 0 | 0
| Admin user changes | 0 | 0
| Modifications initiated by other users (optional) | 0 | 0 | [7 empty] | exception handling and such
auditing and logging
Configuration Requirements
| Deployed as Docker containers. | 16 | 2
Integration Requirements
| Integration with AD, SSO, Future identity & access management systems | 16 | 2
| E-mail, SMS & messaging apps integration | 16 | 2
| MOE internal/external applications via API (3 hrs / integration): Total 10 considered | 30 | 3.75
| SOC integration(security) | 8 | 1
Security
| Protection against injection attacks (SQL, CRLF) | 6 | 0.75
| URL encoding, Input validation | 6 | 0.75
| Cookie Encryption, Cookie replay attacks | 6 | 0.75
| Session hijacking prevention | 6 | 0.75
| Cross site scripting and session management | 6 | 0.75
System
| Authentication, Authorization, Entitlements | 12 | 1.5
| Exception logging & error handling | 12 | 1.5
| Payment gateway Integration | 12 | 1.5
| Document management | 12 | 1.5
| Search engine | 12 | 1.5
| Reporting engine | 12 | 1.5
| Communication / Message management | 12 | 1.5
| SMS gateway integration | 18 | 2.25
| Workflow management | 18 | 2.25
Quality Assurance
| QA & Bug Fixing | 257.6 | 32.2
| UAT | 40 | 5
| Deployment per instance | 16 | 2
| Total Effort |  | 160.4
Assumptions
The effort may change after a detailed system study

## MOE-Scalable
| Scholarship Student Record System |  | 14/62020
Sunday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 10 | 10
1 | Business analysis | 40 | 5 | Sr Developer | 1 | 35 | 35 | 95 | 104.5 | 95 | 95
2 | Project Management | 76 | 9.5 | Jr Developer | 1.5 | 40 | 60
3 | SRS,FS,User Manual | 40 | 5 | PM | 1 | 9.5 | 9.5
4 | Design and Prototype | 80 | 10 | BA | 1 | 5 | 5
| Development |  |  | Tech writer | 1 | 5 | 5
5 | Application basic setup | 8 | 1 | QA | 2 | 20.125 | 40.25
| Student Profile |  |  | Total | 8.5 | 124.625 | 164.75
| Bio Demographics - Name, Country, Contact details at the time of registration etc. | 6 | 0.75
| Academic Details - Details of the institution where they are enrolled, duration of study etc. | 6 | 0.75 | Effort | 164.75 | + 1 Day (Deployment)
| Visa and Passport Details – Details of students passport and UAE visa | 6 | 0.75 | Delivery Time | 75.125 | + 1 Day (Deployment)
| send notification alerts to users before expiry of the visa. | 6 | 0.75
| Bank Account details | 6 | 0.75
| Language Test details | 6 | 0.75
| Employment history | 4 | 0.5
| General Attachments | 3 | 0.375
| Known Languages | 3 | 0.375
| Decree Details | 2 | 0.25
| Allowances paid to the student – including allowance types, amount, periodic / non-periodic etc.B65 | 4 | 0.5
| High School Graduation Details | 2 | 0.25
| Health insurance Details – Option to send notification alerts before expiry | 2 | 0.25
| Transcripts –recording of detailed transcript for different years, and attachments against each record. | 2 | 0.25
| Warnings issued – Details of warnings issued to the student | 6 | 0.75
| Application number: Reference number for tracking purposes | 2 | 0.25
Student e-services / Self-Service for students
| Login, forgot pwd, remember pwd | 6 | 0.75
| Raising requests, complaints, sending suggestions or inquiries, submitting feedback | 16 | 2
| Update profile(after approval in some cases) | 6 | 0.75
| Submit Request | 6 | 0.75
| Fill forms | 4 | 0.5
| View application status (In Progress / Accepted / Rejected) | 4 | 0.5
| Receive notification alerts upon action on the request | 6 | 0.75
Admin Functions
| Add users (other admins) and University Team members granting them access to the system | 8 | 1
| Import student profiles to populate data for each student | 8 | 1
| View / Edit Student profiles | 8 | 1
| Manage Lookups like Universities, Embassies, Specialization, Majors, Contact Type etc. | 8 | 1
| Manage User permissions and access | 16 | 2
| Manage application labels and fields | 16 | 2
| Manage service catalogue requests by creating forms with different types of fields as per the service | 16 | 2
| Configuring workflow approval to service requests | 16 | 2
| Adding acceptance criteria for each stage of the service request | 16 | 2
| Assigning system users as approvers for acceptance criteria | 8 | 1
| Assigning SLA for acceptance criteria | 8 | 1
| Form builder to create different types of forms | 12 | 1.5
0
University Admin functions
| Receive notification alerts (actions to submitted forms by students) | 6 | 0.75
| View student profiles of all students assigned to their universities | 8 | 1
| Based on permissions granted, add / edit / delete functionality on student profiles | 8 | 1
| Dashboard displays all open and closed applications (with statuses) for e-service requests raised by students under their admin | 16 | 2
| Accept / reject / request more information / return for correction for the requests that are in their queue | 6 | 0.75
Embassy users Access
| Receive notification alerts (actions to submitted forms by students) | 6 | 0.75
| View student profiles of all students from their countries | 8 | 1
| Based on permissions granted, add / edit / delete functionality on student profiles | 8 | 1
| Access to a dashboard that displays all open and closed applications (with statuses) for e-service requests raised by students under their admin | 24 | 3
| Accept / reject / request more information / return for correction for the requests that are in their queue | 6 | 0.75
Ministry of Foreign Affairs users Access
| Dashboard and report access | 32 | 4
Usability Requirements
| Mobile responsive | 6 | 0.75
| Exception handling | 6 | 0.75
| Prompt error messages | 6 | 0.75
| in app notification | 6 | 0.75
Configuration Requirements
| Deployed as Docker containers / Docker Swarm | 20 | 2.5
Integration Requirements
| Integration with AD, SSO, Future identity & access management systems | 16 | 2
| E-mail, SMS & messaging apps integration | 16 | 2
| MOE internal/external applications via API (3 hrs / integration): Total 10 considered | 30 | 3.75
| SOC integration(security) | 8 | 1
Security
| Protection against injection attacks (SQL, CRLF) | 6 | 0.75
| URL encoding, Input validation | 6 | 0.75
| Cookie Encryption, Cookie replay attacks | 6 | 0.75
| Session hijacking prevention | 6 | 0.75
| Cross site scripting and session management | 6 | 0.75
| Authentication, Authorization, Entitlements (All Users) | 16 | 2
| Auditing and Logging | 16 | 2
System
| Identity Server Integration (SSO + AD, LDAP etc.) | 32 | 4
| MS Workflow Engine (Form and workflow designer) | 32 | 4
| ELK Stack Integration (Serach , Log Aggregation, Analytics) | 32 | 4
| Payment gateway Integration | 16 | 2
| MInIO Integration | 32 | 4
| Reporting (Tableu) | 32 | 4
| SMS gateway integration | 18 | 2.25
| Quality Assurance | [9 empty] | exception handling and such
| QA & Bug Fixing | 266 | 33.25 | [7 empty] | auditing and logging
| UAT | 40 | 5
| Deployment per instance | 16 | 2
| Total Effort |  | 164.75
Assumptions
Not inclusive of product prices