## Web
| MOE Founder Award |  | 19/4/2020
Monday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 10 | 10
1 | Business analysis | 40 | 5 | Sr Developer | 1 | 35 | 35 | 107.5 | 118.75 | 107.5 | 108
2 | Project Management | 86 | 10.75 | Jr Developer | 2 | 36.5 | 73
3 | SRS,FS,User Manual | 24 | 3 | PM | 1 | 10.75 | 10.75
4 | Design(Infographics,responsive) and Prototype | 80 | 10 | BA | 1 | 5 | 5
| Development |  |  | Tech writer | 1 | 3 | 3
5 | Application basic setup | 8 | 1 | QA | 1.5 | 28.4167 | 42.625
| Front end |  |  | Total | 8.5 | 128.6667 | 179.375
| Home page | 32 | 4
| Contact Us | 4 | 0.5 | Effort | 179.375 | + 1 Day (Deployment)
| About Us including award timelines | 4 | 0.5 | Delivery Time | 79.9167 | + 1 Day (Deployment)
| Award Main Categories with listing and details page for each | 4 | 0.5
| Application/participation form for each award | 8 | 1
| Login and registration (to participate in an award) via local membership provider or UAE pass | 24 | 3
| FAQs | 16 | 2
Media Centre
| Upcoming events and workshops with (Photo & Video Gallery) | 24 | 3
| Winners of previous editions with (Photo & Video Gallery) | 16 | 2
| Social media links | 4 | 0.5
Backend/Super Amin
| User Roles Management(Add/update/delete) | 6 | 0.75
| Super admin (personal details,status,etc) | 6 | 0.75
| Business admin (personal details,status,etc) | 6 | 0.75
| Editor (personal details,status,etc) | 6 | 0.75
| Assessor (personal details,status,etc) | 6 | 0.75
| Reviewer (personal details,status,etc) | 6 | 0.75
| Approver (personal details,status,etc) | 6 | 0.75
| Manage Security Roles/ Groups | 6 | 0.75
| Manage Entities and their representatives’ information. | 8 | 1
| Email notifications / invitations to these users | 12 | 1.5
| Activate/deactiavte users | 4 | 0.5
Business Admin
| Login/Logout remember password, forgot password, email validation, registration | 12 | 1.5
| Dashboard | 32 | 4
| Manage Awards | 6 | 0.75
| Categories | 4 | 0.5
| Specific Participation Award for each Category | 6 | 0.75
| Develop Forms (static forms - max 3) | 24 | 3
| Include types and fields and validation | 6 | 0.75
| Add success message and error message | 6 | 0.75
| Fliter, delete, edit forms based on category | 6 | 0.75
| Manage evaluation | 12 | 1.5
| Delegate/escalate tasks | 6 | 0.75
| Define score sheet for each award | 6 | 0.75
| Matrix of assessment: Dynamic to calculate the results based on weight criteria and final score | 6 | 0.75
| Assign each category for users | 6 | 0.75
| View each application stage | 6 | 0.75
| Set timeframe for each stage of application(SLA configuration) | 6 | 0.75
| Reminder/notification to Evaluators if action not taken within set timeframe(SLA configuration) | 6 | 0.75
| View Shortlisted participants per award | 6 | 0.75
| Reports |  | 0
| Download reports for each category | 6 | 0.75
| export reports PDF and excel format | 12 | 1.5
Editor
| Login/Logout | 8 | 1
| Dashboard | 16 | 2
| Manage contents | 12 | 1.5
| About us | 4 | 0.5
| Contact us forms, tag status of each entry | 6 | 0.75
| FAQ | 6 | 0.75
| Events & workshops |  | 0
| Upload videos and images | 6 | 0.75
| Category, date ,title, description | 6 | 0.75
End user/Participant
New Registration
| Register new user | 8 | 1
| User Name, Official mail ID, mobile Number,etc | 2 | 0.25
| Receive verification mail | 2 | 0.25
| Registered User |  | 0
| Login/Logout | 4 | 0.5
| Dashboard(View application status,events and workshops date,etc) | 12 | 1.5
| New award application | 16 | 2
| select category |  | 0
| Fill participation forms |  | 0
| Save application as draft |  | 0
| Edit saved application if not send/submitted |  | 0
| Upload documents(doc,PDF,excel) |  | 0
| Submit |  | 0
| Receive notification on submission | 6 | 0.75
| Receive notification mail on activation | 6 | 0.75
| Receive Invitations | 6 | 0.75
| Payment | 16 | 2
Assessor
| login/logout | 4 | 0.5
| Dashboard | 10 | 1.25
| Receive reminders, invitations | 6 | 0.75
| Evaluate the submitted forms | 6 | 0.75
| Escalate/delegate | 6 | 0.75
| Receive notification mail on activation/deactivation | 4 | 0.5
Reviewer
| login/logout | 4 | 0.5
| Dashboard | 8 | 1
| Receive reminders, invitations | 4 | 0.5
| Review the forms | 6 | 0.75
| Escalate/delegate | 6 | 0.75
| Receive notification mail on activation/deactivation | 4 | 0.5
Approver
| login/logout | 4 | 0.5
| Dashboard | 6 | 0.75
| Receive reminders, invitations | 4 | 0.5
| Approve/reject | 4 | 0.5
| Receive notification mail on activation/deactivation | 4 | 0.5
| Escalate/delegate | 4 | 0.5
Integration
| Payment Integration | 16 | 2
| REDIS integraion | 16 | 2
| Minio Integration | 16 | 2
| Keycloak integration | 16 | 2
| ELK stack integration | 16 | 2
Security
| Protection against injection attacks (SQL, CRLF) | 12 | 1.5
| URL encoding, Input validation | 6 | 0.75
| Cookie Encryption, Cookie replay attacks | 6 | 0.75
| Session hijacking prevention | 6 | 0.75
| Cross site scripting and session management | 6 | 0.75
System Requirements
| Notification mail on activation/deactivation | 4 | 0.5
| Verification mail on new user registration | 4 | 0.5
| Notification mail on submission | 4 | 0.5
| Notification to approver, assessor, reviewer at different stages | 4 | 0.5
| Store all form submissions in backend |  | 0
| 2,000 simultaneous users |  | 0
| 1 second response time |  | 0
| 500 transactions per second |  | 0
| role base access control (RBAC) for application logs |  | 0
| audit tables for all transactional related data |  | 0
| Detailed Audit logs to track any action done by any user ( |  | 0
| capture activity dates and activity users |  | 0
| Payment Integration | 16 | 2
| Google Analytics | 24 | 3
| CMS | 56 | 7
Quality Assurance
| QA & Bug Fixing | 301 | 37.625
| UAT | 40 | 5
| Deployment per instance |  | 0
| Total Effort |  | 178.875
Assumptions
The effort may change after a detailed system study

## mobile
MOE Founder Award |  |  |  | 19/4/2020
Sunday
Module | Android |  | iOS |  |  | No | Man Days | Total Effort
| Hours | Man Days | Hours | Man Days | Designer | 1 | 3 | 3
Development |  |  |  |  | Sr Developer | 1 | 9 | 9 | 22 | 19 | 19 | 19
Design | 24 | 3 | 24 | 3 | Jr Developer | 1 | 10 | 10
App. Basic setup | 8 | 1 | 8 | 1 | QA | 1.5 | 7.8 | 11.7
New registration |  |  |  |  | Total | 4.5 | 29.8 | 33.7
Splash Screen | 8 | 1 | 8 | 1 |  | Days
Register new user |  | 0 |  | 0 | Effort | 33.7 | + 1 Day (Deployment)
User Name, Official mail ID, mobile Number,etc | 8 | 1 | 8 | 1 | Delivery Time | 20.8 | + 1 Day (Deployment)
Receive verification mail |  | 0 |  | 0
[5 empty] | API development | 9.9
User/Participant
Login/Logout | 8 | 1 | 8 | 1
Dashboard(View application status,events and workshops date,etc) | 10 | 1.25 | 10 | 1.25 | Android Development Effort | 33.7 | +1 deployment
New award application |  | 0 |  | 0 | IOS Development Effort | 33.7 | +1 deployment
select category | 6 | 0.75 | 6 | 0.75 | Mobile Delivery Time (Common) | 20.8
Fill participation forms | 8 | 1 | 8 | 1 | API Development Effort (Common) | 12.375
Save application as draft | 10 | 1.25 | 10 | 1.25
Edit saved application if not send/submitted | 6 | 0.75 | 6 | 0.75
Upload documents(doc,PDF,excel) | 8 | 1 | 8 | 1
Submit | 6 | 0.75 | 6 | 0.75 | Total Effort | 79.775
Receive notification on submission | 6 | 0.75 | 6 | 0.75
Receive notification mail on activation | 6 | 0.75 | 6 | 0.75
Receive Invitations | 6 | 0.75 | 6 | 0.75
Payment | 24 | 3 | 24 | 3
Bilingual(english& arabic) | 24 | 3 | 24 | 3
API Development | 79.2 | 9.9
Quality Assurance
QA & Bug Fixing | 61.6 | 7.7 | 61.6 | 7.7
UAT | 32 | 4 | 32 | 4
Deployment per instance | 8 | 1 | 8 | 1
Total Effort | 356.8 | 44.6 | 277.6 | 34.7
Assumptions 1.This estimation is done only for portarit mode of the applictaion. 2.The estimation may vary with changes or addition of new features. 3.The notification is considered to be from the backend and from the mobile side.