## students Portal
Crowd Funding & Students Portal |  | 31/3/2020
Tuesday
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Designer | 1 | 8 | 8
Business analysis | 64 | 8 | Sr Developer | 1 | 50 | 50 | 65.75 | 110.125 | 101.25 | 100
Project Management | 81 | 10.125 | Jr Developer | 1 | 50 | 50
SRS,FS,User Manual | 32 | 4 | PM | 1 | 10.125 | 10.125
Design(responsive) and Prototype | 64 | 8 | BA | 1 | 8 | 8
Development |  |  | Tech writer | 1 | 4 | 4
Application basic setup | 8 | 1 | QA | 2 | 21.5437 | 43.0875
Crowd Funding Portal |  |  | Total |  | 87.5438 | 173.2125
Fundraising Ideas | 32 | 4
Submit Application | 36 | 4.5 | Effort | 173.2125
Personal details |  | 0 | Delivery Time | 87.5438 | + | 3 |  |  | Days for deployment
University details |  | 0
Project details |  | 0
Add attachments |  | 0
Class year/grade |  | 0
Proposed Campaign |  | 0
Campaign description |  | 0
Receive acceptance |  | 0
Programs | 16 | 2
Campaigns | 64 | 8
Education(Different Projects ) |  | 0
Student Support(Scholarship Schemes) |  | 0
Club Events (Arts & Culture) |  | 0
View details (Images, Videos, etc.) |  | 0
Raised (amount) |  | 0
Donors |  | 0 |  | 40
Time/days left |  | 0 |  | 75
Give Now/donate |  | 0
Ways of Giving/donating | 24 | 3
Credit/Debit Cards |  | 0
Cheque |  | 0
Acceptance |  | 0
Wire Transfers, etc. |  | 0
0
Student's Portal
Manage Student Affairs (Financial aid, Academic Advising, campus activities, financial aid, campus safety) | 56 | 7
Academics |  | 0
Manage Degree Equivalency | 24 | 3
Find potential alternatives (courses comparison) | 24 | 3
Courses |  | 0
Interested | 16 | 2
Decided | 16 | 2
List of Universities (Display, Filter, sort) | 24 | 3
Study in UAE | 6 | 0.75
Apply for government scholarship | 32 | 4
How to Apply/Enroll | 72 | 9
Bachelor Programs |  | 0
Master Programs |  | 0
Research |  | 0
Entry Exams |  | 0
Application Forms |  | 0
Receive acceptance |  | 0
Careers | 32 | 4
Internships |  | 0
Jobs |  | 0
Feedback |  | 0
Guidance and FAQs |  | 0
Dashboard |  | 0
My pending actions | 6 | 0.75
My actioned items | 6 | 0.75
My open requests | 6 | 0.75
My closed requests | 6 | 0.75
Filters, Sorting & Export | 6 | 0.75
Apply & Receive Acceptance on awards, scholarships,admission | 8 | 1
Look up values | 6 | 0.75
Report Features | 32 | 4
Filters |  | 0
Sorting |  | 0
Grouping |  | 0
Export to Excel |  | 0
Export to PDF |  | 0
Workflow features |  | 0
Form to submit application with approximately 10 fields | 12 | 1.5
Option to add attachments | 4 | 0.5
Multiple levels of approvals | 4 | 0.5
Option to add notes during the approval | 4 | 0.5
Mail & SMS notifications | 12 | 1.5
0
Backend
Extract reports in excel/PDF format | 12 | 1.5
Backend management |  | 0
User roles management | 12 | 1.5
FAQ(edit/delete) | 6 | 0.75
Upload documents | 4 | 0.5
Manage Careers | 8 | 1
Manage Courses | 8 | 1
Manage Institutions/Universities | 8 | 1
Create Programs | 8 | 1
Campaigns Management | 16 | 2
Add attachments | 4 | 0.5
Login/Logout | 6 | 0.75
Admin panels for the content management | 8 | 1
General Characterstics
Blogs | 40 | 5
Contact Us | 4 | 0.5
About Us | 4 | 0.5
Dashboard | 16 | 2
Bilingual(English & Arabic) | 40 | 5
Register,Login/Logout | 12 | 1.5
Quality Assurance
QA & Bug Fixing | 280.7 | 35.0875
UAT | 40 | 5
Deployment per instance | 24 | 3
Total Effort | 1395.7 | 174.4625
Assumptions
English & Arabic language is considered
The effort may change after a detailed system study