## MOHRE
| MOHRE - Website Management |  | 20/4/2020
Monday
| Module | Hours | Man Days | Resource | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 6 | 6
1 | Business analysis | 32 | 4 | Sr Developer | 1 | 41 | 41 | 97.25 | 112.625 | 102.25 | 103
2 | Project Management | 77 | 9.625 | Jr Developer | 1.5 | 41.3333 | 62
3 | SRS,FS,User Manual | 32 | 4 | PM | 1 | 9.625 | 9.625
4 | Design and Prototype | 48 | 6 | BA | 1 | 4 | 4
| Development |  |  | Tech writer | 1 | 4 | 4
5 | Application basic setup | 8 | 1 | QA | 2 | 19.5187 | 39.0375
| Existing |  |  | Total | 8.5 | 125.4771 | 165.6625
| Website Maintenance (Avg. 32 hrs / week) |  |  | - | - | - | -
| Technical Support for iCMS | 8 | 1 | Effort | 165.6625 | + 2 Day (Deployment) |  |  |  | 20.7078
| Design Work | 8 | 1 | Delivery Time | 70.8521 | + 2 Day (Deployment) |  |  |  | 3.5426
| Development & Management of sub sites | 8 | 1
| Ongoing support of pages and modules | 8 | 1
New
Awards and new developments
| UAE Emiritization Award | 0 | 0
| Establishments category award | 24 | 3
| Emiritasation pioneer award | 20 | 2.5
| Emiritisation supporting entity award | 20 | 2.5
| Emirati employee category | 20 | 2.5
| Emiratisation Award Assessor Nomination Award | 20 | 2.5
| Happiest Work Environment Award | 20 | 2.5
| · MOHRE Innovation Award | 16 | 2
| · MOHRE Excellence Award | 16 | 2
| Smart services and applications award | 16 | 2
| Workshop Attendance forms | 8 | 1
Award Entry /Application submission
| User registration (email validation) | 12 | 1.5
| Social & Mobile authentication | 6 | 0.75
| Role registration | 6 | 0.75
| Manage award contents Description, images, videos) | 24 | 3
Award Management
| Count down timer ( timer for prestart, voting period) | 6 | 0.75
| Management Dashboard | 12 | 1.5
| Custom reports (exportable as PDF, word or excel) | 6 | 0.75
| Broadcast email communication | 4 | 0.5
Enhancements
| Careers |  | 0
| Job Openings | 24 | 3
| Job Applications | 24 | 3
| Job Descriptions | 24 | 3
| Address Book | 24 | 3
Admin
| Login/logout | 6 | 0.75
| manage Users | 14 | 1.75
| Track user activity | 6 | 0.75
| Dashboard to view all applications | 16 | 2
| View job applications | 8 | 1
| Create Jobs | 12 | 1.5
| Update Address book | 6 | 0.75
| Add Job descriptions | 6 | 0.75
| View Award nominations and nomination results | 6 | 0.75
Users
| Submit workshop Attendees | 4 | 0.5
| Submit Job Applications | 4 | 0.5
| Submit nominations (Vote) | 4 | 0.5
| View Address Book | 4 | 0.5
| View Job Openings | 4 | 0.5
Third Party Integration
| TRA E-Consultation | 24 | 3
| PMO Khadamathi | 24 | 3
| Check Application Status | 24 | 3
| Happiness meter | 24 | 3
| Waiting time for happiness center | 24 | 3
| Happpiness center reading from mobile application database | 24 | 3
| Sign language AI | 24 | 3
| UAE SDG KPI's | 24 | 3
| SMS & Email | 12 | 1.5
System Features
| User management | 8 | 1
| Authentication, Authorization, Entitlements | 8 | 1
| Auditing and Logging | 8 | 1
| Managing Exceptions and Errors | 8 | 1
| Communication Management | 8 | 1
Security Features
| Protection against injection (SQL, CRLF, LDAP) | 6 | 0.75
| URL encoding, Input validation | 6 | 0.75
| Cookie Encryption, Cookie replay attacks | 6 | 0.75
| Session hijacking prevention | 6 | 0.75
| Cross site scripting and session management | 6 | 0.75
| Auditing and logging | 6 | 0.75
| Exceptions and error handling | 6 | 0.75
| Bilingual site | 40 | 5
Quality Assurance
| QA & Bug Fixing | 272.3 | 34.0375
| UAT | 40 | 5
| Deployment per instance | 16 | 2
| Total Effort |  | 166.9125
Assumptions
Maintenance shall be on Time and Material