## Chatbot
| Chatbot-Admin |  | 2020-05-04
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 7 | 7
1 | Business analysis | 64 | 8 | Sr Developer | 1 | 86 | 86 | 261 | 270.3 | 261 | 261
2 | Project Management | 74.4 | 9.3 | Jr Developer | 2 | 87.5 | 175
3 | SRS,FS,User Manual | 24 | 3 | PM | 1 | 9.3 | 9.3
4 | Design and branding as per the federal visual identity guideline(effective and enjoyable UX) | 56 | 7 | BA | 1 | 8 | 8
5 | Application Demo, Prototype |  |  | Tech writer | 1 | 3 | 3
| Development |  |  | QA | 2 | 23.425 | 46.85
6 | Application basic setup | 8 | 1 | Total | 9 | 224.225 | 335.15
| Administration |  |  |  | Man Days |  |  |  |  | Man Months
| Create user accounts | 6 | 0.75 | Effort | 335.15 | + 1 Day (Deployment) |  |  |  | 16.7575
| Create super users | 6 | 0.75 | Delivery Time | 125.925 | + 1 Day (Deployment) |  |  |  | 6.2962
| Login/Logout | 6 | 0.75
| Identify previliged users for Approval if required | 8 | 1
| Assign authority to post to each section of the questions | 8 | 1
| Specify whether any section requires approval for publication | 8 | 1
| Define the sections of questions | 16 | 2
Main Dashboard
| Total number of Q&A maintained | 6 | 0.75
| Total number of questions asked by the public | 6 | 0.75
| Number of correct/incorrect answers | 6 | 0.75
| Number of new questions answered by the Chatbot | 6 | 0.75
| Number of users | 6 | 0.75
| Other requested services | 6 | 0.75
0
Questions Editing
| Search | 6 | 0.75
| Filters | 6 | 0.75
| Retrieve question and answers (dropdown) | 6 | 0.75
| Add/delete/maintain Q&A | 6 | 0.75
| Q&A publishing (by the authorized user) | 6 | 0.75
| Notification on adding an existing or similar to an existing question | 6 | 0.75
Machine Learning
| Machine learning templates: Feeding the system with multiple alternatives for the same Q&A | 32 | 4
| Get user feedback on the received answer | 32 | 4
| Display questions asked and answers given with the related level of accuracy | 32 | 4
| Ability to approve current answer thus increasing accuracy | 32 | 4
| Review, update, improve, and/or change Q&A and related machine learning templates based on user feedback and/or answers provided by the chatbot and corresponding level of accuracy | 32 | 4
Statistical Reporting
| Ability to filter results based on a number of criteria ex. Questions' section, date, users,…… | 6 | 0.75
| Number of total questions | 6 | 0.75
| Number of total questions asked by the public | 6 | 0.75
| Number of correct/accurate answers | 6 | 0.75
| Number of new questions not yet answered by the Chatbot/asked by the public | 6 | 0.75
| Users' based reports | 6 | 0.75
| Other statistics and reports as per MOJ request | 6 | 0.75
Lawyers services
| E-services offered by the e-Lawyer Portal availability thru the Chatbot. | 16 | 2
| Chatbot (new user interface) built over the existing backend | 16 | 2
| OTP Authentication of registered lawyers | 16 | 2
| Register new lawyers | 8 | 1
Integration Requirements
| MOJ e-Lawyers Portal/database | 16 | 16
| e-dirham online payment gateway | 16 | 16
| SMS notifications thru MOJ-SMS gateway (pre-defined & configurable templates) | 16 | 16
| Ability to create and send SMS thru integration with the SMS-gateway | 16 | 16
| Happiness Meter | 16 | 16
| email notifications (pre-defined & configurable templates) | 16 | 16
| MOJ Website | 16 | 16
| Active Directory SSO for MOJ users | 16 | 16
| Scanners, Barcode & QR, e-signature pads if applicable | 16 | 16
| Any application(s), s/w and h/w required by the solution | 16 | 16
Reports
| Pre-configured/standard/customized/user defined reports | 16 | 2
| Save user defined reports | 32 | 4
| Printing and exporting to other formats | 6 | 0.75
| Automated reports to be emailed upon preset schedule | 6 | 0.75
| Performance indicators reporting | 16 | 2
| Productivity reporting | 16 | 2
| Management dashboards | 40 | 5
| App Analytics, reports, vital statistics and analysis | 8 | 1
| Pre-configured/standard/customized/user defined reports | 16 | 2
General Requirements
| Time-out sessions handling | 8 | 8
| Data encryption | 8 | 8
| TRA guidelines, i.e. the federal website quality guidelines and the e-services' quality criteria | 8 | 8
| Authenticated and authorized access to data | 8 | 8
Quality Assurance
| QA & Bug Fixing | 334.8 | 41.85
| UAT | 40 | 5
| Deployment per instance | 8 | 1
| Total Effort |  | 336.15
Assumptions
The effort may change after a detailed system study