## Media Land
Media Land FZ | 04 10 2017
Friday
Module | Man Hours | Man Days
Initiation
Requirements gathering and documentation (SRS) | 8 | 3
Functional Specification | 8 | 3
Project Management | 23.6 | 4
0
Graphic Design (Web + Mobile + Tablet) | 40 | 5
Development
Admin (Web Application) | hours | days
Import Corporations and contacts via CSV | 8 | 1
Manage Organization | 4 | 0.5
Manage mobile app users (assign Organization) | 8 | 1
Manage Contact Categories | 4 | 0.5
Manage Contacts | 4 | 0.5
Send Email to individual or organization contacts (selected) | 12 | 1.5
Send SMS to individual or organization contacts (selected) | 8 | 1
Permission Management | 4 | 0.5
Admin Dashboard | 8 | 1 | [5 empty] | No | Man hours | Man Days | Total Effort
Mobile User (Native App) | Man Hours | Man Days | Man Hours | Man Days | Hours | Days | Designer | 1 | 40 | 5 | 5
| Web |  | Mobile |  | API |  | Sr Developer (Web) | 1 | 92 | 11.5 | 11.5
Dashboard | 8 | 1 | 12 | 1.5 | 4 | 0.5 | IOS Developer | 1 | 85 | 10.625 | 10.625
Login, Authentication etc.. | 6 | 0.75 | 8 | 1 | 4 | 0.5 | Android Developer | 1 | 68 | 8.5 | 8.5
Add Organization | 4 | 0.5 | 6 | 0.75 | 4 | 0.5 | BA | 1 | 16 | 2 | 2
Add contacts | 4 | 0.5 | 6 | 0.75 | 4 | 0.5 | PM | 1 | 23.6 | 2.95 | 2.95
Email contacts in organization | 6 | 0.75 | 8 | 1 | 4 | 0.5 | QA | 1 | 78.8 | 9.85 | 9.85
SMS contacts in organization | 6 | 0.75 | 8 | 1 | 4 | 0.5 | Total |  | 403.4 | 50.425 | 50.425
Select Organization | 4 | 0.5 | 6 | 0.75 | 4 | 0.5
Select contacts within organization | 4 | 0.5 | 6 | 0.75 | 4 | 0.5 | Total Delivery days | 29.3
Sort contacts | 4 | 0.5 | 4 | 0.5 | 4 | 0.5 | Total Man day Effort | 50.425
Filter Contacts | 6 | 0.75 | 4 | 0.5 | 4 | 0.5
System
Password salting / Authentication | 8 | 1
Logging / Auditing | 8 | 1
Testing & Deployment
Testing | 70.8 | 8.85
UAT | 8 | 1
Deployment | 8 | 1
Total Effort | 402.4 | 50.3
(