## Media Land
Media Land FZ | 04 10 2017
Friday
Module | Man Hours | Man Days
Initiation
Requirements gathering and documentation (SRS) | 8 | 3
Functional Specification | 8 | 3
Project Management | 16.8 | 4
0
Graphic Design (Web + Mobile + Tablet) | 40 | 5
Development
Admin (Web Application) | hours | days
Import Corporations and contacts via CSV | 8 | 1
Manage Organization | 4 | 0.5
Manage mobile app users (assign Organization) | 8 | 1
Manage Contact Categories | 4 | 0.5
Manage Contacts | 4 | 0.5
Send Email to individual or organization contacts (selected) | 12 | 1.5
Send SMS to individual or organization contacts (selected) | 8 | 1
Permission Management | 4 | 0.5
Admin Dashboard | 8 | 1 | [5 empty] | No | Man hours | Man Days | Total Effort
Mobile User (Native App) | Man Hours | Man Days | Man Hours | Man Days | Hours | Days | Designer | 1 | 40 | 5 | 5
| Web |  | Mobile |  | API |  | Sr Developer (Web) | 2 | 84 | 10.5 | 21
Dashboard | 12 | 1.5 | 12 | 1.5 | 4 | 0.5 | IOS Developer | 0 | 85 | 10.625 | 0
Login, Authentication etc.. | 10 | 1.25 | 8 | 1 | 4 | 0.5 | Android Developer | 0 | 68 | 8.5 | 0
Add Organization | 8 | 1 | 6 | 0.75 | 4 | 0.5 | BA | 1 | 16 | 2 | 2
Add contacts | 8 | 1 | 6 | 0.75 | 4 | 0.5 | PM | 1 | 16.8 | 2.1 | 2.1
Email contacts in organization | 10 | 1.25 | 8 | 1 | 4 | 0.5 | QA | 1 | 58.4 | 7.3 | 7.3
SMS contacts in organization | 10 | 1.25 | 8 | 1 | 4 | 0.5 | Total |  | 368.2 | 46.025 | 37.4
Select Organization | 8 | 1 | 6 | 0.75 | 4 | 0.5
Select contacts within organization | 8 | 1 | 6 | 0.75 | 4 | 0.5 | Total Delivery days | 22.8 | +1 deployment
Sort contacts | 8 | 1 | 4 | 0.5 | 4 | 0.5 | Total Man day Effort | 37.4
Filter Contacts | 10 | 1.25 | 4 | 0.5 | 4 | 0.5
System
Password salting / Authentication | 8 | 1
Logging / Auditing | 8 | 1
Testing & Deployment
Testing | 50.4 | 6.3
UAT | 8 | 1
Deployment | 8 | 1
Total Effort | 307.2 | 38.4
(