## Android
Miral
# | Modules | Hours | Days
Android
Ui Design
| Page Design | 130 | 16.25
Development
0
| User Management |  | 0
| Initiators Login ,registration page and dash board | 12 | 1.5
| Incident Owners Login ,registration page and dash board | 12 | 1.5
| Recipients Login ,registration page and dash board | 12 | 1.5
| System Administrator Login ,registration page and dash board | 12 | 1.5
0
| Incident Reporting - Creation |  | 0
| Identify Geo Location automatically | 8 | 1
| Option to manually select Location | 4 | 0.5
| Select incident Category, Severity, Type | 2 | 0.25
| Incident time & date, Status, User ID | 4 | 0.5
| Optional Text | 2 | 0.25
| Option to capture Audio, Video or Image | 8 | 1
| Push notifications |  | 0
| Push notification Integration | 8 | 1
| Customizations App |  | 0
| Change font | 16 | 2
| Change color theme | 16 | 2
| Communication Options |  | 0
| Voice call via App | 8 | 1
| Auto IVR Call | 16 | 2
| Chat room integration for incident collaboration | 24 | 3
| Email | 4 | 0.5
| Oflline Messaging via SMS (optional) | 8 | 1
| Online Messaging via Net | 4 | 0.5
| Intelligence to choose mode of communication | 8 | 1
| Feedback |  | 0
| Feedback page | 4 | 0.5
| Download |  | 0
| Download Documents | 16 | 2
| Option to choose between Wifi & mobile data plan for document downloads | 8 | 1
| Notification |  | 0
| Incident notification receipt | 8 | 1
| Incident status change notifications | 4 | 0.5
| Receive emrgency alerts | 4 | 0.5
| Panic button ( for emrgency calls) | 12 | 1.5
| Planned event notifications | 8 | 1
| Camera |  | 0
| Camera integration | 4 | 0.5
| Audio |  | 0
| Audio Integration | 4 | 0.5
| Smart Search |  | 0
| Search page |  | 0
| Incident Owners funcatinality |  | 0
| Drill down graphs | 16 | 2
| Trend analysis (Monthly, Severity, Status etc.) | 16 | 2
| Master data Reports | 12 | 1.5
| Functional role assignment matrix reports | 12 | 1.5
| Parametrized incident reports | 10 | 1.25
| duplicate incident report | 8 | 1
| Root Cause Analysis Report | 6 | 0.75
| Incident closure reports | 6 | 0.75
| Performance reports | 6 | 0.75
| Planned events reports | 6 | 0.75
| Receive incident notification | 6 | 0.75
| Confirm incident receipt | 6 | 0.75
| Take incident ownership | 8 | 1
| Option to change incident status to "OnHold" or "In Progress" | 8 | 1
| Enter incident root cause | 12 | 1.5
| Option to close incident or change to resolved | 8 | 1
0
Api Integration
| Api integration | 55 | 6.875
| Total effort |  | 73.875