## Miral
| Miral Incident management |  | 2018-06-26
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 5 | 5
| Business Analysis | 32 | 4 | Sr Developer | 1 | 50 | 50 | 24.25 | 125 | 24.25 | 100
| Project Management | 20 | 2.5 | Jr Developer | 1 | 50 | 50
| Design and Prototype | 40 | 5 | IOS | 1 | 25 | 25
| Documentation (SRS, FS, Weekly Reports) |  |  | PM | 1 | 2.5 | 2.5
| Development |  |  | BA | 1 | 4 | 4
| Application Basic Setup | 8 | 1 | Tech writer | 1 | 3 | 3
|  |  |  | QA | 2 | 6.625 | 13.25
| Master Data Management (Admin) |  |  | Total |  |  | 152.75
1 | Stakeholders (App Users, Functional Role, Event Stakeholders) | 6 | 0.75
Stakeholder communication and contact info
2 | User Roles | 6 | 0.75 | Total Delivery days | 61.625
3 | incident Severity Levels | 6 | 0.75 | Total Effort | 152.75 | (+1 Day deployment)
4 | Iuncident category | 6 | 0.75
5 | Incident Status | 6 | 0.75
6 | Incident Type | 6
7 | incident Location (Physical) | 6 | 0.75
8 | Location Mapping (GEO Mapping) | 6 | 0.75
9 | Functional Category | 6 | 0.75
10 | Functional Role | 6 | 0.75
11 | Event Types | 6 | 0.75
Event plan types
Email/SMS notofication templates for events
Approve event
12 | Notification Types | 6 | 0.75
13 | Severity Confirmation matrix | 6 | 0.75
14 | Status Change notification setup | 6 | 0.75
15 | Incident Management Team | 6 | 0.75
16 | Default System Messages | 6 | 0.75
17 | Default Contact Info | 6 | 0.75 | [8 empty] | 6 | 0.75
18 | Planned Events (Event Planner) | 12 | 1.5 | [7 empty] | 22 |  | 6 | 0.75
19 | Allowed file formats with extensions (allowed and unallowed types) | 6 | 0.75 | [7 empty] | 20 |  | 6 | 0.75
20 | Artifact Repository (Audio, Video, document) | 6 | 0.75 | [8 empty] | 6 | 0.75
21 | Document Metatags | 6 | 0.75 | [8 empty] | 6 | 0.75
Data Mapping
18 | User - Role Mapping (Role Assignments) | 6 | 0.75
19 | Incident Acknowledgement Role matrix | 6 | 0.75
18 | Functional Role-incident resolution matrix | 6 | 0.75
19 | Severity - incident category mapping | 6 | 0.75
20 | Location - Category Mapping | 6 | 0.75
21 | Team - Role - User Mapping | 6 | 0.75
22 | Incident - Role Mapping | 6 | 0.75
23 | Notification - Role Mapping | 6 | 0.75
24 | Notofication - User Mapping | 6 | 0.75
24 | Event - Location | 6 | 0.75
Incident Receipt & Notification (Mobile)
26 | Process Incident notification |  | 0
27 | Identify recepients for notification |  | 0
28 | Auto confirm receipt if not acknowledged within timeframe (Ack) |  | 0
29 | Change Incident owner after confirmation |  | 0
30 | Incident processing based on L1, L2 & L3 (workflow) |  | 0
31 | Incident resolution rules and logic |  | 0
32 | Incident acknowledgment rules and logic |  | 0
33 | Incident closure rules and logic |  | 0
34 | Incident notification rules |  | 0
35 | Incident acknowledgment alert workflow |  | 0
36 | Incident collaboration via chat |  | 0
Incident audit logs
39 | Planned Events (Event Planner) |  | 0
40 | Create event plan with calendar , Media uploads, event types, stakeholders |  | 0
41 | Notify event stakeholders |  | 0
42 | Send for Approval |  | 0
43 | Event Scheduler (Single day, Multi day, continious) |  | 0 |  | Onsite inspection (mobile App)
47 | Others |  | 0
48 | Application dashboard for admin |  | 0
49 | Master data reports for admin |  | 0
50 | Reports functional assignments |  | 0
51 | Various Reports |  | 0
System features
108 | Authentication & authorization |  | 0
109 | Auditing & logging |  | 0
110 | Exception handling |  | 0
111 | Manage files and folders |  | 0
113 | SMS & Email |  | 0
115 | Scheduling |  | 0
Quality Assurance
| QA & Bug Fixing | 90 | 11.25
| UAT | 16 | 2
| Deployment per instance | 8 | 1
| Total Effort | 406 | 50
Assumptions
Pre defined format for print and format will designed in HTML and print in plain paper
Need clarification
Mobile App For TSD Inspector. App should work offline
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118

## Mobile App
1 | Miral Branding Guidelines with strong emphasis on visuals
2 | User Authentication (stay logged in until sign out)
App User
Incident Reporting - Creation
Identify Geo Location automatically
Option to manually select Location
Select incident Category, Severity, Type
Incident time & date, Status, User ID
Optional Text
Option to capture Audio, Video or Image
Receive Push notifications
Customizations
Change font
Change color theme
Communication Options
Voice call via App
Auto IVR Call
Chat room integration for incident collaboration
Email
Oflline Messaging via SMS (optional)
Message format for Sending SMS Messages
Online Messaging via Net
Intelligence to choose mode of communication
Feedback
Download Documents
Option to choose between Wifi & mobile data plan for document downloads
Incident notification receipt
Incident status change notifications
Receive emrgency alerts
Panic button ( for emrgency calls)
Planned event notifications
Camera integration
Audio Integration
Smart Search
Emergency Responder
Entitlement based Dashboard
Drill down graphs
Trend analysis (Monthly, Severity, Status etc.)
Master data Reports
Functional role assignment matrix reports
Parametrized incident reports
duplicate incident report
Root Cause Analysis Report
Incident closure reports
Performance reports
Planned events reports
Receive incident notification
Confirm incident receipt
Take incident ownership
Option to change incident status to "OnHold" or "In Progress"
Enter incident root cause
Option to close incident or change to resolved
Planned events
Receive event plan notification