## Miral
| Miral Incident management |  | 2018-06-26
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 9 | 9
| Business Analysis (srs + fs+ Project Scedules, Meeting minutes etc) | 56 | 7 | Sr Developer | 1 | 40 | 40 | 79.5 | 154.875 | 81 | 81
| Project Management | 64.8 | 8.1 | Jr Developer | 1 | 41 | 41
| Design and Prototype | 72 | 9 | Android | 1 | 73.875 | 73.875
| Documentation (SRS, FS, Weekly Reports) | 80 | 10 | IOS | 1 | 84.9562 | 84.9562 |  |  | 68.9562
| Development |  |  | PM | 1 | 8.1 | 8.1
| Application Basic Setup | 8 | 1 | BA | 1 | 7 | 7
|  |  |  | QA ( Web + IOS + Android) | 2 | 19.225 | 38.45
| Master Data Management (Admin) |  |  | Total |  |  | 302.3813
1 | Stakeholders (App Users, Functional Role, Event Stakeholders) | 8 | 1
2 | Stakeholder communication and contact info | 12 | 1.5
3 | User Roles | 4 | 0.5 | Total Delivery days | 69.225 | 60.225
4 | incident Severity Levels | 4 | 0.5 | Total Effort | 302.3813 | (+1 Day deployment)
5 | Iuncident category | 4 | 0.5
6 | Incident Status | 4 | 0.5
7 | Incident Type | 4 | 0.5
8 | incident Location (Physical) | 4 | 0.5
9 | Location Mapping (GEO Mapping) | 8 | 1
10 | Functional Category | 4 | 0.5
11 | Functional Role | 4 | 0.5
12 | Event Types | 4 | 0.5
13 | Event plan types | 4 | 0.5
14 | Email/SMS notofication templates for events | 12 | 1.5
15 | Approve event | 8 | 1
16 | Notification Types | 4 | 0.5
17 | Severity Confirmation matrix | 4 | 0.5
18 | Status Change notification setup | 4 | 0.5
19 | Incident Management Team | 4 | 0.5
20 | Default System Messages | 4 | 0.5
21 | Default Contact Info | 4 | 0.5
22 | Planned Events (Event Planner) | 12 | 1.5
23 | Allowed file formats with extensions (allowed and unallowed types) | 8 | 1
24 | Artifact Repository (Audio, Video, document) | 16 | 2
25 | Document Metatags | 12 | 1.5
Data Mapping
25 | User - Role Mapping (Role Assignments) | 4 | 0.5
26 | Incident Acknowledgement Role matrix | 16 | 2
27 | Functional Role-incident resolution matrix | 8 | 1
28 | Severity - incident category mapping | 8 | 1
29 | Location - Category Mapping | 4 | 0.5
30 | Team - Role - User Mapping | 4 | 0.5
31 | Incident - Role Mapping | 12 | 1.5
32 | Notification - Role Mapping | 4 | 0.5
33 | Notofication - User Mapping | 4 | 0.5
34 | Event - Location | 4 | 0.5
Incident Receipt & Notification (Mobile Web API)
35 | Process Incident notification | 8 | 1
36 | Identify recepients for notification | 8 | 1
37 | Auto confirm receipt if not acknowledged within timeframe (Ack) | 16 | 2
38 | Change Incident owner after confirmation | 12 | 1.5
39 | Incident processing based on L1, L2 & L3 (workflow) | 28 | 3.5
40 | Incident resolution rules and logic | 12 | 1.5
41 | Incident acknowledgment rules and logic | 8 | 1
42 | Incident closure rules and logic | 16 | 2
43 | Incident notification rules | 16 | 2
44 | Incident acknowledgment alert workflow | 24 | 3
45 | Incident collaboration via chat | 20 | 2.5
46 | Incident audit logs | 12 | 1.5
Planned Events (Event Planner)
47 | Create event plan with calendar , Media uploads, event types, stakeholders | 20 | 2.5
48 | Notify event stakeholders | 8 | 1
49 | Send for Approval | 12 | 1.5
50 | Event Scheduler (Single day, Multi day, continious) | 20 | 2.5
Others
51 | Application dashboard for admin | 16 | 2
52 | Master data reports for admin | 12 | 1.5
53 | Reports functional assignments (3 Tabular reports) | 24 | 3
54 | Various Reports (3 Tabular reports) | 24 | 3
55 | Integration with CRM partner | 40 | 5
System features
55 | Authentication & authorization | 12 | 1.5
56 | Auditing & logging | 12 | 1.5
57 | Exception handling | 4 | 0.5
58 | Manage files and folders | 12 | 1.5
59 | SMS & Email | 4 | 0.5
60 | Scheduling | 12 | 1.5
Quality Assurance
61 | QA & Bug Fixing | 291.6 | 36.45
62 | UAT | 16 | 2
63 | Deployment per instance | 8 | 1
| Total Effort | 1236.4 | 154.55
Assumptions
The actual effort for the CRM integration can be estimated once the integration details are available
The effort might change after a detaile system study

## Mobile App
Miral
# | Modules | Hours | Days
Android Only
Ui Design
| Page Design | 130 | 16.25
Development
User Management
| Initiators Login ,registration page and dash board | 12 | 1.5
| Incident Owners Login ,registration page and dash board | 12 | 1.5
| Recipients Login ,registration page and dash board | 12 | 1.5
| System Administrator Login ,registration page and dash board | 12 | 1.5
0
Incident Reporting - Creation
| Identify Geo Location automatically | 8 | 1
| Option to manually select Location | 4 | 0.5
| Select incident Category, Severity, Type | 2 | 0.25
| Incident time & date, Status, User ID | 4 | 0.5
| Optional Text | 2 | 0.25
| Option to capture Audio, Video or Image | 8 | 1
Push notifications
| Push notification Integration | 8 | 1
Customizations App
| Change font | 16 | 2
| Change color theme | 16 | 2
Communication Options
| Voice call via App | 8 | 1
| Auto IVR Call | 16 | 2
| Chat room integration for incident collaboration | 24 | 3
| Email | 4 | 0.5
| Oflline Messaging via SMS (optional) | 8 | 1
| Online Messaging via Net | 4 | 0.5
| Intelligence to choose mode of communication | 8 | 1
Feedback
| Feedback page | 4 | 0.5
Download
| Download Documents | 16 | 2
| Option to choose between Wifi & mobile data plan for document downloads | 8 | 1
Notification
| Incident notification receipt | 8 | 1
| Incident status change notifications | 4 | 0.5
| Receive emrgency alerts | 4 | 0.5
| Panic button ( for emrgency calls) | 12 | 1.5
| Planned event notifications | 8 | 1
| Camera |  | 0
| Camera integration | 4 | 0.5
| Audio |  | 0
| Audio Integration | 4 | 0.5
| Smart Search |  | 0
| Search page |  | 0
Incident Owners funcatinality
| Drill down graphs | 16 | 2
| Trend analysis (Monthly, Severity, Status etc.) | 16 | 2
| Master data Reports | 12 | 1.5
| Functional role assignment matrix reports | 12 | 1.5
| Parametrized incident reports | 10 | 1.25
| duplicate incident report | 8 | 1
| Root Cause Analysis Report | 6 | 0.75
| Incident closure reports | 6 | 0.75
| Performance reports | 6 | 0.75
| Planned events reports | 6 | 0.75
| Receive incident notification | 6 | 0.75
| Confirm incident receipt | 6 | 0.75
| Take incident ownership | 8 | 1
| Option to change incident status to "OnHold" or "In Progress" | 8 | 1
| Enter incident root cause | 12 | 1.5
| Option to close incident or change to resolved | 8 | 1
0
Api Integration
| Api integration | 55 | 6.875
| Total effort |  | 73.875