## Web
PISIQ CRM 06 July 2020
Module | Hours | Man Days | Resources | # | Days | Total
Project Initiation |  |  | UI / UX | 1 | 10 | 10
Business analysis | 56 | 7 | BA | 1 | 7 | 7
Project Management | 179 | 22.375 | Tech Writer | 1 | 5 | 5
SRS,FS,User Manual | 40 | 5 | PM | 1 | 22.375 | 22.375
Design and Prototype (mobile & Web) | 80 | 10 | Jr Developer | 2 | 56 | 112 | 224 | 223
Development |  |  | Sr Developer | 2 | 56 | 112
Application Basic setup | 0 | 0 | Mobile API | 1 | 0 | 0
Customer Profile |  |  | QA | 2 | 45.6562 | 91.3125
Manage Customer Profile | 6 | 0.75 | Total |  |  | 359.6875
Customer Application History | 6 | 0.75
Recent Customer Support Queries | 6 | 0.75 |  | Days | Months
Edit cases raised by customer | 6 | 0.75 | Total Effort | 359.6875 | 17.9844
Call logs from customer over time | 6 | 0.75 | Delivery Timeline | 118.6562 | 5.9328
Create case with reminders | 6 | 0.75
Manage Customer Applications
New Connection | 6 | 0.75
Temporary Connection | 6 | 0.75
Relocate MBD | 6 | 0.75
Relocate SDB | 6 | 0.75
Cable laying estimate | 6 | 0.75
Reconnection | 6 | 0.75
Temp disconnection | 6 | 0.75
Perm disconnection | 6 | 0.75
Approve new meter model | 6 | 0.75
Replace meter | 6 | 0.75
Relocate meter board | 6 | 0.75
Exiusting Meter to panel | 6 | 0.75
Panel modification testing | 6 | 0.75
Existing meter testing | 6 | 0.75
New meter testing | 6 | 0.75
Temporary board connection | 6 | 0.75
New switch board connection (panel) | 6 | 0.75
New switch board connection through existing (panel) | 6 | 0.75
Service main cable replacement | 6 | 0.75
Edit application details based on type and process. | 6 | 0.75
System should ensure different workflows and processes to be managed in this | 6 | 0.75
section according to application duration limits. | 6 | 0.75
System should record and identify the location of the application. | 6 | 0.75
Options to conduct surveys for customer applications if applicable. | 6 | 0.75
Manage survey activities and permits if applicable | 6 | 0.75
Manage pre and post survey activities as jobs to be marked with completion | 6 | 0.75
status from both staff and Contactor. | 6 | 0.75
Integrations to DB Tracer Software to identify and view power distribution | 6 | 0.75
networks and locations. | 6 | 0.75
System should be allocated to Manage applications from multiple locations. | 6 | 0.75
Applications Payments & Refunds
View Online payment history for customer applications
Update and keep track of both physical and online payments and references. | 6 | 0.75
View payment logs of all BML and MIB payments in case of an issue or a refund process. | 6 | 0.75
View related invoices, estimates for the payments regarding the applications. | 6 | 0.75
Attach documents to payments. | 6 | 0.75
Add/edit refunds to different applications. | 6 | 0.75
Costing & Estimates
Generate costing options and estimates for applications. | 6 | 0.75
Generate Estimates while integrating to billing system and procurement system to check item availability and payment details. | 6 | 0.75
View costing history. | 6 | 0.75
Review costing and approval process. | 6 | 0.75
Include contractor details on estimates. | 6 | 0.75
Costing and Estimates should configure different approval processes. | 6 | 0.75
View and Manage cancelled estimates. | 6 | 0.75
Case Management
Case Profiling
Create a case coming from different sources like calls, email, chat, physical etc.. | 8 | 1
Case types (billing, queries, applications, payments, etc.) | 2 | 0.25
Manage and update case status (created, assigned, on Hold, approved, etc.) - Edit and update case time / date (create and closed). | 2 | 0.25
Manage Case Sources (emails, phone, feedback, social, etc.) | 2 | 0.25
Edit and update Case Handling / Escalations / Completions | 6 | 0.75
Create new task or new event | 6 | 0.75
Log a call or send email from a case | 6 | 0.75
Create files, notes with in a case | 6 | 0.75
Generate case reports based on existing data. | 6 | 0.75
Case creation & Identification
Ability to create case from
Matching profile from already existing customer base. | 6 | 0.75
From Emails by customer. | 4 | 0.5
From Social media posts and inboxes (Facebook and Twitter) - Manual Case Creation | 4 | 0.5
Ability to Indicate the source of case | 2 | 0.25
Manage Types of cases | 4 | 0.5
Assignment of case and case status history | 4 | 0.5
Resolution types and closing of cases | 4 | 0.5
Case Escalations |  | 0
Case escalation To CRM Users on different rules based on time slots. | 6 | 0.75
Escalations as Notification (SMS, Email, etc) to relevant users and teams. | 6 | 0.75
Assignment and reassignment of cases. | 4 | 0.5
Customer Feedback & Collections
Feedback Collection
Create and manage feedback from customers. | 6 | 0.75
Identify feedback sources like calls, emails, social media, physical etc.. | 6 | 0.75
Feedback real time overview and insights. | 6 | 0.75
Feedback forms and displayed on kiosk or tablets. | 6 | 0.75
Customer Surveys
Create and manage and conduct customer service surveys. | 6 | 0.75
Collecting feedback via surveys from web links, kiosks, counters etc. | 6 | 0.75
Survey results and insights. | 6 | 0.75
Survey fill out options and display on kiosk or tablets. | 6 | 0.75
System Integrations
The CRM solution should support integration capabilities via API’s both read and write operations from and to different systems like existing Billing System, Procurement System and other existing systems if required. All integrations must be done securely via standard API’s and modern concepts. | 40 | 5
Options to match Customer Profile in CRM via Central System for data synchronization. | 6 | 0.75
Synchronization of customer data and CRM data on all relevant systems to T-1 hour. . | 6 | 0.75
Required validations and exception handling during all data sync. | 6 | 0.75
Up to date data to Customer Profiles in CRM should be maintained. | 6 | 0.75
Call Center Integrations
CRM Software should be able to connect to existing telephone systems/PABX to keep records of call logs with respect to customer calls. | 40 | 5
Integration options to Alcatel, 3CX or other available options via the telecom service provider or related third parties. | 8 | 1
System should show Incoming Caller identification by customer profile within the CRM. | 6 | 0.75
Customer profile summary on call match profiling. | 6 | 0.75
Recent cases, tasks, event, etc | 6 | 0.75
Contact information, social information and demographic data - Matching Caller ID and case match customer profile for existing cases. | 6 | 0.75 |  | data encryption
Integration of Facebook and Twitter (Feeds, Inboxes, other relevant data) to all customer incoming queries. | 8 | 1
Attend social media customer queries from Facebook and Twitter to create / assign cases. | 40 | 5 | 40
Respond/Manage Facebook Messages to customers via CRM. | 12 | 1.5 | 32
Respond/Manage Twitter Messages to customers via CRM. | 12 | 1.5
Show social media insights from Facebook and twitter as for Customer Profiles. | 20 | 2.5
Monitor a feed of social page posts by hashtags eg: by # or by keywords etc from both Facebook and Twitter on one dashboard. | 20 | 2.5
Show timely feeds from social channels to CRM on one dashboard with sorting options. | 12 | 1.5
Options to Map customer profile to social media ids or emails. | 12 | 1.5
Options for Caller ID non-match then provides an option to easily create cases. | 12 | 1.5
Outlook Email Integrations
System should cater to integration to Exchange/Outlook for managing customer incoming, outgoing emails and all email related tasks. | 12 | 1.5
System should be able to configure one email for all communication purposes. | 6 | 0.75
Exchange accounts (IMAP) to CRM software integration | 6 | 0.75
Batch import email inbox to CRM (cron job) if required to cater existing emails. | 12 | 1.5
Read / Respond / Forward / Emails | 40 | 5
Send emails with contents like attachments, links, images and videos. | 12 | 1.5
Create / Assign a case from email by a customer | 6 | 0.75
Options to map customer profiles on all emails if customers are identified. | 6 | 0.75
Customer Communications
Contact Groups
System to enable to create and manage contact groups as emails and mobile numbers for communication purposes within the system. | 8 | 1
Edit/Add and remove contact groups. | 6 | 0.75
Ability to take contacts from AD (Active directory) data structure. | 6 | 0.75
Options to create contact groups for internal users and customers too. | 8 | 1
Send bulk SMS & Emails
Send notification to groups and specific customers within the group or any other system users.
By SMS | 6 | 0.75
By Email | 6 | 0.75
Ability to send SMS/Email to internal staff | 6 | 0.75
Ability to send SMS/Email to customers | 6 | 0.75
Manage and maintain dynamic SMS/Email templates for different types of communications. | 6 | 0.75
SMS integration via telecom provider or SMS gateway (API) | 6 | 0.75
Email integrations should be integrated via Outlook/Exchange systems. | 6 | 0.75
View all SMS and Email history logs | 6 | 0.75
Helpdesk & Templates
Help Desk
Create help topics and contents for all relevant information | 40 | 5
Search and lookup for topics and contents | 16 | 2
Template Management |  | 0
Create response to email templates | 16 | 2
Create social media post / tweet templates | 6 | 0.75
Case / Customer profile inclusions | 6 | 0.75
Email templates | 6 | 0.75
Promotions | 6 | 0.75
Marketing SMS type emails | 6 | 0.75
Case escalation | 6 | 0.75
Case assigned | 6 | 0.75
Case reminder - Email Signatures | 6 | 0.75
Reporting & Insights |  | 0
Standard reports | 24 | 3
Customer Application reports | 6 | 0.75
Application Status reports | 6 | 0.75
Customer reports | 6 | 0.75
Case Profiling report | 6 | 0.75
Feedbacks report | 6 | 0.75
Survey reports | 6 | 0.75
Call center reports and Insights | 6 | 0.75
Customer Email reports | 6 | 0.75
Customer Service KPI reports | 6 | 0.75
Volume per source of cases report | 6 | 0.75
Volume per source of resolution type report | 6 | 0.75
Calculate case turnover type | 6 | 0.75
Customer Demographics (age group, gender, financial, etc.) Segregation reports. | 6 | 0.75
Customizable reporting Options (Dynamic fields and dimensions / segments selection) to create own reports | 6 | 0.75
Customized dashboard creation options. | 6 | 0.75
Options to configure reports on dashboards. | 6 | 0.75
Control access to reports at user levels. | 6 | 0.75
Draft and Save reports | 6 | 0.75
View and search all saved reports. | 6 | 0.75
Scheduled reporting options | 6 | 0.75
Ability to export reports as CSV, Excel, PDF and Image formats. | 6 | 0.75
System Configuration & Support Services |  | 0
Common Settings |  | 0
Company Configurations | 12 | 1.5
Options to manage a central company and its branches. | 12 | 1.5
Options to manage departments and sections at different levels | 12 | 1.5
Add/edit location details | 4 | 0.5
Add edit contact information. | 4 | 0.5
Central System Connection/API Configuration to existing billing system and procurement system. | 12 | 1.5
Email/Exchange settings and configurations. | 12 | 1.5
Telephone Provider Connection/API Configuration and setup. | 16 | 2
SMS provider settings and configuration settings. | 12 | 1.5
Options to configure Media configurations for Facebook andTwitter API’s and Pages. - | 12 | 1.5
Manage Terms and Policies. | 12 | 1.5
IAM |  | 0
System should cater to create roles and control access to different levels within the system for all types of users. | 12 | 1.5
User types and levels are as follows: |  | 0
Admins | 4 | 0.5
Executives | 4 | 0.5
MM (Managers) | 4 | 0.5
Supervisors | 4 | 0.5
Operators | 4 | 0.5
User Access groups (roles and rights) should be made available to give access module wise. | 6 | 0.75
Dynamic user roles and content control by admins to give and remove access to the system. | 8 | 1
System should cater login to the CRM system via AD (Active Directory) credentials using a web login using existing email. | 8 | 1
Application Logs & Audit Logs |  | 0
Audit logs on all data read, create, update and delete. | 6 | 0.75
Error logs on application endpoints. | 6 | 0.75
Communication logs | 6 | 0.75
Synchronization log | 6 | 0.75
Application logs | 6 | 0.75
Both database and files logs. | 6 | 0.75
Payment Logs on all online transactions. | 6 | 0.75
Files & Content Management |  | 0
System should support upload and backup different file types like pdf, image, excel, csv, jpg etc. | 6 | 0.75
Customer related files. | 6 | 0.75
Application related files. | 6 | 0.75
Case related files. | 6 | 0.75
Feedback related files. | 6 | 0.75
Other files. | 6 | 0.75
Data Import & Migrations | 6 | 0.75
System should support Import Excel/CSV data into CRM for customers from existing systems. | 6 | 0.75
System should enable to import data from AD (Active Directory) to enable existing user login migrations. | 6 | 0.75
Customer Portal Requirements
Register / Login
Customer registration using account number and first-time password setup. | 12 | 1.5
New customer registration process and approval by the customer service department. | 8 | 1
New Engineer Portal access registration and approval by customer service department. | 12 | 1.5
Customer and Engineer Login using relevant user credentials. | 12 | 1.5
Password reset for Customers and Engineers. | 4 | 0.5
Applications |  | 0
Customers should be able to apply forms within the customer portal: |  | 0
New Connection | 6 | 0.75
Temporary Connection | 6 | 0.75
New Connection by Provided Panel | 6 | 0.75
Relocate Mdb | 6 | 0.75
Relocate Sdb | 6 | 0.75
Cable Laying Estimate | 6 | 0.75
Reconnection | 6 | 0.75
Temp and Permanent Disconnection | 6 | 0.75
Approve New Meter Model | 6 | 0.75
Replacing Meter | 6 | 0.75
Relocating Meter Board | 6 | 0.75
Existing Meter to Panel | 6 | 0.75
Panel Modification Testing | 6 | 0.75
Existing Meter Testing | 6 | 0.75
New Meter Testing | 6 | 0.75
Temporary Board Connection | 6 | 0.75
New Switch Board Connection (Panel) | 6 | 0.75
New Switch Board Connection Through Existing (Panel) | 6 | 0.75
Service Main Cable Replacement | 6 | 0.75
New Engineer Portal Access Application | 6 | 0.75
Customer Chat
Online chat integrated to website plus customer portal. | 32 | 4
Queries from the chat will be raised within the CRM to customer service representatives. | 16 | 2
Customer Account Profile |  | 0
Customer Account details | 6 | 0.75
Contact details | 4 | 0.5
Manage location of customer | 4 | 0.5
View application history | 4 | 0.5
Payments |  | 0
Customer should be able to make online payments within the customer portal | 32 | 4
Customer should be able to view all the payments made under his/her account | 6 | 0.75
BML, MIB gateway integration | 8 | 1
Security
Protection against injection attacks (SQL, CRLF) | 6
URL encoding, Input validation | 6 | 0.75
Cookie Encryption, Cookie replay attacks | 6 | 0.75
Session hijacking prevention | 6 | 0.75
Cross site scripting and session management | 6 | 0.75
System Features
Authentication, Authorization, Roles | 8 | 1
Exception Handling and Error logging | 8 | 1
Auditing & Logging | 8 | 1
Search Engine | 8 | 1
Notification management | 8 | 1
Reporting Engine | 8 | 1
Workflow management | 8 | 1
Mobile API
Mobile API
SQA
QA & Bug fixing | 626.5 | 78.3125
UAT | 80 | 10
Deployment | 24 | 3
Total | 2875.5 | 359.4375

## Mobile
Agriculture & Food Safety Authority 03 July 2020
| Hrs | Days | Hrs | Days
| Android |  | IOS
Customer Mobile App
Agriculture Directory Services
eServices &
Control Management Systems
Assumption 1.The estimation is for portrait mode. 2.The estimation may vary with the difference in functionality and the design. 3.The estimation is done for native android and iOS app.