## Estimate
Project Name : PRISMA WEB APP ESTIMATE
Inputs |  | Estimation Summary (Hours and Business days)
Risk and/or "unknown" (25% ; 50% ; 25% ; 10%) | 20 | Optimistic hours | 5361.81 | 223.4087 |  | 739.56
Project Complexity scale Extreme(100%); high(50%) ; medium(25%) ; low(10%) | 25 | Most likely hours** | 6166.0815 | 256.9201 | 3200 | 924.45
Average productive hours per day | 8 | Pessimistic hours* | 6970.353 | 290.4314 |  | 1608.543 | Holidays in 2016 | Date
Estimation parameters | Hours | [5 empty] | New Year's Day | 2016-01-01
Requirement gathering | 80 | Expected Duration |  | Hours |  |  | Republic Day | 2016-01-26
Research and analysis | 40 | Triangular distribution method |  | 256.9201 |  |  | Monty Thursday | 2016-03-24
Development | 2364 | Beta distribution (PERT technique) |  | 256.9201 |  |  | Good Friday | 2016-03-25
Design | 120 | [5 empty] | Vishu | 2016-04-14
Testing | 945.6 | Finish Date |  |  |  |  | May Day | 2016-05-01
Training | 0 | Earliest start date | 07/01/2016 |  |  |  | Assembly Elections | 2016-05-16
Documentation | 8 | Earliest completion date | 2017-05-17 | Optimistic |  |  | Onam | 2016-09-13
Meetings | 16 | Earliest completion date | 2017-07-03 | Most likely |  |  | Onam | 2016-09-14
Migration (data or content) | 0 | Earliest completion date | 2017-08-18 | Pessimistic |  |  | Onam | 2016-09-15
Project management | 118.2 | [5 empty] | Gandhi Jayanthi | 2016-10-02
Reports | 0 | Latest start date | 2016-08-01 |  |  |  | Deepavali | 2016-10-29
UAT | 0 | Latest completion date | 2017-06-15 | Optimistic |  |  | Christmas | 2016-12-26
Accessibility test | 0 | Latest completion date | 2017-08-01 | Most likely |  |  | Indepedence Day | 2016-08-15
Pre deployment process | 1 | Latest completion date | 2017-09-18 | Pessimistic |  |  | Ramzan
Deployment | 4
Post production testing | 0 | Pessimistic case buffer (in percentage) |  | 30
Knowledge transfer/ Service transition | 1 | No of resources (This will impact the number of business days to complete and finish date calculation.) on average |  | 3
Marketing | 0
Project retrospective | 0
* Pessimistic hours= Best case hours+ Pessimistic case buffer **Most likely=(Optimistic + Pessimistic )/2 ***Excluded Saturdays, Sundays and state holidays
Total | 3697.8
Note on E13: Prashant Thomas: Please enter your estimated start date here

## Hybrid App
| PRISMA WEB APP ESTIMATE | 2016-06-01
Sl. No. | Product Log | Hours | Comments | Reports
1 | General Ledger |  |  | Reports
| Master |  |  | Reports
| Main Accounts | 5 |  | Reports
| Sub Accounts | 5 |  | Reports
| Account Category | 5 |  | Reports
| Account Type |  |  | Reports
| Listings |  |  | Reports
| Account Type Listing | 4 |  | Reports
| Account Category List | 4 |  | Reports
| Main Accounts List | 4 |  | Reports
| Sub Accounts List | 4 |  | Reports
| Auto Journals |  |  | Reports
| Correction Voucher-ACC ALKOMRA | 5 |  | Reports
| Fixed Voucher | 5 |  | Reports
| Allocation Voucher | 5 |  | Reports
| Reports |  |  | Reports
| Journal Reports |  |  | Reports
| Voucher | 4
| Main Ac Trial Bal | 4
| Journal Daybook | 4
| Consolidate Accountwise Summary | 4
| ALL Ledger | 4
| All Ledger CY | 4
| Main Acct Bal By DVN/DEP | 4
| Sub Acoounts Trial Balance | 4
| Sub Acoounts Trial Balance - All Branches | 4
| Sub Ledger Summary | 4
| unprocessed transactions | 4
| All Ledger for Currency | 4
| Account Ledger Report | 4
| Main Acts Summary for sub Acts | 4
| Pre Paid Expenses allocation | 4
| Chart of Act Listing | 4
| Main Act Trial Balance- Posted | 4
| Main Acts Summary report | 4
| Branch Trial Balance | 4
| Un-Balanced Vouchers | 4
| Branch Trial Balance by sub account | 4
| Employee Loans | 4
| Branch Trial Balance Draft | 4
Comparison Reports
| Years Comparison | 4
| Months Comparison | 4
| Yearly Budget | 4
| monthly budget | 4
| Companies Account Report setUp | 4
| Companies Account Report | 4
| Financial Reports for a year | 4
| Financial Reports for a period | 4
| Financial Reports for a period- Details | 4
| Category Reports Setup | 4
| GL Report by Category | 4
Misc Reports
| Branch Sub Ledger-xxx | 4
Budgeting
| Budget Entry | 5
| Budgets Transfer | 5
| Budget Listing | 5
| New Balance Sheet with Budgeting | 5
Processing
| Operation Transaction Confirmation | 7
| UnConfirmed Operation Transaction | 7
| Financial Transaction Generation | 7
| Accounting Transaction Processing | 7
| Month Closing | 7
| operations Month Closing | 7
| New Year Processing | 7
Queries
| Transaction Details | 5
| Account Balance | 5
| Allocation JV | 5
| Unposted transaction | 5
| Chart of Accounts | 5
| Account Balance | 5
| Financial Ratios | 5
| open Printed Voucher | 5
Journals - Palestine
| Journal Voucher - Palestine | 6
Journals - Hamdania
| Journal Voucher - Hamdania | 1
Journals - Baesha
| Journal Voucher - Baesha | 1
Journals - Bin Laden
| Journal Voucher - Bin Laden | 1
Journals - Nammas
| Journal Voucher - Nammas | 1
Journals - Afrah Alaya
| Journal Voucher - Afrah Alaya | 1
Journals - Bashayer
| Journal Voucher - Bashayer | 1
Reports
2 | Fixed Assets |  |  | Reports
| Master |  |  | Reports
| Asset Master | 4
| Asset Category Master | 4
| Asset Other Master | 4
Listings
| Asset Master Listing | 4
| Location Master | 4
| Category Master | 4
| Person Master | 4
| Reason Master | 4
| Sub category Master | 4
Document Print
| Purchase document | 4
| Transfer Document | 4
| Adjustment Document | 4
Reports
| Monthly depreciation by Category | 4
| Monthly depreciation by Location | 4
| Asset Sale Register | 4
| Asset register Summary by Location | 4
| Asset Register | 4
| AC Fixed Assets | 4
| Asset Barcode Printing | 4
| Fixed Asset depreciation detail | 4
| Fixed Asset Depreciation summary | 4
Processing Agent
| Month Processing | 5
| transaction Confirmation | 5
| Year End | 5 |  | Reports
Transaction- Palestine
| Asset purchase | 7
| Asset Sale | 7
| Asset Transfer | 7
| Asset Adjustment | 7
Transaction- Palestine
| Asset purchase | 1
| Asset Sale | 1
| Asset Transfer | 1
| Asset Adjustment | 1
Transaction- Hamadia
| Asset purchase | 1
| Asset Sale | 1
| Asset Transfer | 1
| Asset Adjustment | 1
Transaction- Baesha
| Asset purchase | 1
| Asset Sale | 1
| Asset Transfer | 1
| Asset Adjustment | 1
Transaction- Bin Laden
| Asset purchase | 1
| Asset Sale | 1
| Asset Transfer | 1
| Asset Adjustment | 1
Transaction- Nammas
| Asset purchase | 1
| Asset Sale | 1
| Asset Transfer | 1
| Asset Adjustment | 1
Transaction- Bashayer
| Asset purchase | 1
| Asset Sale | 1
| Asset Transfer | 1
| Asset Adjustment | 1
Reports
3 | Cash Management |  |  | Reports
| Masters |  |  | Reports
| General Masters | 5 |  | Reports
| Bank Master | 5 |  | Reports
| Update Bank Reconciliation | 5
| Receipt Voucher Book Master | 5
Cash
| Cash Movement Last Date | 5
| Cash Movement as Date & Branch | 5
| Cash Movement for a Period - All Branches | 5
| Close Cash Sales AFRAH ALAYA | 5
| Daily Cash Flow | 5
| Cash Flow for a Period | 5
| Cash Box Report | 5
Loan
| Open Loan | 6
| Loan Expiry Date Entry | 6
| Loan Report | 6 |  | Reports
| Loan Details | 6 |  | Reports
| Redistribute loan expenses | 6 |  | Reports
| NCB Loan Details Report | 6 |  | Reports
| Bank Account |  |  | Reports
| Bank Master Listing | 6 |  | Reports
| Daily Bank Report | 6 |  | Reports
| Bank Reconciliation | 6
| Available Checks | 6
| Paid Check Details | 6
| Void Checks | 6
| Void Checks report | 6 |  | Reports
| LC |  |  | Reports
| LC Open | 6
| LC report | 6
| LC Summary | 6
| LC Status Details | 6
| LC Payment Schedule | 6 |  | Reports
Reports
4 | AR-AP |  |  | Reports
| Master |  |  | Reports
| Customer Credit Control | 6
| Supplier Credit Control | 6
| Link Customer and supplier codes | 6
| Supplier Jeddah | 6
| Supplier ALAYA | 6
| Book Management | 6
| Transaction Credit Control | 6
Listings
| Customer Credit Control | 4
| Supplier Credit Control | 4
| Customer Status | 4
Queries
| Supplier Status | 4
| Customer Payments | 4
| Supplier payment | 4
Reports
Supplier
| Supplier Statement | 2
| Supplier Mailing Labels | 2
| Aged Supplier | 2
| Supplier Statement After Matching | 1
| AC Supplier | 2
| Employee Loans | 2
| Statement Account Customer After Matching | 2
Customer
| Aged Customer | 2
| Statement Account All Customers | 2
| Customer with Sales Man | 2
| Customer Mailing Labels | 2
| Customer With Salesman New | 2
| No Of sales Order by Cust & Sales | 2
| Customer Balance Report | 2
| Customer Statement by Branch | 2
| Sub Ledger Summary | 2
| Customer Statemen after matching | 2
| Customer Statement | 2
| Receipt Voucher Reports | 2
| Payment Voucher | 2
| Aged Customer New | 2
| Customer with Sales Man Factory | 2
| Customer with sales man Alaya | 2
| Payment Voucher | 2
| Receipt Voucher | 2
| Receipt / Payement Voucher (New) | 2
Transaction Entry -Palestine
| Cash Receipt | 6
| Payment Voucher | 6
| Bank deposits | 6
| Bank Payement Voucher | 6 |  | Reports
Transaction Entry -Hamadia
| Cash Receipt | 1
| Payment Voucher | 1
| Bank deposits | 1
| Bank Payement Voucher | 1
Transaction Entry -Baesha
| Cash Receipt | 1
| Payment Voucher | 1
| Bank deposits | 1
Bank Payement Voucher
Transaction Entry -Bin Laden
| Cash Receipt | 1
| Payment Voucher | 1
| Bank deposits | 1
| Bank Payement Voucher | 1
Transaction Entry -Nammas
| Cash Receipt | 1
| Payment Voucher | 1
| Bank deposits | 1
| Bank Payement Voucher | 1
Transaction Entry - Afrah Alaya
| Cash Receipt | 1
| Payment Voucher | 1
| Bank deposits | 1
| Bank Payement Voucher | 1
Transaction Entry -Bashayer
| Cash Receipt | 1
| Payment Voucher | 1
| Bank deposits | 1
| Bank Payement Voucher | 1
Transaction Equipment
| Sales Invoice Equipment | 2
Reports
6 | Inventory |  |  | Reports
| Master |  |  | Reports
| Item Master | 5
| Item Group | 5
| Stores Location | 5
| Other Master | 5
| vehicles | 5
| Drivers | 5
| Inventory Master Listing | 5
| Sevice (non-stock) Master | 5
| Sevice (non-stock) Master (old) | 5
Transaction Listing
| Purchase Return to Supplier | 6
| requisition | 6
| Material Issue | 6
| Material return | 6
| Location Transfer Out | 6
| Location Transfer In | 6
| Adjustment | 6
| DE-Reservation | 6
Document Print
| Goods Receipt | 2
| Purchase Return to Supplier | 2
| Material Issue | 2
| Material return | 2
| Location Transfer out | 2
| Location Transfer In | 2
| reservation | 2
| DE-Reservation | 2
| Reports |  |  | Reports
Location
| Stock Movement by Location | 2
| Valuation by Location | 2
| Stock Unconfirmed | 2
| Daily Stores Movement | 2
| Goods Receipt Costing Sheet | 2
| Transfer Summary by Issue | 2
| Transfer Summary by receiving | 2
| Stock Ledger | 2
| Delivery by Vehicle & Driver | 2
| Unconfirmed stock ledger ALT UOM | 2
| Daily Store Movement General | 2
| Loacation Stock Quantity (UNC) | 2
| Inventory transfer out | 2
| Inventory transfer In | 2
| Summery Unconfirmed Stock Ledger Alt UOM | 2
| Stock Unconfirmed | 2
| Issued Items in a period | 2
| Summary Stock Ledger - Unconfirmed | 2
| TopTen Reports | 2
| Location Stock Quantity (UNC) with Sub Group | 2
| Location Stock by Sub Group | 2
Item reports
| Slow & Fast Moving Items | 2
| Cost deviation report | 2
| batch Movement | 2
| Item Movement with Batch | 2
| Item Movement Stock | 2
| Item List | 2
| Adjustment Type Wise Summary of Adjustment | 2
| Adjustment Type Wise List of Adjustment | 2
| Consolidated Store Receipt Summary | 2
| Item Stock Card | 2
Queries
| Material Requisition Status | 3
| Stock Status | 3
| Alternate Item Stock Status | 3
| Stock Ledger Query ( Only confirmed Documents) | 3
| Stock ledger Query (confirmed & UnConfirmed) | 3
| Item Stock | 3 |  | Reports
| Item Barcode | 3
Transaction- Palestine
| Transfer Out | 5
| Transfer In | 5
| Material Issue | 5
| Material return | 5
| Stock Adjustment | 5
| Stock Taking Entry | 5
| Stock Taking Generation | 5
Transaction- Hamadia
| Transfer Out | 1
| Transfer In | 1
| Material Issue | 1
| Material return | 1
| Stock Adjustment | 1
| Stock Taking Entry | 1
| Stock Taking Generation | 1
Transaction- Baesha
| Transfer Out | 1
| Transfer In | 1
| Material Issue | 1
| Material return | 1
| Stock Adjustment | 1
| Stock Taking Entry | 1
| Stock Taking Generation | 1
Transaction- Bin Laden
| Transfer Out | 1
| Transfer In | 1
| Material Issue | 1
| Material return | 1
| Stock Adjustment | 1
| Stock Taking Entry | 1
| Stock Taking Generation | 1
Transaction- Nammas
| Transfer Out | 1
| Transfer In | 1
| Material Issue | 1
| Material return | 1
| Stock Adjustment | 1
| Stock Taking Entry | 1
| Stock Taking Generation | 1
Transaction- Afrah Alaya
| Transfer Out | 1
| Transfer In | 1
| Material Issue | 1
| Material return | 1
| Stock Adjustment | 1
| Stock Taking Entry | 1
| Stock Taking Generation | 1
Transaction- Bashaer
| Transfer Out | 1
| Transfer In | 1
| Material Issue | 1
| Material return | 1
| Stock Adjustment | 1
| Stock Taking Entry | 1
| Stock Taking Generation | 1
7 | Puchasing
Master
| Supplier Master | 6
| All Master | 6
| Supplier Items | 6
Listings
| Supplier Category | 4
| Service Type | 4
| Supplier Master | 4
| Supplier Items | 4
Transaction Listing
| Requisition | 4
| Enquiry | 4
| Supplier Quotation | 4
| Purchase Order | 4
| Shipment | 4
Document Print
| requisition | 4
| Enquiry to Supplier | 4
| Purcahse Order | 4
Reports
Purchase Inquiry
| Division department wise pending Purchase Requisition | 4
| Suggested Order Report | 4
| Pending Enquiries | 4
| Itemwise Pending Enquiries | 4
| 5 Year Supplierwise summary of purchases | 4
| Comparison of Quotation | 4
| Lead Time Variance | 4
Purchase Orders
| Pending Purchase Orders | 4
| Supplier wise Pending Purchase Order | 4
| Goods in Transit | 4
| Material Purchase Card | 4
| Purchase Price Comparison | 4
| Pending Purchase All Details | 4
| Purchase order by supplier and Items | 4
| GRN List | 4
| Pending Purchase Order -2 | 4
| Item Purchase Report | 4
Queries
| Item Purchase Order | 4
| Purchase Order Status | 4
| Item Purchase Query | 4
Transaction L/C
| Purchase Order L/C | 6
| Shipment Advice L/C | 6
Transaction- Palestine
| Purchase Requisition | 6
| Supplier Inquiry | 6
| Supplier Quotation | 6
| Rated Agreement | 6
| Purchase Order | 6
| Goods Receipt-RM | 6
| Supplier Return | 6
| Supplier Invoice | 6
Transaction- Hamdania
| Purchase Requisition | 1
| Supplier Inquiry | 1
| Supplier Quotation | 1
| Rated Agreement | 1
| Purchase Order | 1
| Goods Receipt-RM | 1
| Supplier Return | 1
| Supplier Invoice | 1
Transaction- Baesha
| Purchase Requisition | 1
| Supplier Inquiry | 1
| Supplier Quotation | 1
| Rated Agreement | 1
| Purchase Order | 1
| Goods Receipt-RM | 1
| Supplier Return | 1
| Supplier Invoice | 1
Transaction- Bin Laden
| Purchase Requisition | 1
| Supplier Inquiry | 1
| Supplier Quotation | 1
| Rated Agreement | 1
| Purchase Order | 1
| Goods Receipt-RM | 1
| Supplier Return | 1
| Supplier Invoice | 1
Transaction- Nammas
| Purchase Requisition | 1
| Supplier Inquiry | 1
| Supplier Quotation | 1
| Rated Agreement | 1
| Purchase Order | 1
| Goods Receipt-RM | 1
| Supplier Return | 1
| Supplier Invoice | 1
Transaction- Afrah Alaya
| Purchase Requisition | 1
| Supplier Inquiry | 1
| Supplier Quotation | 1
| Rated Agreement | 1
| Purchase Order | 1
| Goods Receipt-RM | 1
| Supplier Return | 1
| Supplier Invoice | 1
Transaction- Bashayer
| Purchase Requisition | 1
| Supplier Inquiry | 1
| Supplier Quotation | 1
| Rated Agreement | 1
| Purchase Order | 1
| Goods Receipt-RM | 1
| Supplier Return | 1
| Supplier Invoice | 1
8 | Sales
| Master | 5
| All Master | 5
| Prices | 5
| Customer Master Jeddah | 5
| Customer Master Nammas | 5
| Customer Master Alaya | 5
| Master & Global Customers | 5
Listings
| Price List | 4
| Salesman | 4
| Cusomer Group | 4
| Customer | 4
| Price List WAC | 4
| Customer List by Salesman | 4
Transaction Listing
| Quotation to Customer | 4
| Sales Order | 4
| Delivery Notes | 4
| Invoice | 4
| Sales Return | 4
Document Print
| Quotation to Customer | 4
| Sales Order | 4
| Delivery Notes | 4
| Sales Return | 4
Reports
| Analysis Reports - Portrait | 4
| Sales Net | 4
| Daily Sales Report for Salesman | 4
| Daily Sales Order | 4
| Monthly Sales | 4
| Daily Sales with Cost | 4
| Daily Sales | 4
| Monthly Sales | 4
| Pending Invoice for Delivery | 4
| Item Sales | 4
| Sales Quantity | 4
| Item Sales by Customer | 4
| Item Sales Profit | 4
| Pending Delivery for Invoice | 4
| Pending Sales Order for Delivery Note | 4
| Transaction Credit Ratings | 4
| Salesman Daily Sales | 4
| Sales Order by Salesman/Customer | 4
| Daily Sales with Cost Report and summary Quantity | 4
| Delivery reports | 4
| Pending Sales orders by Item | 4
| Delivery Agenda | 4
| Salesman Commision Report (Summary) | 4
| YTD Stock Movement | 4
| Salesman Sales and Collection Report (not working) | 4
| Monthly Sales and Collection _Details_not_work | 4
| Item Sales by Customer | 4
| Pending Sales orders by Item | 4
| Sales by User and Salesman | 4
| Item Sales by Customer - Additional Info | 4
Queries
| Items Sales | 4
| Customer Sales for an Item | 4
| Customer Sales Query | 4
| Items Sales | 4
| Analysis Report setup | 4
Transaction-Palestine
| Customer Contract | 6
| Casting Order | 6
| Delivery Notes | 6
| Credit Invoice | 6
| Cash Invoice | 6
| Sales Return | 6
| Customer Quotation | 6
| Sales Contract | 6
Transaction-Hamdania
| Customer Contract | 1
| Casting Order | 1
| Delivery Notes | 1
| Credit Invoice | 1
| Cash Invoice | 1
| Sales Return | 1
| Customer Quotation | 1
| Sales Contract | 1
Transaction-Baesha
| Customer Contract | 1
| Casting Order | 1
| Delivery Notes | 1
| Credit Invoice | 1
| Cash Invoice | 1
| Sales Return | 1
| Customer Quotation | 1
| Sales Contract | 1
Transaction-Bin laden
| Customer Contract | 1
| Casting Order | 1
| Delivery Notes | 1
| Credit Invoice | 1
| Cash Invoice | 1
| Sales Return | 1
| Customer Quotation | 1
| Sales Contract | 1
Transaction- Nammas
| Customer Contract | 1
| Casting Order | 1
| Delivery Notes | 1
| Credit Invoice | 1
| Cash Invoice | 1
| Sales Return | 1
| Customer Quotation | 1
| Sales Contract | 1
Transaction- Afrah Alaya
| Customer Contract | 1
| Casting Order | 1
| Delivery Notes | 1
| Credit Invoice | 1
| Cash Invoice | 1
| Sales Return | 1
| Customer Quotation | 1
| Sales Contract | 1
Transaction- Bashayer
| Customer Contract | 1
| Casting Order | 1
| Delivery Notes | 1
| Credit Invoice | 1
| Cash Invoice | 1
| Sales Return | 1
| Customer Quotation | 1
| Sales Contract | 1
Equipment Hire
| Equipment Hire Invoice | 5
Manufacturing
Master
| Master | 6
| Machine | 6
| Bill of Material | 6
Listings
| Finished Goods Bill of Material | 6
| Operation | 6
| Manufacturing Expenses | 6
| Machine Listings | 6
| Raw Material Item Used in BOM | 6
| Formulation | 6
Transaction Listing
| Work Order | 4
| Work Order Actual | 4
| Schedule | 4
| WORK ORDER | 4
Reports
| Work Order Report | 4
| Raw Material Consumption Analysis | 4
| Actual Work Order with Sales | 4
| Work Order Schedule | 4
| Machine schedule | 4
| Machine Productivity Analysis | 4
| Daily Production Report | 4
| Raw Material Usage | 4
| Daily Production by BOM | 4
| RM Usage Quantity Summary / Detail | 4
| RM Quantity Smmary / Detail Sub Category | 4
| Raw Material by Customer | 4
| Production in a Period | 4
Queries
| Work Order Schedule | 4
Transaction-Palestine
| Work Order | 6
| Actual Work Order | 6
| Work Order Schedule | 6
Transaction-Hamdania
| Work Order | 1
| Actual Work Order | 1
| Work Order Schedule | 1
Transaction-Bayesha
| Work Order | 1
| Actual Work Order | 1
| Work Order Schedule | 1
Transaction-Bin Laden
| Work Order | 1
| Actual Work Order | 1
| Work Order Schedule | 1
Transaction-Namaas
| Work Order | 1
| Actual Work Order | 1
| Work Order Schedule | 1
Transaction-Afrah Alaya
| Work Order | 1
| Actual Work Order | 1
| Work Order Schedule | 1
Transaction-Bashayer
| Work Order | 1
| Actual Work Order | 1
| Work Order Schedule | 1
Payroll & HR
Master
| Employee Personal Information | 5
| Employee Financial Information | 5
| Payroll Earning Defenition | 5
| Payroll Deduction defenition | 5
| Human Resources Master Codes | 5
| Payroll Master Codes | 5
| Jobs and Positions | 5
| Employee Organization Structure | 5
| Create / Update Employee Accounts | 5
| Loan Repayment | 5
| Jobs & Positions | 5
Listings
| Deduction | 4
| Earning | 4
| Document | 4
| Religion | 4
| Relation | 4
| Passage | 4
| Approved Position | 4
| Reason Master | 4
| Calender Listing | 4
Transaction Listing
| Leave Application | 6
| Leave Resumption | 6
| Attendance - By Date | 6
| Salary Revision | 6
| Overtime | 6
| Loan Application | 6
| Loan Repayment | 6
| End of Service | 6
| Monthly Overtime Sheet | 6
Reports
| Employee Data | 4
| Employee Pay | 4
| Employee Master Information List | 4
| Manpower movement | 4
| List for Labour Office - ENG | 4
| Employee Leave | 4
| Position Status | 4
| Renewal Due Document | 4
| List of Employees | 4
| Employee Report by Employee/Division/Department/Nationality | 4
| Organization Structure | 4
| Dummy Payroll Slip | 4
| Payroll Slip | 4
| End of Service | 4
| Renewal Due Document -2 | 4
| Employee with no IQAMA Entered | 4
| Unprocessed time sheet report | 4
| Employee Attendance | 4
| EOS Summary | 4
| Positions and Licenced jobs of employees | 4
| Nationality of Employees | 4
| Employee Overtime, Absence Desciplinary Action | 4
Queries
| Employee Query | 4
| Employee Organization Structure | 4
| Organization Structure | 4
Transaction Operations
| Loan Application | 6
| Loan Entry Suspension | 6
| Annual Leave Application | 6
| Return to Work | 6
| End of Service | 6
| Employee Transfer | 6
Transaction-Palestine
| Attendance - By Absence | 6
| Pay Adjustment | 6
| Overtime | 6
| Variable Earn/Deduction | 6
Transaction-Hamdania
| Attendance - By Absence | 1
| Pay Adjustment | 1
| Overtime | 1
| Variable Earn/Deduction | 1
Transaction-Nammas
| Attendance - By Absence | 1
| Pay Adjustment | 1
| Overtime | 1
| Variable Earn/Deduction | 1
Transaction-Afrah Alaya
| Attendance - By Absence | 1
| Pay Adjustment | 1
| Overtime | 1
| Variable Earn/Deduction | 1
Transaction-Bashayer
| Attendance - By Absence | 1
| Pay Adjustment | 1
| Overtime | 1
| Variable Earn/Deduction | 1
Processing
Dummy Processing
| Pre-Payroll Processing | 6
| Payroll Register Before Processing | 6
| Payroll Register Before Processing - Summary | 6
| Filtered Payroll Register before Processing | 6
Final Processing
| Final Payroll Processing | 7
| Payroll Register after Processing' | 7
| Accrual Payroll Processing | 7
System Admin
Common Masters
| Organization Structure | 6
| Currency Definition | 6
| Region / Country / City | 6
| Company Document | 6
Common Master Listings
| Country Listing | 6
| Document Listing - Error | 6
Modules Setup
Payroll
| Annual Leave Opening Balance | 6
| Employee Data Upload | 6
Financials
| Accounting Period Setup | 5
| Valid Combination Setup | 5
| Account Opening Balance Setup - REM | 5
| Company Accounting Year | 5
| Upload JVS | 5
Security setup
| User Groups Setup | 5
| Users Setup | 5
| Accounts Security | 5
| User Password Change | 5
System Interface Setup
| Bilingual Window Title | 4
| Biligual Tab Titles | 4
| Bilingual Labels Setup | 4
| User Interface Setup | 4
| Application Forms Setup | 4
System Parameters
| Company Parameters Setup | 4
| Operations parameters setup | 4
| Common Parameters Setup | 4
| Financial Parameter Setup | 4
| HRMS & Payroll Paraemeters | 4
| HR Company Parameter | 4
System Administration
| Application Modules | 4
| Application Menu | 4
| User Menus Report | 4
| Company Images Path | 4
| User Announcements | 4
| Transaction Setup | 4
| User Mail | 4
| System Codes | 4
| Transaction Approval Setup | 4
| Transaction Tail Setup | 4
| Transaction Flow | 4
| Uploads Type | 4
Email
| Email Settings | 1
| Send E-Mail | 1
| Total | 2361
| Cumulative Total | 2364