## Web
Puffy Paws 23 September 2020
Module | Hours | Man Days | Resources | # | Days | Total
Project Initiation |  |  | UI / UX | 1 | 10 | 10
Business analysis | 24 | 3 | BA | 1 | 3 | 3
Project Management | 74.6 | 9.325 | Tech Writer | 1 | 3 | 3
SRS,FS,User Manual | 24 | 3 | PM | 1 | 9.325 | 9.325
Design and Prototype (mobile & Web) | 80 | 10 | Jr Developer | 1 | 47 | 47 | 94 | 93.25
Development |  |  | Sr Developer | 1 | 47 | 47
Application Basic setup | 0 | 0 | Mobile API | 1 | 23.3125 | 23.3125
User Registration |  |  | QA | 2 | 19.3188 | 38.6375
Home page | 8 | 1 | Total |  |  | 181.275
Forgot password with OTP | 4 | 0.5
Remember password | 4 | 0.5 |  | Days | Months
Registration | 6 | 0.75 | Total Effort | 181.275 | 9.0638
OTP verification | 6 | 0.75 | Delivery Timeline | 79.3187 | 3.9659
Login | 6 | 0.75
Choose emirate | 4 | 0.5
Choose pet type | 4 | 0.5
Services & Products
Services listing | 8 | 1
Product listing | 8 | 1
Services in locality (search) | 8 | 1
Services in facility (Search) | 4 | 0.5
Service details for an instance (Service offerings + Prices + Description + Profile + pictures) | 8 | 1
Services offered by pet | 4 | 0.5
Book service ( Pick time & date based on existing schedule) : slots | 8 | 1
Checkout (edit cart – add , delete) | 8 | 1
Bill summary (Bill details + taxes + total amount + delivery charges) | 6 | 0.75
Apply discount vouchers | 4 | 0.5
Make payment (billing address, delivery address, credit card details) | 8 | 1
Search products by locality or category + other criteria | 6 | 0.75
List shops | 6 | 0.75
Shop page ( List products, prices & description + pictures-thumbnails) | 6 | 0.75
Product details (images + description + prices ) | 6 | 0.75
Checkout (edit cart -add, delete) | 6 | 0.75
Bill summary (Bill details + taxes + total amount + delivery charges) | 4 | 0.5
Cash on delivery option | 4 | 0.5
Apply discount vouchers | 4 | 0.5
Make payment (billing address, delivery address, credit card details) | 8 | 1
Order Confirmation (for both products & services) | 6 | 0.75
Push notifications -> Receive SMS + email notifications of order details (Services + products) | 16 | 2
Integrations
Strype payment gateway | 16 | 2
email | 6 | 0.75
SMS | 8 | 1
OTP generation | 4 | 0.5
My Account (customer)
View Profile | 6 | 0.75
Edit profile | 6 | 0.75
Add / Edit addresses (multiple) | 4 | 0.5
Select language | 40 | 5 | Multilingual considered only for Arabic & English
Manage payment card details | 6 | 0.75
Change password with OTP | 6 | 0.75
About Us | 4 | 0.5
FAQ | 4 | 0.5
Privacy policy | 4 | 0.5
T & C | 4 | 0.5
Contact Us with a simple form | 4 | 0.5
Orders Placed | 6 | 0.75
Orders completed | 4 | 0.5
Orders Cancelled | 4 | 0.5
Providers (available to logged in users)
provider Registration (on main site menu) | 6 | 0.75
Provider dashboard (incoming orders + Bookings + Completed Transations) | 16 | 2
Realtime notifications with alerts | 12 | 1.5
Order details + customer details /w delivery address | 6 | 0.75
Transaction details | 4 | 0.5
Reports on best selling products & services, total order by day/week/month, Total amount received by day/week/month | 16 | 2
Add / manage products (name, description, images, prices, discounts) | 12 | 1.5
Add / manage services (name , description, images, prices, discounts) | 12 | 1.5
manage service schedules | 10 | 1.25
Manage vouchers for services & products (date range, discount, shop, product, service) | 16 | 2
Communication dashboard to send / receive notification to customers / providers / admins | 24 | 3
Update profile | 4 | 0.5
Customer care Agent
Customer care dashboard (Orders received, Orders completed) | 16 | 2
Order cancellations | 6 | 0.75
Manage disputes | 6 | 0.75
Replace orders | 12 | 1.5
refill orders | 6 | 0.75
Track orders | 6 | 0.75
Cancel and book service slots | 8 | 1
reschedule service slots | 6 | 0.75
Update order status | 4 | 0.5
Communication dashboard to send / receive notification to customers / providers / admins | 4 | 0.5
Admin
Create provider accounts | 4 | 0.5
Create customer care agents | 4 | 0.5
Update customer info | 4 | 0.5
Hold & Activate provider activities | 8 | 1
Access audit trail of activities conducted by Customer care Agent | 12 | 1.5
View audit trail of providers | 12 | 1.5
Dashboard for analytics related to the performance of the platform | 24 | 3
Add advertisements / display advertisements on site | 16 | 2
Rank provider priority in search listings | 12 | 1.5
Manage products / prices | 6 | 0.75
Manage vouchers for services & products (date range, discount, shop, product, service) | 16 | 2
Communication dashboard to send / receive notification to customers / providers / admins | 4 | 0.5
System
Auditing & logging (CCA + Providers + customers) | 12 | 1.5
Protection against injection attacks (SQL, CRLF) | 6 | 0.75
URL encoding, Input validation | 6 | 0.75
Cookie Encryption, Cookie replay attacks | 6 | 0.75
Session hijacking prevention | 6 | 0.75
Cross site scripting and session management | 6 | 0.75
Authentication, Authorization, Roles | 6 | 0.75
Exception Handling and Error logging | 6 | 0.75
Notification management | 6 | 0.75
Reporting Engine | 6 | 0.75
Workflow management | 16 | 2
Search Engine | 6 | 0.75
Mobile API
Mobile api |  |  | 186.5 | 23.3125
SQA
QA & Bug fixing | 261.1 | 32.6375
UAT | 40 | 5
Deployment | 8 | 1
Total | 1257.7 | 157.2125
vvvcnmnmvbn

## Mobile
PuffyPaws 23 September 2020
| Hrs | Days | Resources | # | Days | Total
| Flutter |  | AndroidDeveloper | 1 |  | 0
User Registration |  |  | iOS Developer | 1 |  | 0
Splash Screen | 10 | 1.25 | QA | 1 | #REF! | #REF!
Forgot password with OTP | 12 | 1.5 | Total |  |  | #REF!
Remember password | 12 | 1.5
Registration | 12 | 1.5 |  | Days | Months | With 1.5 resources (maybe)
OTP verification | 10 | 1.25 | Total effort | 115.5187 | 5.7759 | 3.8506
Login | 10 | 1.25 | dellivery time | 115.5187 | 5.7759
Choose emirate | 10 | 1.25
Choose pet type | 8 | 1
Services & Products
Services listing | 16 | 2
Product listing | 10 | 1.25
Services in locality (search) | 10 | 1.25
Services in facility (Search) | 8 | 1
Service details for an instance (Service offerings + Prices + Description + Profile + pictures) | 24 | 3
Services offered by pet | 16 | 2
Service description page | 12 | 1.5
Book service ( Pick time & date based on existing schedule) : Slots | 12 | 1.5
Checkout (edit cart – add , delete) | 16 | 2
Bill summary (Bill details + taxes + total amount + delivery charges) | 16 | 2
Apply discount vouchers | 12 | 1.5
Make payment (billing address, delivery address, credit card details) | 24 | 3
Search products by locality or category + other criteria | 12 | 1.5
List shops | 12 | 1.5
Shop page ( List products, prices & description + pictures-thumbnails) | 16 | 2
Product details (images + description + prices ) | 12 | 1.5
Chaeckout (edit cart -add, delete) | 8 | 1
Bill summary (Bill details + taxes + total amount + delivery charges) | 8 | 1
Cash on delivery option | 8 | 1
Apply discount vouchers | 12 | 1.5
Make payment (billing address, delivery address, credit card details) | 10 | 1.25
Order Confirmation (for both products & services) | 16 | 2
Push notifications -> Receive SMS + email notifications of order details (Services + products) | 24 | 3
Integrations
Strype payment gateway | 24 | 3
email | 16 | 2
SMS | 16 | 2
OTP generation | 10 | 1.25
My Account
View Profile | 16 | 2
Edit profile | 16 | 2
Add / Edit addresses (multiple) | 21 | 2.625
Select language | 10 | 1.25
Manage payment card details | 16 | 2
Change password | 12 | 1.5
About Us | 12 | 1.5
FAQ | 12 | 1.5
Privacy policy | 12 | 1.5
T & C | 12 | 1.5
Contact Us with a simple form | 16 | 2
Orders Placed | 10 | 1.25
Orders completed | 10 | 1.25
Orders Cancelled | 10 | 1.25
SQA
QA & Bug fixing | 227.15 | 28.3938
UAT | 40 | 5
Deployment | 8 | 1
Total | 924.15 | 115.5187
Assumption 1.The estimation is for portrait mode. 2.The estimation may vary with the difference in functionality and the design. 3.The estimation is done for hybrid app using flutter.